## WilhIssueBluePrintRollout
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Roll-out Wilhelmsen | Project
0. Project Management | Epic | Roll-out Wilhelmsen
0_1 - Update_all_related_dates_in_this_project | Task | 0. Project Management |  |  |  | 1
0_2 - Update_roll-out_plan | Task | 0. Project Management |  |  | File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E | 1
0_3 - Internal_meetings | Task | 0. Project Management |  |  | Task to log general internal meetings | 10
1. Process Discovery | Epic | Roll-out Wilhelmsen
1_1 - Data_Acquisition | Task | 1. Process Discovery | 1_1 - Data_Acquisition | 1_2 - Requirement_Gathering |  | 3
Training & Posting Data Request | Sub-task | 1_1 - Data_Acquisition
Posting Data Analysis | Sub-task | 1_1 - Data_Acquisition |  |  | Analyze posting data and determine top suppliers (>90% coverage)
Training Data Assessment | Sub-task | 1_1 - Data_Acquisition |  |  | Check if all top suppliers has sample documents with specified naming convention
Request additional documents if required | Sub-task | 1_1 - Data_Acquisition |  |  | Request if any top supplier document is missing
Training Data/Document Set Preparation | Sub-task | 1_1 - Data_Acquisition |  |  | Prepare training, annotation documents
Match training documents with posting data | Sub-task | 1_1 - Data_Acquisition |  |  | Match selected documents with posting data
1_2 - Requirement_Gathering | Task | 1. Process Discovery | 1_2 - Requirement_Gathering | 2_1 - Capturing_Model_Training,2_2 - Enrichment_Model_Training |  | 3
Provide Digitalization Details form to Local Finance Team and ask examples for Edge cases | Sub-task | 1_2 - Requirement_Gathering |  |  | EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y
Provide Assessment Gathering and Training Data Folders | Sub-task | 1_2 - Requirement_Gathering |  |  | Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data
[ML] Demo Project Creation for Requirements Gathering Meeting | Sub-task | 1_2 - Requirement_Gathering |  |  | Take the example from [ML] Project - [OC Entities][Phase 3] Oman
Requirement Gathering Meeting | Sub-task | 1_2 - Requirement_Gathering
Request examples for Edge cases | Sub-task | 1_2 - Requirement_Gathering
Complete full set-up of training data for all of the top suppliers with Edge cases shared during requirements session | Sub-task | 1_2 - Requirement_Gathering
Update WHL Requirement List | Sub-task | 1_2 - Requirement_Gathering |  |  | https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Requirement Gathering Finalization | Sub-task | 1_2 - Requirement_Gathering
2. Model Training | Epic | Roll-out Wilhelmsen
2_1 - Capturing_Model_Training | Task | 2. Model Training | 2_1 - Capturing_Model_Training | 2_3 - Model_Fine_Tuning |  | 3
Create baseline (groundtruth) project to annotate [ML] | Sub-task | 2_1 - Capturing_Model_Training |  |  | Take the example from [ML] Project - NZ_Annotation
Upload documents selected for annotation to groundtruth project (Top suppliers and Edge cases) | Sub-task | 2_1 - Capturing_Model_Training
Create a task for annotation (add details per requirements) | Sub-task | 2_1 - Capturing_Model_Training
Validate annotation results with posting data | Sub-task | 2_1 - Capturing_Model_Training
Improve annotation quality based on validation with posting data | Sub-task | 2_1 - Capturing_Model_Training
Create Training Project [ML] | Sub-task | 2_1 - Capturing_Model_Training |  |  | Take the example from[ML] Project - [Training][PROD][NZ]
Upload selected training documents from baseline project to Training Project [ML] | Sub-task | 2_1 - Capturing_Model_Training
Create QA Project [ML] | Sub-task | 2_1 - Capturing_Model_Training |  |  | Take the example from [ML] Project - [QA] NZ
Configure QA project with Composite Enrichment Index | Sub-task | 2_1 - Capturing_Model_Training
Create LLM Prompting Service [ML] | Sub-task | 2_1 - Capturing_Model_Training
Upload baseline (groundtruth) documents to QA Project [ML] | Sub-task | 2_1 - Capturing_Model_Training
Create Error Analysis Dashboard | Sub-task | 2_1 - Capturing_Model_Training
Analyze QA results and accuracy | Sub-task | 2_1 - Capturing_Model_Training
2_2 - Enrichment_Model_Training | Task | 2. Model Training | 2_2 - Enrichment_Model_Training | 2_3 - Model_Fine_Tuning |  | 1
Create IMP training project [TEST] | Sub-task | 2_2 - Enrichment_Model_Training
Contact with IM to enable IMP pipeline | Sub-task | 2_2 - Enrichment_Model_Training
Upload documents to IMP training project | Sub-task | 2_2 - Enrichment_Model_Training
Train suppliers using documents uploaded to IMP project | Sub-task | 2_2 - Enrichment_Model_Training
2_3 - Model_Fine_Tuning | Task | 2. Model Training | 2_3 - Model_Fine_Tuning | 3_1 - Create_Projects_[TEST] |  | 1
Improve/Optimize LLM Prompting Service prompt with Error Analysis results | Sub-task | 2_3 - Model_Fine_Tuning
Add additional suppliers to IMP project if required | Sub-task | 2_3 - Model_Fine_Tuning
3.Studio Configuration | Epic | Roll-out Wilhelmsen
3_1 - Create_Projects_[TEST] | Task | 3.Studio Configuration | 3_1 - Create_Projects_[TEST] | 3_2 - Configure_Projects_[TEST] |  | 1
Configure project schema with agreed upon requirements lists points | Sub-task | 3_1 - Create_Projects_[TEST]
Add/Change accounting supplier/customer party | Sub-task | 3_1 - Create_Projects_[TEST]
Add/Change company name validation | Sub-task | 3_1 - Create_Projects_[TEST]
Add/check vat id validation | Sub-task | 3_1 - Create_Projects_[TEST]
Check/change duplicate source data point | Sub-task | 3_1 - Create_Projects_[TEST]
(Optional) Add translation data points if required | Sub-task | 3_1 - Create_Projects_[TEST]
3_2 - Configure_Projects_[TEST] | Task | 3.Studio Configuration | 3_2 - Configure_Projects_[TEST] | 4_1 - Testing_Set-up |  | 1
Create a COE ticket to configure Rerouting rules | Sub-task | 3_2 - Configure_Projects_[TEST] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
Contact IM for composite enrichment set-up configuration | Sub-task | 3_2 - Configure_Projects_[TEST]
Contact IM to create and configure LLM prompting service | Sub-task | 3_2 - Configure_Projects_[TEST]
Contact IM to enable newly created [TEST] outbound projects for duplicate check pipeline (Connect projects to IMP pipeline) | Sub-task | 3_2 - Configure_Projects_[TEST]
Contact IM to add outbound projects to XML UBL 2.1 endpoint [TEST] | Sub-task | 3_2 - Configure_Projects_[TEST]
Contact IM to enable translation for outbound projects | Sub-task | 3_2 - Configure_Projects_[TEST]
4. Testing | Epic | Roll-out Wilhelmsen
4_1 - Testing_Set-up | Task | 4. Testing | 4_1 - Testing_Set-up | 4_2 - Functional_Testing_by_HY |  | 1
Copy and update Test Workbook for new phase if needed | Sub-task | 4_1 - Testing_Set-up |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
4_2 - Functional_Testing_by_HY | Task | 4. Testing | 4_2 - Functional_Testing_by_HY | 4_3 - Testing_by_Wilhelmsen |  | 1
Compare project set-up with requirements list for specific country | Sub-task | 4_2 - Functional_Testing_by_HY |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Upload documents to Gateway project and test routing | Sub-task | 4_2 - Functional_Testing_by_HY
Test advanced duplicate testing | Sub-task | 4_2 - Functional_Testing_by_HY
Test if enrichment is working properly with company code filter | Sub-task | 4_2 - Functional_Testing_by_HY
Test if XML endpoint if available for outbound projects (Postman) | Sub-task | 4_2 - Functional_Testing_by_HY
[Optional] Test translation feature | Sub-task | 4_2 - Functional_Testing_by_HY
4_3 - Testing_by_Wilhelmsen | Task | 4. Testing | 4_3 - Testing_by_Wilhelmsen | 5_1 - Create_Projects_[PROD] |  | 3
Add projects to Requirements List | Sub-task | 4_3 - Testing_by_Wilhelmsen
Share Test Workbook | Sub-task | 4_3 - Testing_by_Wilhelmsen |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Wilhelmsen to configure integration & perform System Integration Testing (SIT) | Sub-task | 4_3 - Testing_by_Wilhelmsen
Wilhelmsen to perform Functional Testing | Sub-task | 4_3 - Testing_by_Wilhelmsen
Wilhelmsen to perform User Acceptance Testing (UAT) | Sub-task | 4_3 - Testing_by_Wilhelmsen
Testing Support Tasks (Issue Resolution) | Sub-task | 4_3 - Testing_by_Wilhelmsen
Analysis & Finalization of Tests | Sub-task | 4_3 - Testing_by_Wilhelmsen
5. Deployment to Production | Epic | Roll-out Wilhelmsen
5_1 - Create_Projects_[PROD] | Task | 5. Deployment to Production | 5_1 - Create_Projects_[PROD] | 5_2 - Configure_Projects_[PROD] |  | 1
Configure project schema with agreed upon requirements lists points | Sub-task | 5_1 - Create_Projects_[PROD]
Check accounting supplier/customer party | Sub-task | 5_1 - Create_Projects_[PROD]
Check company name validation | Sub-task | 5_1 - Create_Projects_[PROD]
Check Vat Id validation | Sub-task | 5_1 - Create_Projects_[PROD]
Check duplicate source data point | Sub-task | 5_1 - Create_Projects_[PROD]
(Optional) Check translation data points if required | Sub-task | 5_1 - Create_Projects_[PROD]
5_2 - Configure_Projects_[PROD] | Task | 5. Deployment to Production | 5_2 - Configure_Projects_[PROD] | 5_3 - Smoke_test |  | 1
Create a COE ticket to configure Rerouting rules | Sub-task | 5_2 - Configure_Projects_[PROD] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
Contact IM for composite enrichment set-up configuration | Sub-task | 5_2 - Configure_Projects_[PROD]
Contact IM to create and configure LLM prompting service | Sub-task | 5_2 - Configure_Projects_[PROD]
Contact IM to enable newly created [PROD] outbound projects for duplicate check pipeline (Connect projects to IMP pipeline) | Sub-task | 5_2 - Configure_Projects_[PROD]
Contact IM to add outbound projects to XML UBL 2.1 endpoint [PROD] | Sub-task | 5_2 - Configure_Projects_[PROD]
Contact IM to enable translation for outbound projects | Sub-task | 5_2 - Configure_Projects_[PROD]
5_3 - Smoke_test | Task | 5. Deployment to Production | 5_3 - Smoke_test | 5_4 - Cutover_and_Go_Live |  | 1
Compare project set-up with [TEST] project | Sub-task | 5_3 - Smoke_test
Upload documents to Gateway project and test routing | Sub-task | 5_3 - Smoke_test
Test advanced duplicate testing | Sub-task | 5_3 - Smoke_test
Test if enrichment is working properly with company code filter | Sub-task | 5_3 - Smoke_test
Test if XML endpoint if available for outbound projects (Postman) | Sub-task | 5_3 - Smoke_test
[Optional] Test translation feature | Sub-task | 5_3 - Smoke_test
5_4 - Cutover_and_Go_Live | Task | 5. Deployment to Production | 5_4 - Cutover_and_Go_Live | 6_1 - Hypercare_Issues |  | 1
Create and share cutover Plan | Sub-task | 5_4 - Cutover_and_Go_Live |  |  | Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7
Add projects to Requirements List | Sub-task | 5_4 - Cutover_and_Go_Live |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Inform customer for Production Readiness & initiate Production deployment | Sub-task | 5_4 - Cutover_and_Go_Live
6. Hypercare Phase | Epic | Roll-out Wilhelmsen
6_1 - Hypercare_Issues | Task | 6. Hypercare Phase | 6_1 - Hypercare_Issues | 6_2 - Handover_to_Hypatos_Customer_Care |  | 5
Create and share Hypercare Issue Log | Sub-task | 6_1 - Hypercare_Issues |  |  | Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk
Hypercare issue resolutions | Sub-task | 6_1 - Hypercare_Issues
6_2 - Handover_to_Hypatos_Customer_Care | Task | 6. Hypercare Phase | 6_2 - Handover_to_Hypatos_Customer_Care | 7_1 - Update_initial_design_sign-off_if_needed,7_2 - Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint |  | 1
Update CC Handover Page | Sub-task | 6_2 - Handover_to_Hypatos_Customer_Care
7. Documentation Update | Epic | Roll-out Wilhelmsen
7_1 - Update_initial_design_sign-off_if_needed | Task | 7. Documentation Update |  |  |  | 1
7_2 - Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint | Task | 7. Documentation Update |  |  |  | 1