## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-5644 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-11-19 | 2024-11-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5643 | Lessons learned | Task | Delivery | To Do | 2024-11-19 | 2024-11-20 |  | stephan.kuche |  | []
TD-5642 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-11-18 | 2024-11-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5641 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | []
TD-5640 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | []
TD-5639 | Hypercare_Phase | Task | Delivery | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5638 | MileStone_Go Live | Task | Delivery | To Do | 2024-10-27 | 2024-10-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5637 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5636 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5635 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5634 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5633 | Deployment | Task | Delivery | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5632 | Delivery | Epic | Pilot | To Do | 2024-10-25 | 2024-11-20 |  | stephan.kuche |  | []
TD-5631 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-10-24 | 2024-10-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5630 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5629 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5628 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5627 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5626 | User Acceptance Testing | Task | Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-5625 | MileStone_SIT_approval | Task | Testing | To Do | 2024-10-02 | 2024-10-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5624 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5623 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5622 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5621 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5620 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5619 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5618 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5617 | System Integration Test (E2E) | Task | Testing | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5616 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5615 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5614 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5613 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-5612 | Functional_Testing | Task | Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5611 | Testing | Epic | Pilot | To Do | 2024-09-22 | 2024-10-25 |  | stephan.kuche |  | []
TD-5610 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5609 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5608 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5607 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5606 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5605 | Schema Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5604 | Configure Translation Service | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5603 | Create LLM Config | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5602 | Configure ReRouting Rules | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5601 | Create projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5600 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5599 | Studio Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5598 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5597 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5596 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5595 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5594 | Application Implementation | Epic | Pilot | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5593 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-29 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5592 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5591 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-08-01 | 2024-08-04 |  | stephan.kuche |  | []
TD-5590 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5589 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | []
TD-5588 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5587 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5586 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5585 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5584 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5583 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5582 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5581 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | []
TD-5580 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | []
TD-5579 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5578 | Integration Implementation | Epic | Pilot | To Do | 2024-08-01 | 2024-09-29 |  | stephan.kuche |  | []
TD-5577 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5576 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5575 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5574 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5573 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5572 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5571 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5570 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5569 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5568 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5567 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5566 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5565 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5564 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5563 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5562 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5561 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5560 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5559 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5558 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5557 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5556 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5555 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5554 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5553 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5552 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5551 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5550 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5549 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5548 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5547 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5546 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5545 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5544 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5543 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5542 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5541 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5540 | Machine Learning | Epic | Pilot | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5539 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-09-07 | 2024-09-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-5538 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5537 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5536 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5535 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5534 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5533 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5532 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5531 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5530 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5529 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5528 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-5527 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5526 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5525 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5524 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5523 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5522 | Functional & Technical Solution Design | Task | Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5521 | Design | Epic | Pilot | To Do | 2024-08-24 | 2024-09-08 |  | stephan.kuche |  | []
TD-5520 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-08-23 | 2024-08-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5519 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5518 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5517 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | CUS Deliverable | stephan.kuche |  | []
TD-5516 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | CUS Deliverable | stephan.kuche |  | []
TD-5515 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-5514 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5513 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5512 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-5511 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5510 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5509 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5508 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | ERP PO data | stephan.kuche |  | []
TD-5507 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | ERP master data | stephan.kuche |  | []
TD-5506 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-5505 | Requirement Analysis | Task | Assessment | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5504 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-5503 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5502 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5501 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5500 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5499 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5498 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5497 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5496 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5495 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5494 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5493 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5492 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5491 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5490 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5489 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5488 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5487 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5486 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5485 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5484 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5483 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5482 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5481 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-5480 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5479 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-5478 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5477 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-5476 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5475 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5474 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | [TEST] | stephan.kuche |  | []
TD-5473 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5472 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5471 | Data Acquisition | Task | Assessment | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5470 | Assessment | Epic | Pilot | To Do | 2024-08-06 | 2024-08-24 |  | stephan.kuche |  | []
TD-5469 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-08-01 | 2024-08-02 |  | stephan.kuche |  | []
TD-5468 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5467 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5466 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5465 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-5464 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-5463 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5462 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5461 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5460 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5459 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5458 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5457 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Optional | stephan.kuche |  | []
TD-5456 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5455 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5454 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5453 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5452 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5451 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5450 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-5449 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5448 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5447 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5446 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5445 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Including all relevant Files | stephan.kuche |  | []
TD-5444 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5443 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-5442 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5441 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5440 | Project Set up | Task | Project Management | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5439 | Project Management | Epic | Pilot | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5438 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-11-29 | 2024-11-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-5437 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5436 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5435 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5434 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5433 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 | recommendations to improve model performance | stephan.kuche |  | []
TD-5432 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5431 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5430 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5429 | Request UserList | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5428 | User Onboarding | Task | User Training | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-5427 | User Training | Epic | Pilot | To Do | 2024-08-01 | 2024-11-30 |  | stephan.kuche |  | []
TD-5426 | Pilot | Project |  | To Do | 2024-08-01 | 2024-11-30 |  | stephan.kuche |  | []