## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-3878 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3877 | Assessment | Epic | Rollout | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | []
TD-3876 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3875 | Project Management | Epic | Rollout | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3874 | Rollout | Project |  | To Do | 2024-01-01 | 2024-01-11 |  | stephan.kuche |  | []
TD-3873 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3872 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | []
TD-3871 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3870 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3869 | Pilot | Project |  | To Do | 2024-01-01 | 2024-01-11 |  | stephan.kuche |  | []
TD-3868 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3867 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-11 |  | stephan.kuche |  | []
TD-3866 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3865 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3864 | Pilot | Project |  | To Do | 2024-01-01 | 2024-01-11 |  | stephan.kuche |  | []