## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-09-01 | R001 | Data Acquisition dependent on SAP addon release and installation - could break project timeline | High | A001 | LOH SAP DEV Team onboarding for integration implementation. LOH PM to raise ressource request to the respective team and actively following up. |  | Open
Open | 2024-09-01 | R002 | AFI integration might take more ressources than expected | High | A002 | Discuss Integration Design extensively and support if needed |  | Open
 | 2024-09-01 |  |  | High | A003 | Hypatos x LOH to revisit Integration and Project Timelines based on resource onboarding. Dependent on A001. Bi-Weekly follow ups. |  | 
 | 2024-09-01 |  |  | High | A004 | Allow a buffer for SIT |  | 
Open | 2024-09-01 | R003 | TBD | High | A005 | TBD |  | Open
Open | 2024-09-01 | R004 | TBD | High | A006 | TBD |  | Open
Open | 2024-09-01 | R005 | Scope of Implementation not clear - expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-09-01 | R006 | Projekt Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in Q4 2024
Timeline subject to change – Assuming that Machine Learning Trainingdata is available on time.
Project Milestone
Go Live
SteerCo Meeting
Workshop
Aug
Sep
Oct
Nov
Dec
Jan
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
01
02
03
Responsible
Activity
CUS, HY
Wave 1,2,n (CompCode xx-xx)
CUS, HY
Delivery (GoLive & Hypercare)
Hypercare Closing & Handover Cus. Care
CUS, HY
Testing (FT & SIT & UAT)
UAT approved & Go Live decision
CUS, HY
Integration Implementation
HY
Application Implement (Studio Config.)
HY
Machine Learning ( Model training + Optimization)
CUS, HY
Design (Technical+Functional)
Kickof WS
CUS, HY
Assessment (Requirement + Data Gathering)
Training Data Confirm.
CUS, HY
Project Management
CUS, HY
User Training
User Training Completed
Solution D.WS
Tech.WS
26.9.24
Ass. WS
SoW & Solution Design Sign-off
Deploy & Roll-out
Implement & Test
Assess & Design
Initiate & Plan
SOW = Statement of Work FT= Functional Testing
SIT= System Integration Testing
UAT= User Acceptance Testing

## Slide 10: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 11: Thank you
Stephan Kuche
Sr. Implementation Manager
stephan.kuche@hypatos.ai
+49 (0) 179 340 36 49
hypatos.ai
Andreas Mösinger
Project Manager
andreas.moesinger@de.ey.com
+49 (0) 160 939 21104