## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-01-10 | R001 | Data Acquisition dependent on SAP addon release and installation - could break project timeline | High | A001 | FNK SAP DEV Team onboarding for integration implementation. FNK PM to raise ressource request to the respective team and actively following up. |  | Open
Open | 2024-01-10 | R002 | xSuite integration might take more ressources than expected | High | A002 | Discuss Solution Design extensively and support if needed |  | Open
 |  |  |  | High | A003 | Hypatos x FNK to revisit Integration and Project Timelines based on resource onboarding. Dependent on A001. Bi-Weekly follow ups. |  | Open
 |  |  |  | High | A004 | Allow a buffer for SIT |  | Open
Open | 2024-01-10 | R003 | PO Matching config and ML Training takes more ressources than expected | High | A005 | Schedule a session with HY SAP and Product Team to |  | Open
Open | 2024-01-10 | R004 | Poor PO Matching Enrichment Quality | Medium | A006 | Ensure that annoation of Line item is done right by providing annotation guideline |  | Open
Open | 2024-01-10 | R005 | Scope of Implementation not clear - customer expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-01-10 | R006 | Project Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in April 2024
Scope, Deliverables and Timeline
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
50
51
52
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
  Funke & HY
Wave 1 (BUKRS xx – xx)
Wave 2 (BUKRS xx – xx)
  Funke & HY
Activities
  Responsible
CW
  Funke & HY
Go-live & Continuous Improvement
Customer Care Support
Hypercare
  Funke
Pilot Phase in Productive System
Roll-out Go/NoGo
  Funke & HY
Testing Phase (SIT & UAT)
Go/NoGo
SAP Addon
Installation
SIT Approved
UAT
SIT
  Funke & HY
System Integration implementation
  HY
Studio and Insights Configuration
Studio V2
Studio V1
  HY
Implementation Phase (3 months)
Model V2
Model V1
  Funke & HY
Assessment & Design of New AP Process
Tech Solution confirmed
  Funke
Providing of training data (images + posting data)
Training data confirmed
  Funke & HY
User Onboarding & Training
Kickoff 15.12.
Go-live Q&A
Leverage User Experience
User Onboarding
  Funke & HY
Today
Project Management
SOW Sign Off
Continuation decision
Go-live Data decision
Technical Workshop
Functional Workshop
Assessment Workshop
ML model training and optimization
Milestone
Project Deliverable
Meeting
SOW = Statement of Work SIT= System Integration Testing
UAT= User Acceptance Testing
Timeline subject to change – pending on Assessment, Functional & Technical Workshops outcomes
Deploy & Roll-out
Configure AI
Implementation & Validation
Design
PMO

## Slide 10: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 11: Thank you
Yavuz Güney
Implementation Manager
stephan.kuche@hypatos.ai
+49 179 340 36 49
hypatos.ai
Dr. Ulrich Erxleben
Chief Executive Officer
uli.erxleben@hypatos.ai +49 157 736 362 22 hypatos.ai