## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-6899 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-04-26 | 2024-04-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-6898 | Lessons learned | Task | Delivery | To Do | 2024-04-26 | 2024-04-27 |  | stephan.kuche |  | []
TD-6897 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | []
TD-6896 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | []
TD-6895 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | []
TD-6894 | Hypercare_Phase | Task | Delivery | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-6893 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | []
TD-6892 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | []
TD-6891 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | []
TD-6890 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | []
TD-6889 | Deployment | Task | Delivery | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-6888 | Delivery | Epic | POC | To Do | 2024-04-03 | 2024-04-27 |  | stephan.kuche |  | []
TD-6887 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6886 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6885 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6884 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 | recommendations to improve model performance | stephan.kuche |  | []
TD-6883 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6882 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6881 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6880 | Request UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6879 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6878 | User Training | Epic | POC | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-6877 | 7_2_-_Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint | Task | 7_Documentation_Update | To Do | 2025-01-28 | 2025-01-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': '6_2_-_Handover_to_Hypatos_Customer_Care'}]
TD-6876 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-13 | 2024-04-03 |  | stephan.kuche |  | []
TD-6875 | 7_1_-_Update_initial_design_sign-off_if_needed | Task | 7_Documentation_Update | To Do | 2025-01-28 | 2025-01-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': '6_2_-_Handover_to_Hypatos_Customer_Care'}]
TD-6874 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-13 | 2024-04-03 |  | stephan.kuche |  | []
TD-6873 | 7_Documentation_Update | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-28 | 2025-01-29 |  | stephan.kuche |  | []
TD-6872 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-03-13 | 2024-04-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-6871 | Update_CC_Handover_Page | Sub-task | 6_2_-_Handover_to_Hypatos_Customer_Care | To Do | 2025-01-27 | 2025-01-28 |  | stephan.kuche |  | []
TD-6870 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-6869 | 6_2_-_Handover_to_Hypatos_Customer_Care | Task | 6_Hypercare_Phase | To Do | 2025-01-27 | 2025-01-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '7_1_-_Update_initial_design_sign-off_if_needed'}, {'LinkType': 'blocks', 'LinkedIssueSummary': '7_2_-_Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '6_1_-_Hypercare_Issues'}]
TD-6868 | Document inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6867 | Hypercare_issue_resolutions | Sub-task | 6_1_-_Hypercare_Issues | To Do | 2025-01-22 | 2025-01-27 |  | stephan.kuche |  | []
TD-6866 | Document inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-6865 | Create_and_share_Hypercare_Issue_Log | Sub-task | 6_1_-_Hypercare_Issues | To Do | 2025-01-22 | 2025-01-27 | Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk | stephan.kuche |  | []
TD-6864 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-6863 | 6_1_-_Hypercare_Issues | Task | 6_Hypercare_Phase | To Do | 2025-01-22 | 2025-01-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '6_2_-_Handover_to_Hypatos_Customer_Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '5_4_-_Cutover_and_Go_Live'}]
TD-6862 | Run Document outbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-6861 | 6_Hypercare_Phase | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-22 | 2025-01-28 |  | stephan.kuche |  | []
TD-6860 | Inform_customer_for_Production_Readiness_&__initiate_Production_deployment | Sub-task | 5_4_-_Cutover_and_Go_Live | To Do | 2025-01-21 | 2025-01-22 |  | stephan.kuche |  | []
TD-6859 | Run Posting Data inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6858 | Run Document inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-6857 | Add_projects_to_Requirements_List | Sub-task | 5_4_-_Cutover_and_Go_Live | To Do | 2025-01-21 | 2025-01-22 | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT | stephan.kuche |  | []
TD-6856 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-6855 | Create_and_share_cutover_Plan | Sub-task | 5_4_-_Cutover_and_Go_Live | To Do | 2025-01-21 | 2025-01-22 | Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7 | stephan.kuche |  | []
TD-6854 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | []
TD-6853 | 5_4_-_Cutover_and_Go_Live | Task | 5_Deployment_to_Production | To Do | 2025-01-21 | 2025-01-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '6_1_-_Hypercare_Issues'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '5_3_-_Smoke_test'}]
TD-6852 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | []
TD-6851 | (Optional)_Test_translation_feature | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6850 | Share Testing Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | []
TD-6849 | Test_if_XML_endpoint_if_available_for_outbound_projects_(Postman) | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6848 | Create testing workbook | Sub-task | Functional_Testing | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | []
TD-6847 | Test_if_enrichment_is_working_properly_with_company_code_filter | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6846 | Functional_Testing | Task | Testing_Phase | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-6845 | Test_advanced_duplicate_testing | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6844 | Testing_Phase | Epic | POC | To Do | 2024-03-03 | 2024-04-03 |  | stephan.kuche |  | []
TD-6843 | Upload_documents_to_Gateway_project_and_test_routing | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6842 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6841 | Compare_project_set-up_with_(TEST)_project | Sub-task | 5_3_-_Smoke_test | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-6840 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6839 | 5_3_-_Smoke_test | Task | 5_Deployment_to_Production | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '5_4_-_Cutover_and_Go_Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '5_2_-_Configure_Projects_(PROD)'}]
TD-6838 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6837 | Contact_IM_to_enable_translation_for_outbound_projects | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6836 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6835 | Contact_IM_to_add_outbound_projects_to_XML_UBL_21_endpoint_(PROD) | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6834 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6833 | Contact_IM_to_enable_newly_created_(PROD)_outbound_projects_for_duplicate_check_pipeline_(Connect_projects_to_IMP_pipeline) | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6832 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-6831 | Contact_IM_to_create_and_configure_LLM_prompting_service | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6830 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6829 | Contact_IM_for_composite_enrichment_set-up_configuration | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6828 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6827 | Create_a_COE_ticket_to_configure_Rerouting_rules | Sub-task | 5_2_-_Configure_Projects_(PROD) | To Do | 2025-01-19 | 2025-01-20 | Example task : https://hypatos.atlassian.net/browse/WHL-825 | stephan.kuche |  | []
TD-6826 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6825 | 5_2_-_Configure_Projects_(PROD) | Task | 5_Deployment_to_Production | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '5_3_-_Smoke_test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '5_1_-_Create_Projects_(PROD)'}]
TD-6824 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6823 | (Optional)_Check__translation_data_points_if_required | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6822 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6821 | Check__duplicate_source_data_point | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6820 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-02-25 | 2024-02-26 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6819 | Check_Vat_Id_validation | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6818 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-02-25 | 2024-02-26 |  | stephan.kuche |  | []
TD-6817 | Check__company_name_validation | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6816 | Application Implementation | Epic | POC | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6815 | Check_accounting_supplier/customer__party | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6814 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-02-25 | 2024-02-26 |  | stephan.kuche |  | []
TD-6813 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-25 | 2024-02-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6812 | Configure_project_schema_with_agreed_upon_requirements_lists_points | Sub-task | 5_1_-_Create_Projects_(PROD) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6811 | 5_1_-_Create_Projects_(PROD) | Task | 5_Deployment_to_Production | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '5_2_-_Configure_Projects_(PROD)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '4_3_-_Testing_by_Wilhelmsen'}]
TD-6810 | API Configuration Support PO | Sub-task | PO data inbound | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | []
TD-6809 | 5_Deployment_to_Production | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-18 | 2025-01-22 |  | stephan.kuche |  | []
TD-6808 | PO data inbound | Task | Integration Implementation | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6807 | Analysis_&_Finalization_of_Tests | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | []
TD-6806 | API Configuration Support PDIB | Sub-task | Posting data inbound | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | []
TD-6805 | Testing_Support_Tasks_(Issue_Resolution) | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | []
TD-6804 | Posting data inbound | Task | Integration Implementation | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | []
TD-6803 | Wilhelmsen_to_perform_User_Acceptance_Testing_(UAT) | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | []
TD-6802 | API Configuration Support OB | Sub-task | Document Outbound | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | []
TD-6801 | Wilhelmsen_to_perform_Functional_Testing | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | []
TD-6800 | Document Outbound | Task | Integration Implementation | To Do | 2024-02-25 | 2024-02-27 |  | stephan.kuche |  | []
TD-6799 | Wilhelmsen_to_configure_integration_&_perform_System_Integration_Testing_(SIT) | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | []
TD-6798 | Support API Configuration | Sub-task | Document Inbound | To Do | 2024-02-25 | 2024-02-28 |  | stephan.kuche |  | []
TD-6797 | Share_Test_Workbook | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-15 | 2025-01-18 | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy | stephan.kuche |  | []
TD-6796 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound | To Do | 2024-02-25 | 2024-02-28 |  | stephan.kuche |  | []
TD-6795 | Document Inbound | Task | Integration Implementation | To Do | 2024-02-25 | 2024-02-28 |  | stephan.kuche |  | []
TD-6794 | Add_projects_to_Requirements_List | Sub-task | 4_3_-_Testing_by_Wilhelmsen | To Do | 2025-01-21 | 2025-01-22 |  | stephan.kuche |  | []
TD-6793 | Integration Implementation | Epic | POC | To Do | 2024-02-25 | 2024-02-28 |  | stephan.kuche |  | []
TD-6792 | 4_3_-_Testing_by_Wilhelmsen | Task | 4_Testing | To Do | 2025-01-15 | 2025-01-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '5_1_-_Create_Projects_(PROD)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '4_2_-_Functional_Testing_by_HY'}]
TD-6791 | Emodel Results analyis | Sub-task | Enrichment_Model_Training | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6790 | (Optional)_Test_translation_feature | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6789 | Test_if_XML_endpoint_if_available_for_outbound_projects_(Postman) | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6788 | QA Emodel | Sub-task | Enrichment_Model_Training | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6787 | Test_if_enrichment_is_working_properly_with_company_code_filter | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6786 | Train EModel | Sub-task | Enrichment_Model_Training | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6785 | Test_advanced_duplicate_testing | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6784 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-6783 | Upload_documents_to_Gateway_project_and_test_routing | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-20 | 2025-01-21 |  | stephan.kuche |  | []
TD-6782 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6781 | Compare_project_set-up_with_requirements_list_for_specific_country | Sub-task | 4_2_-_Functional_Testing_by_HY | To Do | 2025-01-14 | 2025-01-15 | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT | stephan.kuche |  | []
TD-6780 | Capturing Model Evaluation | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6779 | 4_2_-_Functional_Testing_by_HY | Task | 4_Testing | To Do | 2025-01-14 | 2025-01-15 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '4_3_-_Testing_by_Wilhelmsen'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '4_1_-_Testing_Set-up'}]
TD-6778 | Capturing Model Development | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6777 | Copy_and_update_Test_Workbook_for_new_phase_if_needed | Sub-task | 4_1_-_Testing_Set-up | To Do | 2025-01-13 | 2025-01-14 | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy | stephan.kuche |  | []
TD-6776 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6775 | 4_1_-_Testing_Set-up | Task | 4_Testing | To Do | 2025-01-13 | 2025-01-14 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '4_2_-_Functional_Testing_by_HY'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '3_2_-_Configure_Projects_(TEST)'}]
TD-6774 | Perform Capturing Model QA | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6773 | 4_Testing | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-13 | 2025-01-18 |  | stephan.kuche |  | []
TD-6772 | Annotation of Documents | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6771 | Contact_IM_to_enable_translation_for_outbound_projects | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6770 | Upload Training Data | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6769 | Contact_IM_to_add_outbound_projects_to_XML_UBL_21_endpoint_(TEST) | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-12 | 2025-01-13 |  | stephan.kuche |  | []
TD-6768 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6767 | Contact_IM_to_enable_newly_created_(TEST)_outbound_projects_for_duplicate_check_pipeline_(Connect_projects_to_IMP_pipeline) | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-12 | 2025-01-13 |  | stephan.kuche |  | []
TD-6766 | Capturing Model Training | Task | Machine Learning | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6765 | Contact_IM_to_create_and_configure_LLM_prompting_service | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6764 | Machine Learning | Epic | POC | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-6763 | Contact_IM_for_composite_enrichment_set-up_configuration | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-19 | 2025-01-20 |  | stephan.kuche |  | []
TD-6762 | Sign SoW | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6761 | Create_a_COE_ticket_to_configure_Rerouting_rules | Sub-task | 3_2_-_Configure_Projects_(TEST) | To Do | 2025-01-19 | 2025-01-20 | Example task : https://hypatos.atlassian.net/browse/WHL-825 | stephan.kuche |  | []
TD-6760 | Create SoW | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6759 | 3_2_-_Configure_Projects_(TEST) | Task | 3_Studio_Configuration | To Do | 2025-01-12 | 2025-01-13 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '4_1_-_Testing_Set-up'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '3_1_-_Create_Projects_(TEST)'}]
TD-6758 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6757 | (Optional)_Add_translation_data_points_if_required | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | []
TD-6756 | ReportingandMonitoring | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-6755 | Check/change_duplicate_source_data_point | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | []
TD-6754 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6753 | Add/check_vat_id_validation | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | []
TD-6752 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6751 | Add/Change__company_name_validation | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | []
TD-6750 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6749 | Add/Change_accounting_supplier/customer__party | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | []
TD-6748 | Document Outbound Integration | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6747 | Configure_project_schema_with_agreed_upon_requirements_lists_points | Sub-task | 3_1_-_Create_Projects_(TEST) | To Do | 2025-01-18 | 2025-01-19 |  | stephan.kuche |  | []
TD-6746 | Document Inbound Integration | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6745 | 3_1_-_Create_Projects_(TEST) | Task | 3_Studio_Configuration | To Do | 2025-01-11 | 2025-01-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '3_2_-_Configure_Projects_(TEST)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '2_3_-_Model_Fine_Tuning'}]
TD-6744 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6743 | 3_Studio_Configuration | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-11 | 2025-01-13 |  | stephan.kuche |  | []
TD-6742 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 | Customer to provide List | stephan.kuche |  | []
TD-6741 | Add_additional_suppliers_to_IMP_project_if_required | Sub-task | 2_3_-_Model_Fine_Tuning | To Do | 2025-01-10 | 2025-01-11 |  | stephan.kuche |  | []
TD-6740 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6739 | Improve/Optimize__LLM_Prompting_Service_prompt_with_Error_Analysis_results | Sub-task | 2_3_-_Model_Fine_Tuning | To Do | 2025-01-10 | 2025-01-11 |  | stephan.kuche |  | []
TD-6738 | 2_3_-_Model_Fine_Tuning | Task | 2_Model_Training | To Do | 2025-01-10 | 2025-01-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '3_1_-_Create_Projects_(TEST)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '2_1_-_Capturing_Model_Training'}]
TD-6737 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6736 | Train_suppliers_using_documents_uploaded_to_IMP_project | Sub-task | 2_2_-_Enrichment_Model_Training | To Do | 2025-01-07 | 2025-01-08 |  | stephan.kuche |  | []
TD-6735 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6734 | Upload_documents_to_IMP_training_project | Sub-task | 2_2_-_Enrichment_Model_Training | To Do | 2025-01-07 | 2025-01-08 |  | stephan.kuche |  | []
TD-6733 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6732 | Contact_with_IM_to_enable_IMP_pipeline | Sub-task | 2_2_-_Enrichment_Model_Training | To Do | 2025-01-07 | 2025-01-08 |  | stephan.kuche |  | []
TD-6731 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6730 | Create_IMP_training_project_(TEST) | Sub-task | 2_2_-_Enrichment_Model_Training | To Do | 2025-01-07 | 2025-01-08 |  | stephan.kuche |  | []
TD-6729 | Functional Design | Task | Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'ReportingandMonitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO data inbound'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting Data inbound load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document inbound and outbound penny test in PROD env'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Key User Reporting and Monitoring Training and QandA'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-6728 | 2_2_-_Enrichment_Model_Training | Task | 2_Model_Training | To Do | 2025-01-07 | 2025-01-08 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': '1_2_-_Requirement_Gathering'}]
TD-6727 | Design | Epic | POC | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-6726 | Analyze_QA_results_and_accuracy | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6725 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | []
TD-6724 | Create_Error_Analysis_Dashboard | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6723 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | []
TD-6722 | Upload_baseline_(groundtruth)_documents_to_QA_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6721 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | []
TD-6720 | Create_LLM_Prompting_Service_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6719 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | []
TD-6718 | Configure_QA_project_with_Composite_Enrichment_Index | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6717 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6716 | Create__QA_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 | Take the example from (ML) Project - (QA) NZ | stephan.kuche |  | []
TD-6715 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | Update questions, Slidedeck | stephan.kuche |  | []
TD-6714 | Upload_selected_training_documents_from_baseline_project_to_Training_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6713 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6712 | Create_Training__Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 | Take the example from(ML) Project - (Training)(PROD)(NZ) | stephan.kuche |  | []
TD-6711 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6710 | Improve_annotation_quality_based_on_validation_with_posting_data | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6709 | Perfrom Document analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6708 | Validate_annotation_results_with_posting_data | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6707 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | ERP PO data | stephan.kuche |  | []
TD-6706 | Create_a_task_for_annotation_(add_details_per_requirements) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6705 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | ERP master data | stephan.kuche |  | []
TD-6704 | Upload_documents_selected_for_annotation_to_groundtruth_project_(Top_suppliers_and_Edge_cases) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | []
TD-6703 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-6702 | Create_baseline_(groundtruth)_project_to_annotate_(ML) | Sub-task | 2_1_-_Capturing_Model_Training | To Do | 2025-01-07 | 2025-01-10 | Take the example from (ML) Project - NZ_Annotation | stephan.kuche |  | []
TD-6701 | Requirement Analysis | Task | Assessment | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-6700 | 2_1_-_Capturing_Model_Training | Task | 2_Model_Training | To Do | 2025-01-07 | 2025-01-10 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '2_3_-_Model_Fine_Tuning'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '1_2_-_Requirement_Gathering'}]
TD-6699 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6698 | 2_Model_Training | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-07 | 2025-01-11 |  | stephan.kuche |  | []
TD-6697 | Get Posting and Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6696 | Requirement_Gathering_Finalization | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 |  | stephan.kuche |  | []
TD-6695 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6694 | Update_WHL_Requirement_List | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 | https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT | stephan.kuche |  | []
TD-6693 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6692 | Complete_full_set-up_of_training_data_for_all_of_the_top_suppliers_with_Edge_cases_shared_during_requirements_session | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 |  | stephan.kuche |  | []
TD-6691 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-6690 | Request_examples_for_Edge_cases | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 |  | stephan.kuche |  | []
TD-6689 | Requirement_Gathering_Meeting | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 |  | stephan.kuche |  | []
TD-6688 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6687 | (ML)_Demo_Project_Creation_for_Requirements_Gathering_Meeting | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 | Take the example from (ML) Project - (OC Entities)(Phase 3) Oman | stephan.kuche |  | []
TD-6686 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-6685 | Provide_Assessment_Gathering__and_Training__Data__Folders | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 | Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data | stephan.kuche |  | []
TD-6684 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6683 | Provide_Digitalization_Details_form_to_Local_Finance_Team_and_ask_examples_for_Edge_cases | Sub-task | 1_2_-_Requirement_Gathering | To Do | 2025-01-04 | 2025-01-07 | EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y | stephan.kuche |  | []
TD-6682 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (R3, S4Hana) | stephan.kuche |  | []
TD-6681 | 1_2_-_Requirement_Gathering | Task | 1_Process_Discovery | To Do | 2025-01-04 | 2025-01-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '2_1_-_Capturing_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': '2_2_-_Enrichment_Model_Training'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': '1_1_-_Data_Acquisition'}]
TD-6680 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6679 | Match_training_documents_with_posting_data | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 | Match selected documents with posting data | stephan.kuche |  | []
TD-6678 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6677 | Training_Data/Document_Set_Preparation | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 | Prepare training, annotation documents | stephan.kuche |  | []
TD-6676 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | [TEST and [ML] | stephan.kuche |  | []
TD-6675 | Request_additional_documents_if_required | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 | Request if any top supplier document is missing | stephan.kuche |  | []
TD-6674 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-6673 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Compare_project_set-up_with_(TEST)_project'}]
TD-6672 | Training_Data_Assessment | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 | Check if all top suppliers has sample documents with specified naming convention | stephan.kuche |  | []
TD-6671 | Assessment | Epic | POC | To Do | 2024-01-06 | 2024-02-11 |  | stephan.kuche |  | []
TD-6670 | Posting_Data_Analysis | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 | Analyze posting data and determine top suppliers (>90% coverage) | stephan.kuche |  | []
TD-6669 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6668 | Training_&_Posting_Data_Request | Sub-task | 1_1_-_Data_Acquisition | To Do | 2025-01-01 | 2025-01-04 |  | stephan.kuche |  | []
TD-6667 | 1_1_-_Data_Acquisition | Task | 1_Process_Discovery | To Do | 2025-01-01 | 2025-01-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': '1_2_-_Requirement_Gathering'}]
TD-6666 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6665 | 1_Process_Discovery | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-01 | 2025-01-07 |  | stephan.kuche |  | []
TD-6664 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6663 | 0_3_-_Internal_meetings | Task | 0_Project_Management | To Do | 2025-01-01 | 2025-01-11 | Task to log general internal meetings | stephan.kuche |  | []
TD-6662 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6661 | 0_2_-_Update_roll-out_plan | Task | 0_Project_Management | To Do | 2025-01-01 | 2025-01-02 | File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E | stephan.kuche |  | []
TD-6660 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6659 | 0_1_-_Update_all_related_dates_in_this_project | Task | 0_Project_Management | To Do | 2025-01-01 | 2025-01-02 |  | stephan.kuche |  | []
TD-6658 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6657 | 0_Project_Management | Epic | Roll-out_Wilhelmsen | To Do | 2025-01-01 | 2025-01-11 |  | stephan.kuche |  | []
TD-6656 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6655 | Roll-out_Wilhelmsen | Project |  | To Do | 2025-01-01 | 2025-01-29 |  | stephan.kuche |  | []
TD-6654 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6653 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6652 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Optional | stephan.kuche |  | []
TD-6651 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6650 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6649 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6648 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6647 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6646 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-6645 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6644 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6643 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6642 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6641 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-6640 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6639 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-6638 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6637 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6636 | Project Management | Epic | POC | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6635 | POC | Project | CustomerName | To Do | 2024-01-01 | 2024-04-27 |  | stephan.kuche |  | []
TD-6634 | CustomerName | Account |  | To Do | 2024-01-01 | 2024-01-01 |  | stephan.kuche |  | []
TD-6473 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-6472 | Lessons learned | Task | Delivery | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | []
TD-6471 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-04-19 | 2024-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-6470 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | []
TD-6469 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | []
TD-6468 | Hypercare_Phase | Task | Delivery | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-6467 | MileStone_Go Live | Task | Delivery | To Do | 2024-03-28 | 2024-03-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-6466 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-6465 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-6464 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-6463 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-6462 | Deployment | Task | Delivery | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-6461 | Delivery | Epic | Pilot | To Do | 2024-03-26 | 2024-04-21 |  | stephan.kuche |  | []
TD-6460 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-03-25 | 2024-03-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-6459 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-6458 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-6457 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-6456 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-6455 | User Acceptance Testing | Task | Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-6454 | MileStone_SIT_approval | Task | Testing | To Do | 2024-03-03 | 2024-03-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-6453 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6452 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6451 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6450 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6449 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6448 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6447 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-6446 | System Integration Test (E2E) | Task | Testing | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-6445 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-6444 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-6443 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-6442 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-6441 | Functional_Testing | Task | Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}]
TD-6440 | Testing | Epic | Pilot | To Do | 2024-02-22 | 2024-03-26 |  | stephan.kuche |  | []
TD-6439 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6438 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6437 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6436 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6435 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6434 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6433 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6432 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6431 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6430 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6429 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6428 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6427 | Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6426 | Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6425 | Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6424 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6423 | Application Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-6422 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-29 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6421 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6420 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6419 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6418 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | []
TD-6417 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6416 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6415 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6414 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6413 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6412 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6411 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6410 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-6409 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-6408 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6407 | Integration Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6406 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6405 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6404 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6403 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6402 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6401 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-6400 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6399 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6398 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6397 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6396 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6395 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6394 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6393 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6392 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6391 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6390 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6389 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6388 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6387 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6386 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6385 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6384 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6383 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6382 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6381 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-6380 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6379 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6378 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6377 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6376 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6375 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6374 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6373 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6372 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6371 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6370 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6369 | Machine Learning | Epic | Pilot | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-6368 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-02-07 | 2024-02-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-6367 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6366 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6365 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6364 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6363 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6362 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6361 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6360 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6359 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6358 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6357 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-6356 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6355 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6354 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6353 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6352 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-6351 | Functional & Technical Solution Design | Task | Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TD-6350 | Design | Epic | Pilot | To Do | 2024-01-24 | 2024-02-08 |  | stephan.kuche |  | []
TD-6349 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2024-01-23 | 2024-01-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-6348 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6347 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6346 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-6345 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-6344 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-6343 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6342 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6341 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-6340 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6339 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6338 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6337 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | ERP PO data | stephan.kuche |  | []
TD-6336 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | ERP master data | stephan.kuche |  | []
TD-6335 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-6334 | Requirement Analysis | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-6333 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-6332 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6331 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6330 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6329 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6328 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6327 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6326 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6325 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6324 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6323 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6322 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6321 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6320 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6319 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6318 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6317 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6316 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6315 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6314 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6313 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6312 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6311 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6310 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-6309 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6308 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-6307 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6306 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-6305 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6304 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6303 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | [TEST] | stephan.kuche |  | []
TD-6302 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6301 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-6300 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-6299 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-24 |  | stephan.kuche |  | []
TD-6298 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-6297 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6296 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6295 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6294 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-6293 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-6292 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6291 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6290 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6289 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6288 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6287 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6286 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Optional | stephan.kuche |  | []
TD-6285 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6284 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6283 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6282 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6281 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6280 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6279 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-6278 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6277 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6276 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6275 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6274 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-6273 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6272 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-6271 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6270 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-6269 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-6268 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-6267 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-6266 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6265 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6264 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6263 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6262 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 | recommendations to improve model performance | stephan.kuche |  | []
TD-6261 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6260 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6259 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6258 | Request UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | []
TD-6257 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-6256 | User Training | Epic | Pilot | To Do | 2024-01-01 | 2024-04-21 |  | stephan.kuche |  | []
TD-6255 | Pilot | Project |  | To Do | 2024-01-01 | 2024-04-21 |  | stephan.kuche |  | []