## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Rollout | Project
Project Management | Epic | Rollout
Project Set up | Task | Project Management | Project Set up | Data Acquisition |  | 5
Create StakeholderMapping | Sub-task | Project Set up
Assessment | Epic | Rollout
Data Acquisition | Task | Assessment | Data Acquisition | Requirement Analysis |  | 19
Prepare and send out data and documentation request | Sub-task | Data Acquisition
Requirement Analysis | Task | Assessment | Requirement Analysis | Functional Design |  | 17
Posting data analysis | Sub-task | Requirement Analysis |  |  | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template
Design | Epic | Rollout
Functional Design | Task | Design | Functional Design | Capturing Model Training,Enrichment_Model_Training,Studio Configuration,Schema Configuration,Reporting and Monitoring |  | 14
Create and populate Datapoint Template | Sub-task | Functional Design
Machine Learning | Epic | Rollout
Capturing Model Training | Task | Machine Learning |  |  |  | 21
Create Baseline Project | Sub-task | Capturing Model Training
Enrichment_Model_Training | Task | Machine Learning |  |  |  | 14
Create EM Ticket | Sub-task | Enrichment_Model_Training
Application Implementation | Epic | Rollout
Reporting and Monitoring | Task | Application Implementation |  |  |  | 1
Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring |  |  | Insights Standard Collections for Reporting and Monitoring
Studio Configuration | Task | Application Implementation |  |  |  | 14
Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration
Schema Configuration | Task | Application Implementation | Schema Configuration | Functional_Testing |  | 7
Create Composite Enrichment in Setup | Sub-task | Schema Configuration |  |  | Configure Attribute Prediction, Configure Master Data Enrichment
Testing_Phase | Epic | Rollout
Functional_Testing | Task | Testing_Phase | Functional_Testing | System Integration Test (E2E) |  | 3
CUS to perform funct. Testing | Sub-task | Functional_Testing
System Integration Test (E2E) | Task | Testing_Phase | System Integration Test (E2E) | User Acceptance Testing |  | 7
Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E)
User Acceptance Testing | Task | Testing_Phase | User Acceptance Testing | Deployment |  | 21
Run Studio UAT | Sub-task | User Acceptance Testing
User Training | Epic | Rollout
User Onboarding | Task | User Training |  |  |  | 30
Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding
Delivery | Epic | Rollout
Deployment | Task | Delivery | Deployment | Hypercare_Phase |  | 2
Hypercare_Phase | Task | Delivery | Hypercare_Phase | Lessons learned |  | 21
Handover to Customer Care | Sub-task | Hypercare_Phase
Lessons learned | Task | Delivery |  |  |  | 1
Create lessons learned page | Sub-task | Lessons learned