## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-910 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2025-01-25 | 2025-01-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-909 | Lessons learned | Task | Delivery | To Do | 2025-01-25 | 2025-01-26 |  | stephan.kuche |  | []
TD-908 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2025-01-04 | 2025-01-25 |  | stephan.kuche |  | []
TD-907 | Hypercare_Phase | Task | Delivery | To Do | 2025-01-04 | 2025-01-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-906 | Deployment | Task | Delivery | To Do | 2025-01-02 | 2025-01-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-905 | Delivery | Epic | Rollout | To Do | 2025-01-02 | 2025-01-26 |  | stephan.kuche |  | []
TD-904 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-10-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-903 | User Onboarding | Task | User Training | To Do | 2024-10-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-902 | User Training | Epic | Rollout | To Do | 2024-10-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-901 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-12-12 | 2025-01-02 |  | stephan.kuche |  | []
TD-900 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-12-12 | 2025-01-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-899 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-12-05 | 2024-12-12 |  | stephan.kuche |  | []
TD-898 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-12-05 | 2024-12-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-897 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-12-02 | 2024-12-05 |  | stephan.kuche |  | []
TD-896 | Functional_Testing | Task | Testing_Phase | To Do | 2024-12-02 | 2024-12-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-895 | Testing_Phase | Epic | Rollout | To Do | 2024-12-02 | 2025-01-02 |  | stephan.kuche |  | []
TD-894 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-11-25 | 2024-12-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-893 | Schema Configuration | Task | Application Implementation | To Do | 2024-11-25 | 2024-12-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-892 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-11-25 | 2024-12-09 |  | stephan.kuche |  | []
TD-891 | Studio Configuration | Task | Application Implementation | To Do | 2024-11-25 | 2024-12-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-890 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-11-25 | 2024-11-26 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-889 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-11-25 | 2024-11-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-888 | Application Implementation | Epic | Rollout | To Do | 2024-11-25 | 2024-12-09 |  | stephan.kuche |  | []
TD-887 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-11-25 | 2024-12-09 |  | stephan.kuche |  | []
TD-886 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-11-25 | 2024-12-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-885 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-11-25 | 2024-12-16 |  | stephan.kuche |  | []
TD-884 | Capturing Model Training | Task | Machine Learning | To Do | 2024-11-25 | 2024-12-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-883 | Machine Learning | Epic | Rollout | To Do | 2024-11-25 | 2024-12-16 |  | stephan.kuche |  | []
TD-882 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-11-11 | 2024-11-25 |  | stephan.kuche |  | []
TD-881 | Functional Design | Task | Design | To Do | 2024-11-11 | 2024-11-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-880 | Design | Epic | Rollout | To Do | 2024-11-11 | 2024-11-25 |  | stephan.kuche |  | []
TD-879 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-10-25 | 2024-11-11 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-878 | Requirement Analysis | Task | Assessment | To Do | 2024-10-25 | 2024-11-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-877 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-10-06 | 2024-10-25 |  | stephan.kuche |  | []
TD-876 | Data Acquisition | Task | Assessment | To Do | 2024-10-06 | 2024-10-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-875 | Assessment | Epic | Rollout | To Do | 2024-10-06 | 2024-11-11 |  | stephan.kuche |  | []
TD-874 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-10-01 | 2024-10-06 |  | stephan.kuche |  | []
TD-873 | Project Set up | Task | Project Management | To Do | 2024-10-01 | 2024-10-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-872 | Project Management | Epic | Rollout | To Do | 2024-10-01 | 2024-10-06 |  | stephan.kuche |  | []
TD-871 | Rollout | Project | CustomerName | To Do | 2024-10-01 | 2024-10-01 |  | stephan.kuche |  | []
TD-870 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-12-26 | 2024-12-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-869 | Lessons learned | Task | Delivery | To Do | 2024-12-26 | 2024-12-27 |  | stephan.kuche |  | []
TD-868 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-12-05 | 2024-12-26 |  | stephan.kuche |  | []
TD-867 | Hypercare_Phase | Task | Delivery | To Do | 2024-12-05 | 2024-12-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-866 | Deployment | Task | Delivery | To Do | 2024-12-03 | 2024-12-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-865 | Delivery | Epic | Rollout | To Do | 2024-12-03 | 2024-12-27 |  | stephan.kuche |  | []
TD-864 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-01 |  | stephan.kuche |  | []
TD-863 | User Onboarding | Task | User Training | To Do | 2024-09-01 | 2024-10-01 |  | stephan.kuche |  | []
TD-862 | User Training | Epic | Rollout | To Do | 2024-09-01 | 2024-10-01 |  | stephan.kuche |  | []
TD-861 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-11-12 | 2024-12-03 |  | stephan.kuche |  | []
TD-860 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-11-12 | 2024-12-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-859 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-11-05 | 2024-11-12 |  | stephan.kuche |  | []
TD-858 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-11-05 | 2024-11-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-857 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-11-02 | 2024-11-05 |  | stephan.kuche |  | []
TD-856 | Functional_Testing | Task | Testing_Phase | To Do | 2024-11-02 | 2024-11-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-855 | Testing_Phase | Epic | Rollout | To Do | 2024-11-02 | 2024-12-03 |  | stephan.kuche |  | []
TD-854 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-10-26 | 2024-11-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-853 | Schema Configuration | Task | Application Implementation | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-852 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-10-26 | 2024-11-09 |  | stephan.kuche |  | []
TD-851 | Studio Configuration | Task | Application Implementation | To Do | 2024-10-26 | 2024-11-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-850 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-10-26 | 2024-10-27 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-849 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-10-26 | 2024-10-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-848 | Application Implementation | Epic | Rollout | To Do | 2024-10-26 | 2024-11-09 |  | stephan.kuche |  | []
TD-847 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-10-26 | 2024-11-09 |  | stephan.kuche |  | []
TD-846 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-10-26 | 2024-11-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-845 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-10-26 | 2024-11-16 |  | stephan.kuche |  | []
TD-844 | Capturing Model Training | Task | Machine Learning | To Do | 2024-10-26 | 2024-11-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-843 | Machine Learning | Epic | Rollout | To Do | 2024-10-26 | 2024-11-16 |  | stephan.kuche |  | []
TD-842 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-10-12 | 2024-10-26 |  | stephan.kuche |  | []
TD-841 | Functional Design | Task | Design | To Do | 2024-10-12 | 2024-10-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-840 | Design | Epic | Rollout | To Do | 2024-10-12 | 2024-10-26 |  | stephan.kuche |  | []
TD-839 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-25 | 2024-10-12 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-838 | Requirement Analysis | Task | Assessment | To Do | 2024-09-25 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-837 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-25 |  | stephan.kuche |  | []
TD-836 | Data Acquisition | Task | Assessment | To Do | 2024-09-06 | 2024-09-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-835 | Assessment | Epic | Rollout | To Do | 2024-09-06 | 2024-10-12 |  | stephan.kuche |  | []
TD-834 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-833 | Project Set up | Task | Project Management | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-832 | Project Management | Epic | Rollout | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-831 | Rollout | Project |  | To Do | 2024-09-01 | 2024-09-01 |  | stephan.kuche |  | []
TD-830 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-09-25 | 2024-09-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-829 | Lessons learned | Task | Delivery | To Do | 2024-09-25 | 2024-09-26 |  | stephan.kuche |  | []
TD-828 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | []
TD-827 | Hypercare_Phase | Task | Delivery | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-826 | Deployment | Task | Delivery | To Do | 2024-09-02 | 2024-09-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-825 | Delivery | Epic | Rollout | To Do | 2024-09-02 | 2024-09-26 |  | stephan.kuche |  | []
TD-824 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-06-01 | 2024-07-01 |  | stephan.kuche |  | []
TD-823 | User Onboarding | Task | User Training | To Do | 2024-06-01 | 2024-07-01 |  | stephan.kuche |  | []
TD-822 | User Training | Epic | Rollout | To Do | 2024-06-01 | 2024-07-01 |  | stephan.kuche |  | []
TD-821 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-08-12 | 2024-09-02 |  | stephan.kuche |  | []
TD-820 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-08-12 | 2024-09-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-819 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-05 | 2024-08-12 |  | stephan.kuche |  | []
TD-818 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-08-05 | 2024-08-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-817 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-08-02 | 2024-08-05 |  | stephan.kuche |  | []
TD-816 | Functional_Testing | Task | Testing_Phase | To Do | 2024-08-02 | 2024-08-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-815 | Testing_Phase | Epic | Rollout | To Do | 2024-08-02 | 2024-09-02 |  | stephan.kuche |  | []
TD-814 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-07-26 | 2024-08-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-813 | Schema Configuration | Task | Application Implementation | To Do | 2024-07-26 | 2024-08-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-812 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-07-26 | 2024-08-09 |  | stephan.kuche |  | []
TD-811 | Studio Configuration | Task | Application Implementation | To Do | 2024-07-26 | 2024-08-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-810 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-07-26 | 2024-07-27 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-809 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-07-26 | 2024-07-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-808 | Application Implementation | Epic | Rollout | To Do | 2024-07-26 | 2024-08-09 |  | stephan.kuche |  | []
TD-807 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-07-26 | 2024-08-09 |  | stephan.kuche |  | []
TD-806 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-07-26 | 2024-08-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-805 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-07-26 | 2024-08-16 |  | stephan.kuche |  | []
TD-804 | Capturing Model Training | Task | Machine Learning | To Do | 2024-07-26 | 2024-08-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-803 | Machine Learning | Epic | Rollout | To Do | 2024-07-26 | 2024-08-16 |  | stephan.kuche |  | []
TD-802 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-07-12 | 2024-07-26 |  | stephan.kuche |  | []
TD-801 | Functional Design | Task | Design | To Do | 2024-07-12 | 2024-07-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-800 | Design | Epic | Rollout | To Do | 2024-07-12 | 2024-07-26 |  | stephan.kuche |  | []
TD-799 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-06-25 | 2024-07-12 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-798 | Requirement Analysis | Task | Assessment | To Do | 2024-06-25 | 2024-07-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-797 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-06-06 | 2024-06-25 |  | stephan.kuche |  | []
TD-796 | Data Acquisition | Task | Assessment | To Do | 2024-06-06 | 2024-06-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-795 | Assessment | Epic | Rollout | To Do | 2024-06-06 | 2024-07-12 |  | stephan.kuche |  | []
TD-794 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-06-01 | 2024-06-06 |  | stephan.kuche |  | []
TD-793 | Project Set up | Task | Project Management | To Do | 2024-06-01 | 2024-06-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-792 | Project Management | Epic | Rollout | To Do | 2024-06-01 | 2024-06-06 |  | stephan.kuche |  | []
TD-791 | Rollout | Project | CustomerName | To Do | 2024-06-01 | 2024-06-01 |  | stephan.kuche |  | []
TD-790 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-08-25 | 2024-08-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-789 | Lessons learned | Task | Delivery | To Do | 2024-08-25 | 2024-08-26 |  | stephan.kuche |  | []
TD-788 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-787 | Hypercare_Phase | Task | Delivery | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-786 | Deployment | Task | Delivery | To Do | 2024-08-02 | 2024-08-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-785 | Delivery | Epic | Rollout | To Do | 2024-08-02 | 2024-08-26 |  | stephan.kuche |  | []
TD-784 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-05-31 |  | stephan.kuche |  | []
TD-783 | User Onboarding | Task | User Training | To Do | 2024-05-01 | 2024-05-31 |  | stephan.kuche |  | []
TD-782 | User Training | Epic | Rollout | To Do | 2024-05-01 | 2024-05-31 |  | stephan.kuche |  | []
TD-781 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-07-12 | 2024-08-02 |  | stephan.kuche |  | []
TD-780 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-07-12 | 2024-08-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-779 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-07-05 | 2024-07-12 |  | stephan.kuche |  | []
TD-778 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-07-05 | 2024-07-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-777 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-07-02 | 2024-07-05 |  | stephan.kuche |  | []
TD-776 | Functional_Testing | Task | Testing_Phase | To Do | 2024-07-02 | 2024-07-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-775 | Testing_Phase | Epic | Rollout | To Do | 2024-07-02 | 2024-08-02 |  | stephan.kuche |  | []
TD-774 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-06-25 | 2024-07-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-773 | Schema Configuration | Task | Application Implementation | To Do | 2024-06-25 | 2024-07-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-772 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-06-25 | 2024-07-09 |  | stephan.kuche |  | []
TD-771 | Studio Configuration | Task | Application Implementation | To Do | 2024-06-25 | 2024-07-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-770 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-06-25 | 2024-06-26 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-769 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-06-25 | 2024-06-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-768 | Application Implementation | Epic | Rollout | To Do | 2024-06-25 | 2024-07-09 |  | stephan.kuche |  | []
TD-767 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-06-25 | 2024-07-09 |  | stephan.kuche |  | []
TD-766 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-06-25 | 2024-07-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-765 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-06-25 | 2024-07-16 |  | stephan.kuche |  | []
TD-764 | Capturing Model Training | Task | Machine Learning | To Do | 2024-06-25 | 2024-07-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-763 | Machine Learning | Epic | Rollout | To Do | 2024-06-25 | 2024-07-16 |  | stephan.kuche |  | []
TD-762 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-06-11 | 2024-06-25 |  | stephan.kuche |  | []
TD-761 | Functional Design | Task | Design | To Do | 2024-06-11 | 2024-06-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-760 | Design | Epic | Rollout | To Do | 2024-06-11 | 2024-06-25 |  | stephan.kuche |  | []
TD-759 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-05-25 | 2024-06-11 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-758 | Requirement Analysis | Task | Assessment | To Do | 2024-05-25 | 2024-06-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-757 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-756 | Data Acquisition | Task | Assessment | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-755 | Assessment | Epic | Rollout | To Do | 2024-05-06 | 2024-06-11 |  | stephan.kuche |  | []
TD-754 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-753 | Project Set up | Task | Project Management | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-752 | Project Management | Epic | Rollout | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-751 | Rollout | Project | CustomerName | To Do | 2024-05-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-750 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-04-26 | 2024-04-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-749 | Lessons learned | Task | Delivery | To Do | 2024-04-26 | 2024-04-27 |  | stephan.kuche |  | []
TD-748 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | []
TD-747 | Hypercare_Phase | Task | Delivery | To Do | 2024-04-05 | 2024-04-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-746 | Deployment | Task | Delivery | To Do | 2024-04-03 | 2024-04-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-745 | Delivery | Epic | Rollout | To Do | 2024-04-03 | 2024-04-27 |  | stephan.kuche |  | []
TD-744 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-743 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-742 | User Training | Epic | Rollout | To Do | 2024-01-01 | 2024-01-31 |  | stephan.kuche |  | []
TD-741 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-13 | 2024-04-03 |  | stephan.kuche |  | []
TD-740 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-03-13 | 2024-04-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-739 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | []
TD-738 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-03-06 | 2024-03-13 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-737 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | []
TD-736 | Functional_Testing | Task | Testing_Phase | To Do | 2024-03-03 | 2024-03-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-735 | Testing_Phase | Epic | Rollout | To Do | 2024-03-03 | 2024-04-03 |  | stephan.kuche |  | []
TD-734 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-02-25 | 2024-03-03 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-733 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-732 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-731 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-730 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-02-25 | 2024-02-26 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-729 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-02-25 | 2024-02-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-728 | Application Implementation | Epic | Rollout | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-727 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | []
TD-726 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-02-25 | 2024-03-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-725 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-724 | Capturing Model Training | Task | Machine Learning | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-723 | Machine Learning | Epic | Rollout | To Do | 2024-02-25 | 2024-03-17 |  | stephan.kuche |  | []
TD-722 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-721 | Functional Design | Task | Design | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-720 | Design | Epic | Rollout | To Do | 2024-02-11 | 2024-02-25 |  | stephan.kuche |  | []
TD-719 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-25 | 2024-02-11 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-718 | Requirement Analysis | Task | Assessment | To Do | 2024-01-25 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-717 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-716 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-715 | Assessment | Epic | Rollout | To Do | 2024-01-06 | 2024-02-11 |  | stephan.kuche |  | []
TD-714 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-713 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-712 | Project Management | Epic | Rollout | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-711 | Rollout | Project | CustomerName | To Do | 2024-01-01 | 2024-01-01 |  | stephan.kuche |  | []
TD-477 | CustomerName | Account |  | To Do | 2024-01-01 | 2024-01-01 |  | stephan.kuche |  | []