## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-8674 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-11-06 | 2024-11-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Result_Presentation'}]
TD-8673 | Lessons learned | Task | Delivery | To Do | 2024-11-06 | 2024-11-07 |  | stephan.kuche |  | []
TD-8672 | MileStone_Result_Presentation | Task | Delivery | To Do | 2024-11-05 | 2024-11-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Result_Presentation_Preperation'}]
TD-8671 | Create Result_Presentation | Sub-task | Result_Presentation_Preperation | To Do | 2024-11-03 | 2024-11-05 |  | stephan.kuche |  | []
TD-8670 | Result_Presentation_Preperation | Task | Delivery | To Do | 2024-11-03 | 2024-11-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Result_Presentation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved'}]
TD-8669 | Delivery | Epic | POC_TEST | To Do | 2024-11-03 | 2024-11-07 |  | stephan.kuche |  | []
TD-8668 | MileStone_UAT approved | Task | Testing | To Do | 2024-11-02 | 2024-11-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Result_Presentation_Preperation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-8667 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-28 | 2024-11-02 |  | stephan.kuche |  | []
TD-8666 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-28 | 2024-11-02 |  | stephan.kuche |  | []
TD-8665 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-28 | 2024-11-02 |  | stephan.kuche |  | []
TD-8664 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-28 | 2024-11-02 |  | stephan.kuche |  | []
TD-8663 | User Acceptance Testing | Task | Testing | To Do | 2024-10-28 | 2024-11-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-8662 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-10-26 | 2024-10-28 |  | stephan.kuche |  | []
TD-8661 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-10-26 | 2024-10-28 |  | stephan.kuche |  | []
TD-8660 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-10-26 | 2024-10-28 |  | stephan.kuche |  | []
TD-8659 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-10-26 | 2024-10-28 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-8658 | Functional_Testing | Task | Testing | To Do | 2024-10-26 | 2024-10-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
TD-8657 | Testing | Epic | POC_TEST | To Do | 2024-10-26 | 2024-11-03 |  | stephan.kuche |  | []
TD-8656 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8655 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8654 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8653 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8652 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8651 | Schema Configuration | Task | Application Implementation | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8650 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8649 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8648 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8647 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8646 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8645 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8644 | Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-10-05 | 2024-10-06 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8643 | Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-10-05 | 2024-10-06 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8642 | Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-10-05 | 2024-10-06 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8641 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2024-10-05 | 2024-10-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8640 | Application Implementation | Epic | POC_TEST | To Do | 2024-10-05 | 2024-10-19 |  | stephan.kuche |  | []
TD-8639 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | []
TD-8638 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | []
TD-8637 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8636 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | []
TD-8635 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8634 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | []
TD-8633 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8632 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8631 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8630 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8629 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8628 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8627 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8626 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8625 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8624 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8623 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8622 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8621 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8620 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8619 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8618 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8617 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8616 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8615 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8614 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | []
TD-8613 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8612 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8611 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8610 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8609 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8608 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8607 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8606 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8605 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8604 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8603 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8602 | Machine Learning | Epic | POC_TEST | To Do | 2024-10-05 | 2024-10-26 |  | stephan.kuche |  | []
TD-8601 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-10-04 | 2024-10-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-8600 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8599 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8598 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8597 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8596 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8595 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8594 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8593 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-8592 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8591 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8590 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8589 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8588 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | []
TD-8587 | Functional & Technical Solution Design | Task | Design | To Do | 2024-09-20 | 2024-10-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TD-8586 | Design | Epic | POC_TEST | To Do | 2024-09-20 | 2024-10-05 |  | stephan.kuche |  | []
TD-8585 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2024-09-19 | 2024-09-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-8584 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | CUS Deliverable | stephan.kuche |  | []
TD-8583 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | CUS Deliverable | stephan.kuche |  | []
TD-8582 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-8581 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8580 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-8579 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Update questions, Slidedeck | stephan.kuche |  | []
TD-8578 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-8577 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-8576 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-8575 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | ERP PO data | stephan.kuche |  | []
TD-8574 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | ERP master data | stephan.kuche |  | []
TD-8573 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-02 | 2024-09-19 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-8572 | Requirement Analysis | Task | Assessment | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-8571 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-8570 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8569 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8568 | Ingest Supplier Master Data | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8567 | Ingest Purchase Order Data | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8566 | Ingest Company Master Data | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8565 | Ingest CostCenter Data | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8564 | Ingest GL Account Data | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8563 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8562 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8561 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8560 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8559 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8558 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8557 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 | [TEST] | stephan.kuche |  | []
TD-8556 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8555 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | []
TD-8554 | Data Acquisition | Task | Assessment | To Do | 2024-09-02 | 2024-09-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-8553 | Assessment | Epic | POC_TEST | To Do | 2024-09-02 | 2024-09-20 |  | stephan.kuche |  | []
TD-8552 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-09-01 | 2024-09-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-8551 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8550 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8549 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-8548 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-8547 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8546 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8545 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8544 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8543 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8542 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | Optional | stephan.kuche |  | []
TD-8541 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8540 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8539 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8538 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8537 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8536 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8535 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-8534 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8533 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8532 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8531 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8530 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | Including all relevant Files | stephan.kuche |  | []
TD-8529 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8528 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | Included in Handover from Sales | stephan.kuche |  | []
TD-8527 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8526 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-10-31 | PM Deliverable | stephan.kuche |  | []
TD-8525 | Project Set up | Task | Project Management | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8524 | Project Management | Epic | POC_TEST | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8523 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-10-31 | 2024-11-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-8522 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8521 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8520 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8519 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8518 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 | recommendations to improve model performance | stephan.kuche |  | []
TD-8517 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8516 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8515 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8514 | Request UserList | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | []
TD-8513 | User Onboarding | Task | User Training | To Do | 2024-09-01 | 2024-10-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-8512 | User Training | Epic | POC_TEST | To Do | 2024-09-01 | 2024-11-01 |  | stephan.kuche |  | []
TD-8511 | POC_TEST | Project |  | To Do | 2024-09-01 | 2024-11-07 |  | stephan.kuche |  | []
TD-8510 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-10-21 | 2024-10-22 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-8509 | Lessons learned | Task | Delivery | To Do | 2024-10-21 | 2024-10-22 |  | stephan.kuche |  | []
TD-8508 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-10-20 | 2024-10-21 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-8507 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-09-29 | 2024-10-20 |  | stephan.kuche |  | []
TD-8506 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-09-29 | 2024-10-20 |  | stephan.kuche |  | []
TD-8505 | Hypercare_Phase | Task | Delivery | To Do | 2024-09-29 | 2024-10-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-8504 | MileStone_Go Live | Task | Delivery | To Do | 2024-09-28 | 2024-09-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-8503 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-09-26 | 2024-09-28 |  | stephan.kuche |  | []
TD-8502 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-09-26 | 2024-09-28 |  | stephan.kuche |  | []
TD-8501 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-09-26 | 2024-09-28 |  | stephan.kuche |  | []
TD-8500 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-09-26 | 2024-09-28 |  | stephan.kuche |  | []
TD-8499 | Deployment | Task | Delivery | To Do | 2024-09-26 | 2024-09-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-8498 | Delivery | Epic | Pilot | To Do | 2024-09-26 | 2024-10-22 |  | stephan.kuche |  | []
TD-8497 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-09-25 | 2024-09-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-8496 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | []
TD-8495 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | []
TD-8494 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | []
TD-8493 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | []
TD-8492 | User Acceptance Testing | Task | Testing | To Do | 2024-09-04 | 2024-09-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-8491 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | []
TD-8490 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | []
TD-8489 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | []
TD-8488 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | []
TD-8487 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8486 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8485 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | []
TD-8484 | System Integration Test (E2E) | Task | Testing | To Do | 2024-08-28 | 2024-09-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-8483 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-28 |  | stephan.kuche |  | []
TD-8482 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-28 |  | stephan.kuche |  | []
TD-8481 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-28 |  | stephan.kuche |  | []
TD-8480 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-28 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-8479 | Functional_Testing | Task | Testing | To Do | 2024-08-25 | 2024-08-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
TD-8478 | Testing | Epic | Pilot | To Do | 2024-08-25 | 2024-09-26 |  | stephan.kuche |  | []
TD-8477 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8476 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8475 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8474 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8473 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8472 | Schema Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8471 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8470 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8469 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8468 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8467 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8466 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8465 | Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8464 | Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8463 | Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-8462 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-05 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8461 | Application Implementation | Epic | Pilot | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-8460 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-25 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8459 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8458 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8457 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8456 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-08-04 | 2024-08-05 |  | stephan.kuche |  | []
TD-8455 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-05 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8454 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8453 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8452 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8451 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8450 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8449 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8448 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | []
TD-8447 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | []
TD-8446 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-08-04 | 2024-08-07 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8445 | Integration Implementation | Epic | Pilot | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8444 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8443 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8442 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8441 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8440 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8439 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-8438 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8437 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8436 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8435 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8434 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8433 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8432 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8431 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8430 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8429 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8428 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8427 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8426 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8425 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8424 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8423 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8422 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8421 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8420 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8419 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-8418 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8417 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8416 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8415 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8414 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8413 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8412 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8411 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8410 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8409 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8408 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-8407 | Machine Learning | Epic | Pilot | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-8406 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-08-03 | 2024-08-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-8405 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8404 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8403 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8402 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8401 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8400 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8399 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8398 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8397 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8396 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8395 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-8394 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8393 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8392 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8391 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8390 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-8389 | Functional & Technical Solution Design | Task | Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TD-8388 | Design | Epic | Pilot | To Do | 2024-07-20 | 2024-08-04 |  | stephan.kuche |  | []
TD-8387 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2024-07-19 | 2024-07-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-8386 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8385 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8384 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | CUS Deliverable | stephan.kuche |  | []
TD-8383 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | CUS Deliverable | stephan.kuche |  | []
TD-8382 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-8381 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8380 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-8379 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Update questions, Slidedeck | stephan.kuche |  | []
TD-8378 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-8377 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-8376 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-8375 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | ERP PO data | stephan.kuche |  | []
TD-8374 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | ERP master data | stephan.kuche |  | []
TD-8373 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-8372 | Requirement Analysis | Task | Assessment | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-8371 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-8370 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8369 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8368 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8367 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8366 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8365 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8364 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8363 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8362 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8361 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8360 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8359 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8358 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8357 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8356 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8355 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8354 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8353 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8352 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8351 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8350 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8349 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8348 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-8347 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8346 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-8345 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8344 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | (R3, S4Hana) | stephan.kuche |  | []
TD-8343 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8342 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8341 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | [TEST] | stephan.kuche |  | []
TD-8340 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8339 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-8338 | Data Acquisition | Task | Assessment | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-8337 | Assessment | Epic | Pilot | To Do | 2024-07-02 | 2024-07-20 |  | stephan.kuche |  | []
TD-8336 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-07-01 | 2024-07-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-8335 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8334 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8333 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8332 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-8331 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-8330 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8329 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8328 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8327 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8326 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8325 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8324 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | Optional | stephan.kuche |  | []
TD-8323 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8322 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8321 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8320 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8319 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8318 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8317 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-8316 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8315 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8314 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8313 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8312 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | Including all relevant Files | stephan.kuche |  | []
TD-8311 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8310 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | Included in Handover from Sales | stephan.kuche |  | []
TD-8309 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8308 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-10-19 | PM Deliverable | stephan.kuche |  | []
TD-8307 | Project Set up | Task | Project Management | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8306 | Project Management | Epic | Pilot | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8305 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-10-19 | 2024-10-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-8304 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8303 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8302 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8301 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8300 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 | recommendations to improve model performance | stephan.kuche |  | []
TD-8299 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8298 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8297 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8296 | Request UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | []
TD-8295 | User Onboarding | Task | User Training | To Do | 2024-07-01 | 2024-10-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-8294 | User Training | Epic | Pilot | To Do | 2024-07-01 | 2024-10-20 |  | stephan.kuche |  | []
TD-8293 | Pilot | Project |  | To Do | 2024-07-01 | 2024-10-22 |  | stephan.kuche |  | []