## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-7879 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-09-05 | 2024-09-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Result_Presentation'}]
TD-7878 | Lessons learned | Task | Delivery | To Do | 2024-09-05 | 2024-09-06 |  | stephan.kuche |  | []
TD-7877 | MileStone_Result_Presentation | Task | Delivery | To Do | 2024-09-04 | 2024-09-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Result_Presentation_Preperation'}]
TD-7876 | Create Result_Presentation | Sub-task | Result_Presentation_Preperation | To Do | 2024-09-02 | 2024-09-04 |  | stephan.kuche |  | []
TD-7875 | Result_Presentation_Preperation | Task | Delivery | To Do | 2024-09-02 | 2024-09-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Result_Presentation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved'}]
TD-7874 | Delivery | Epic | POC | To Do | 2024-09-02 | 2024-09-06 |  | stephan.kuche |  | []
TD-7873 | MileStone_UAT approved | Task | Testing | To Do | 2024-09-01 | 2024-09-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Result_Presentation_Preperation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-7872 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-08-27 | 2024-09-01 |  | stephan.kuche |  | []
TD-7871 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-08-27 | 2024-09-01 |  | stephan.kuche |  | []
TD-7870 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-08-27 | 2024-09-01 |  | stephan.kuche |  | []
TD-7869 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-08-27 | 2024-09-01 |  | stephan.kuche |  | []
TD-7868 | User Acceptance Testing | Task | Testing | To Do | 2024-08-27 | 2024-09-01 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-7867 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-27 |  | stephan.kuche |  | []
TD-7866 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-27 |  | stephan.kuche |  | []
TD-7865 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-27 |  | stephan.kuche |  | []
TD-7864 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-08-25 | 2024-08-27 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-7863 | Functional_Testing | Task | Testing | To Do | 2024-08-25 | 2024-08-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
TD-7862 | Testing | Epic | POC | To Do | 2024-08-25 | 2024-09-02 |  | stephan.kuche |  | []
TD-7861 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7860 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7859 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7858 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7857 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7856 | Schema Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7855 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7854 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7853 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7852 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7851 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7850 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7849 | Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-7848 | Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-7847 | Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2024-08-04 | 2024-08-05 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-7846 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2024-08-04 | 2024-08-05 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7845 | Application Implementation | Epic | POC | To Do | 2024-08-04 | 2024-08-18 |  | stephan.kuche |  | []
TD-7844 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-7843 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-7842 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7841 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-7840 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7839 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-7838 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7837 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7836 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7835 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7834 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7833 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7832 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7831 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7830 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7829 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7828 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7827 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7826 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7825 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7824 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7823 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7822 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7821 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7820 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7819 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | []
TD-7818 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7817 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7816 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7815 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7814 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7813 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7812 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7811 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7810 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7809 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7808 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-7807 | Machine Learning | Epic | POC | To Do | 2024-08-04 | 2024-08-25 |  | stephan.kuche |  | []
TD-7806 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-08-03 | 2024-08-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-7805 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7804 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7803 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7802 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7801 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7800 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7799 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7798 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7797 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7796 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7795 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-7794 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7793 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7792 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7791 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7790 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | []
TD-7789 | Functional & Technical Solution Design | Task | Design | To Do | 2024-07-20 | 2024-08-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TD-7788 | Design | Epic | POC | To Do | 2024-07-20 | 2024-08-04 |  | stephan.kuche |  | []
TD-7787 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2024-07-19 | 2024-07-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-7786 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7785 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7784 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | CUS Deliverable | stephan.kuche |  | []
TD-7783 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | CUS Deliverable | stephan.kuche |  | []
TD-7782 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-7781 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7780 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-7779 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Update questions, Slidedeck | stephan.kuche |  | []
TD-7778 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-7777 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-7776 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-7775 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | ERP PO data | stephan.kuche |  | []
TD-7774 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | ERP master data | stephan.kuche |  | []
TD-7773 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-02 | 2024-07-19 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-7772 | Requirement Analysis | Task | Assessment | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-7771 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-7770 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7769 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7768 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7767 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7766 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7765 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7764 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7763 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7762 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7761 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7760 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7759 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7758 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7757 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7756 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7755 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7754 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7753 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7752 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7751 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7750 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7749 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7748 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-7747 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7746 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-7745 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7744 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | (R3, S4Hana) | stephan.kuche |  | []
TD-7743 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7742 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7741 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 | [TEST] | stephan.kuche |  | []
TD-7740 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7739 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | []
TD-7738 | Data Acquisition | Task | Assessment | To Do | 2024-07-02 | 2024-07-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TD-7737 | Assessment | Epic | POC | To Do | 2024-07-02 | 2024-07-20 |  | stephan.kuche |  | []
TD-7736 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-07-01 | 2024-07-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-7735 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7734 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7733 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7732 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-7731 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-7730 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7729 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7728 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7727 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7726 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7725 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7724 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | Optional | stephan.kuche |  | []
TD-7723 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7722 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7721 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7720 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7719 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7718 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7717 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-7716 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7715 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7714 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7713 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7712 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | Including all relevant Files | stephan.kuche |  | []
TD-7711 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7710 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | Included in Handover from Sales | stephan.kuche |  | []
TD-7709 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7708 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-08-30 | PM Deliverable | stephan.kuche |  | []
TD-7707 | Project Set up | Task | Project Management | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7706 | Project Management | Epic | POC | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7705 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-08-30 | 2024-08-31 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-7704 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7703 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7702 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7701 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7700 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 | recommendations to improve model performance | stephan.kuche |  | []
TD-7699 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7698 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7697 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7696 | Request UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | []
TD-7695 | User Onboarding | Task | User Training | To Do | 2024-07-01 | 2024-08-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-7694 | User Training | Epic | POC | To Do | 2024-07-01 | 2024-08-31 |  | stephan.kuche |  | []
TD-7693 | POC | Project |  | To Do | 2024-07-01 | 2024-09-06 |  | stephan.kuche |  | []