## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
SKK-382 | tech Design | Task | Project Management | To Do | 2024-01-20 | 2024-02-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
SKK-381 | Functional Design | Task | Project Management | To Do | 2024-01-31 | 2024-02-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
SKK-380 | Requirement Analysis | Task | Project Management | To Do | 2024-01-20 | 2024-01-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
SKK-379 | Data Acquisition | Task | Project Management | To Do | 2024-01-06 | 2024-01-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'tech Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
SKK-378 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
SKK-377 | Project Management | Epic |  | To Do | 2024-01-01 | 2024-02-14 |  | stephan.kuche |  | []
SKK-376 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
SKK-375 | Project Set up | Task | Project Management | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
SKK-374 | Project Management | Epic |  | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
SKK-350 | WILH Annotation Problem - Blocks LLM Transition | Task |  | To Do |  |  | *Current Problem:* We do not have reliable Ground Truth Data that can be used for annotation in Training projects. [https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659e55e7be254382cbb5502d¦https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659e55e7be254382cbb5502d¦smart-link] Document ID : 659e55e7be254382cbb5502d We are facing the following issue: In order to enhance the performance of our machine learning models, we normally use the posting data. As this data is not available, we need to rely on the annotation in the live production projects. Here is an example of a document where the taxes were deleted although our model extracted taxes and tax amounts Link in Insights: [https://insights.hypatos.ai/question#eyJuYW1lIjoiW1dJTEhfUFJPRF0gQWNjdXJhY3kgcGVyIEVudGl0eSBwZXIgUHJvamVjdCAoQ2FwdHVyZSkiLCJkZXNjcmlwdGlvbiI6bnVsbCwiZGF0YXNldF9xdWVyeSI6eyJxdWVyeSI6eyJzb3VyY2UtdGFibGUiOjE4OTMyOCwiZmlsdGVyIjpbIj0iLFsiZmllbGQiLDM5NTU5NjIsbnVsbF0sIjY1OWU1NWU3YmUyNTQzODJjYmI1NTAyZCJdfSwidHlwZSI6InF1ZXJ5IiwiZGF0YWJhc2UiOjN9LCJkaXNwbGF5IjoidGFibGUiLCJkaXNwbGF5SXNMb2NrZWQiOnRydWUsInZpc3VhbGl6YXRpb25fc2V0dGluZ3MiOnsiY29sdW1uX3NldHRpbmdzIjp7IltcIm5hbWVcIixcImF2Z1wiXSI6eyJjb2x1bW5fdGl0bGUiOiJBY2N1cmFjeSJ9fSwicGl2b3RfdGFibGUuY29sdW1uX3NwbGl0Ijp7ImNvbHVtbnMiOltdLCJyb3dzIjpbWyJmaWVsZCIsMzk1NTkzMixudWxsXSxbImZpZWxkIiwzOTU1OTUzLG51bGxdLFsiZmllbGQiLDM5NTU5MjAseyJ0ZW1wb3JhbC11bml0Ijoid2VlayJ9XV0sInZhbHVlcyI6W1siYWdncmVnYXRpb24iLDBdXX19LCJvcmlnaW5hbF9jYXJkX2lkIjozNTU2fQ==¦https://insights.hypatos.ai/question#eyJuYW1lIjoiW1dJTEhfUFJPRF0gQWNjdXJhY3kgcGVyIEVudGl0eSBwZXIgUHJvamVjdCAoQ2FwdHVyZSkiLCJkZXNjcmlwdGlvbiI6bnVsbCwiZGF0YXNldF9xdWVyeSI6eyJxdWVyeSI6eyJzb3VyY2UtdGFibGUiOjE4OTMyOCwiZmlsdGVyIjpbIj0iLFsiZmllbGQiLDM5NTU5NjIsbnVsbF0sIjY1OWU1NWU3YmUyNTQzODJjYmI1NTAyZCJdfSwidHlwZSI6InF1ZXJ5IiwiZGF0YWJhc2UiOjN9LCJkaXNwbGF5IjoidGFibGUiLCJkaXNwbGF5SXNMb2NrZWQiOnRydWUsInZpc3VhbGl6YXRpb25fc2V0dGluZ3MiOnsiY29sdW1uX3NldHRpbmdzIjp7IltcIm5hbWVcIixcImF2Z1wiXSI6eyJjb2x1bW5fdGl0bGUiOiJBY2N1cmFjeSJ9fSwicGl2b3RfdGFibGUuY29sdW1uX3NwbGl0Ijp7ImNvbHVtbnMiOltdLCJyb3dzIjpbWyJmaWVsZCIsMzk1NTkzMixudWxsXSxbImZpZWxkIiwzOTU1OTUzLG51bGxdLFsiZmllbGQiLDM5NTU5MjAseyJ0ZW1wb3JhbC11bml0Ijoid2VlayJ9XV0sInZhbHVlcyI6W1siYWdncmVnYXRpb24iLDBdXX19LCJvcmlnaW5hbF9jYXJkX2lkIjozNTU2fQ==] *Further Examples:* * [https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659c8b888b738168a129114d¦https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659c8b888b738168a129114d¦smart-link] * [https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659b50933839845bab95aeb1¦https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659b50933839845bab95aeb1¦smart-link] * [https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659b49b3a2e3654719ba2dcf¦https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659b49b3a2e3654719ba2dcf¦smart-link] * [https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659ab2f940f91bbda78bb023¦https://cloud.hypatos.ai/projects/au-iwmsau01-non-po-invoices-728p4l2x/659ab2f940f91bbda78bb023¦smart-link] !Screenshot 2024-01-12 at 10.06.45.png¦width=2246,height=664! [^query_result_2024-01-12T09_07_42.122276Z.xlsx] | stephan.kuche |  | []
SKK-349 | Assessement / Technical WS Deck | Task |  | Done |  |  | * error codes validations wie nach xSuite übertragen | stephan.kuche |  | []
SKK-348 | Update infos for WIL - how to add users, how to change request. | Sub-task | OPen items | Done |  |  |  | stephan.kuche |  | []
SKK-347 | derivation to update bank account informaiton from iban | Sub-task | OPen items | To Do |  |  |  | stephan.kuche |  | []
SKK-264 | fams tickedts erstellen | Sub-task | OPen items | To Do | 2023-10-17 | 2023-10-17 |  |  | Tesst | []
SKK-263 | Ktm Upload kickoff Sharepoint | Sub-task | OPen items | Done | 2023-10-17 | 2023-10-17 |  |  | asda | []
SKK-262 | model renaming in the documentation | Sub-task | OPen items | Done | [5 empty] | []
SKK-261 | backend topic - training projects | Sub-task | OPen items | To Do |  |  | [https://hypatos.atlassian.net/browse/BACKEND-581¦https://hypatos.atlassian.net/browse/BACKEND-581¦smart-link] |  |  | []
SKK-260 | Clarify Tax Table | Sub-task | OPen items | To Do | [5 empty] | []
SKK-259 | Regex for Company Names | Sub-task | OPen items | Done | [5 empty] | []
SKK-258 | Save validation schema totals tax totals Gross | Sub-task | OPen items | Done |  |  | {noformat}{ "internalName": "gross", "displayName": "Gross", "type": "money", "normalization": [], "rules": { "required": true, "compare": [ { "failureMessage": "Value does not match the sum of the total net and tax amounts", "operator": "==", "right": { "type": "calc", "left": { "type": "reference", "path": [ "totals", "net" ] }, "operator": "+", "right": { "type": "reference", "path": [ "totals", "tax" ] } } } ] }, "source": { "type": "extractor" } },{noformat} |  |  | []
SKK-257 | Ticket supplier master data wilh | Sub-task | OPen items | Done |  |  | no problem detectd |  |  | []
SKK-256 | OPen items | Task |  | To Do | [5 empty] | []
SKK-87 | [WILH] implement totals net - total gross validation | Task |  | In Progress | [5 empty] | []
SKK-86 | Invite external users to JWM | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-85 | Create Jira (JWM) Project | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-84 | Create JourFixe PMO & Steerco Meeting Series | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-83 | Schedule Workshops (AWS, FWS, TWS) | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-82 | Hy Academy Access | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-81 | Stakeholder mappijng | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-80 | Sharpoint Page | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-79 | Absence Planner | Sub-task | [FUNKE] | Done |  | 2023-12-22 |  |  |  | []
SKK-78 | Update Slidedeck Kickoff | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-77 | Welche Buchungskreise und top vendoren sind relevant | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-76 | Create RAID log | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-75 | teams & sharepoint und externe user zulassen | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-74 | credentials versenden | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-73 | credentials erstellen | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-72 | Send SAP Addon (Install + SP1) | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-71 | doku SAP raussenden | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-70 | sap certificates - name von SAP basis guy an dawid | Sub-task | [FUNKE] | Done | [5 empty] | []
SKK-69 | [FUNKE] | Task |  | To Do |  |  |  | stephan.kuche |  | []
SKK-68 | [WILH] Update PO Number rule - currently captures to many chars | Task |  | To Do | [5 empty] | []
SKK-67 | [OKR] Steps | Task |  | In Progress |  |  | Hi Leticia here are the steps that need to be performed * go to this page: [https://hypatos.atlassian.net/wiki/spaces/PD/pages/960987137/Transition+from+ABBYY+to+Google+Vision+OCR+Part2¦https://hypatos.atlassian.net/wiki/spaces/PD/pages/960987137/Transition+from+ABBYY+to+Google+Vision+OCR+Part2¦smart-link] * check out the table * add find the document volumes per months * Go to Column: *Transition Status* filter for not started * talk to CSM - ask for a Project that has valid production data * clone this project to the ML company of that customer ( if no ML company exists - create a CoE ticket to create one - if you request the company creation , also provide the information that if the company already exists - CoE should just provide the companyid) Always Create a new ML company using this naming convention [ML] Customername * use Hypatools Copydocs to copy the docs from PROD to ML company * to get the documentIds that needs to be copied - use insights - ( take documents of the last months and limit to max 1000 documents) * use the file attached as example when using Hypatools [^copy_list_multi_external_beas_gp4_v2.xlsx] |  |  | []
SKK-66 | [WIL] Insert Dummy Supplier | Task |  | Done | [5 empty] | []
SKK-64 | [WIL] delete company validation JP | Task |  | Done | [5 empty] | []
SKK-63 | [WIL] JP Model enhancement | Task |  | Done |  |  | * annotate a second version of document * maybe use local finance or posting data * qa again and check the performance * get back to He |  |  | []
SKK-62 | [WIL] Cutover Plan | Task |  | Done |  |  | * feature flags ( must correct all errrors ) * routing rules * index * IMP - new index * fingerprint index for duplicate check * API v2 credentials * cadence of MD update / outbound * mapping of outbound projects → denis * list of users to assign to projects * Translation service set up to projects * insights access * create dashboards |  |  | []
SKK-61 | [WIL] Deploy JP model to test env | Task |  | Done | [5 empty] | []
SKK-60 | [WIL] USER training I & II | Task |  | Done |  |  | * Access and Login * User Roles and different permissions * Project Structure * Routing & meaning of each folder * Search (by name / document id / URL * *Duplicates* ** Columns * *Documents* ** Junk ** Move ** Confirm ** Download * *Datapoints* ** Using Filter ** Derivation ** Validation ** Normalization * *Splitting* * ---*--DONE* ------- ** Header ** Table ** Enrichment * *IMP / SUPPLIER MASTER DATA Training* ** how to train ** select and delete vendor *Corrections* * what to do / what not to do |  |  | []
SKK-59 | [WIL] Reduce Schema in Gateway | Task |  | Done | [5 empty] | []
SKK-58 | [WIL] Test Feedback | Task |  | Done |  |  | * involve japanese team to check supplier enrichment * upload all top vendors for each entity (one sample per entity ) → let japanes account check if supplier enrichment was correct * TESTcases that can be closed: ** UAT_TC_01_01 - Duplicated Detection * *Needs Attention:* ** UAT_TC_01_02 Advanced Duplicate Detection ** UAT_TC_01_05 - PO Invoice with over 50 pages → no link ** UAT_TC_01_10 → excel files cannot be processed at all ** UAT_TC_01_12 - Invoice sent as photo → all images are converted to pDF before the upload ** D01 - Able to complete document with missing document type ** D03 ** * Reduce Schema TO minimum *GATEWAY* * GATE WAY Cleansing ** MY18 ** NZ03 ** |  |  | []
SKK-57 | [WIL] CreditNote - minus | Task |  | Done | [5 empty] | []
SKK-55 | Contact ThinkCell - support@think-cell.com - links to ranges | Task |  | Done |  |  | Dear think cell team, I am trying to achieve the following process automation but I am not sure whether this is possible. * set up an excelworkbook that links to a Gantt on a powerpointslidetemplate * now I want to programmatically (using VBA) clone the excelworkbook and powerpointslidetemplate in order to use it for different projects with different start and enddates of each activity * cloning works fine but the issue is that, the link between the wb and the slidedeck remains the same for all cloned versions, which makes sense, but I would rather create a “new” link between the two applications automatically * is there maybe a way to create this link using VBA ? * I could only find this page : [https://www.think-cell.com/en/resources/manual/exceldataautomation#chap_exceldataautomation¦https://www.think-cell.com/en/resources/manual/exceldataautomation#chap_exceldataautomation¦smart-link] , which from my point of view assumes that the workbook (datasource) remains the same only the data within the wb changes. * In my case both the wb and the presentation are templates Thank you very much in advance |  |  | []
SKK-54 | [WILH] SOlution Design Design Sign OFF3 | Task |  | Done | 2023-11-11 | 2023-11-30 | Question to Amadeusz - # What do you actually patch when you upload a document - only externalId ## how is the externalid constructed ? UUID # are email sender etc datapoints used - YES | stephan.kuche |  | []
SKK-53 | [Internal] Feedback | Task |  | Done | [5 empty] | []
SKK-52 | [WIL] Create Testing KIckoff Slidedeck | Task |  | Done | [5 empty] | []
SKK-51 | Delete IMP JP and or link anothert index and create fingerprints again, | Task |  | Done | [5 empty] | []
SKK-50 | [WIL] go through external Data with Amadeusz | Task |  | Done | [5 empty] | []
SKK-49 | check if imp in JP is wired to PO / NON PO project | Task |  | Done | 2023-09-21 | 2023-10-07 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Documentation of Translation Service'}]
SKK-48 | WIL VMD - threshold if confidence too low | Task |  | Done | [5 empty] | []
SKK-47 | Rouitng NON PO Invoices CoE | Task |  | Done | [5 empty] | []
SKK-46 | WIL - discuss OC datapoints | Task |  | Done |  |  | ¦A108¦Merge Data Mapping into one file¦Open¦Stephan¦2023-10-02¦2023-10-05¦ ¦Creation of one Mapping File for Document Outbound (CML¦ |  |  | []
SKK-45 | JP Retraining? | Task |  | Done | [5 empty] | []
SKK-44 | VMD QA Insights - run GH action | Task |  | Done | [5 empty] | []
SKK-43 | CoE Ticket Enhance VMD Matching ACC | Task |  | Done | [5 empty] | []
SKK-42 | Discuss Routijng logic with WIL | Task |  | Done | [5 empty] | []
SKK-41 | WIL finish check routing projects | Task |  | Done | [5 empty] | []
SKK-40 | WIL - Follow up with INT Ticket Denys | Task |  | Done |  |  | [https://hypatos.atlassian.net/browse/INT-605¦https://hypatos.atlassian.net/browse/INT-605¦smart-link] |  |  | []
SKK-39 | WIL Mapping - Recipient CompanyCode | Task |  | Done |  |  | Frage an Fotis - Was ist der letzte stand des mapping files. was ist zu was gemapped? Bzgl. insights und der Gruppe recipeitenCompayna [^WILH_JSON_to_XML_Mapping_v1.0.xlsx] |  |  | []
SKK-38 | [WIL] Schedule kickoff for testing | Task |  | Done | [5 empty] | []
SKK-37 | [WIL] testing workbook - description of terms | Task |  | Done | [5 empty] | []
SKK-36 | Documentation of Translation Service | Task |  | Done | 2023-10-17 | 2023-10-31 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'check if imp in JP is wired to PO / NON PO project'}]
SKK-35 | [WIL] add PO validation also on POLINE ITEM Level | Task |  | Done | [5 empty] | []
SKK-34 | [WIL] Upload Documentation of Archiving to WILH Sharepoint | Task |  | Done | [5 empty] | []
SKK-33 | [WIL] Share Translation Service Credentials - can be shared with customer | Task |  | Done | [5 empty] | []
SKK-32 | [WIL] Translaation service to japanese projects | Task |  | Done | [5 empty] | []
SKK-31 | [WIL] external data - derivation rule / and default values | Task |  | Done |  |  | {noformat}"externalData": { "email": "gbs-finance-service-layer-sol@wilhelmsen.com"{noformat} |  |  | []
SKK-30 | Add PO extract and Reciepient Valdiation to PO/NON invoices Project | Sub-task | [WIL] Studio App Setup | Done |  |  | other: [https://cloud.hypatos.ai/projects/po-extract-agdh8f5s¦https://cloud.hypatos.ai/projects/po-extract-agdh8f5s¦smart-link] JP [https://cloud.hypatos.ai/projects/po-extract-jp-18lyzmdi¦https://cloud.hypatos.ai/projects/po-extract-jp-18lyzmdi¦smart-link] valid - see companies |  |  | []
SKK-29 | [WIL] endusers to add to studio | Task |  | Done | [5 empty] | []
SKK-28 | Validation Rule - Requirement Sheet - Company Name | Task |  | Done | [5 empty] | []
SKK-27 | [WIL] start imp training | Task |  | Done | [5 empty] | []
SKK-26 | [WIL] FILL IMP INDEX | Task |  | Done | [5 empty] | []
SKK-25 | [WIL] Translation Service - Costs | Task |  | Done |  |  | [https://hypatosai.slack.com/archives/C04FX9MN3F1/p1694853778406419?thread_ts=1694760098.313489&cid=C04FX9MN3F1¦https://hypatosai.slack.com/archives/C04FX9MN3F1/p1694853778406419?thread_ts=1694760098.313489&cid=C04FX9MN3F1¦smart-link] |  |  | []
SKK-24 | [WIL] Duplicate Detection and Routing Rule Documentation in Confluence | Task |  | Done |  |  | [https://hypatos.atlassian.net/jira/software/c/projects/COE/boards/137?modal=detail&selectedIssue=COE-604&search=wil¦https://hypatos.atlassian.net/jira/software/c/projects/COE/boards/137?modal=detail&selectedIssue=COE-604&search=wil¦smart-link] |  |  | []
SKK-23 | [WIL] Duplicate Detection Ticket | Task |  | Done |  |  | [https://hypatos.atlassian.net/jira/software/c/projects/COE/boards/137?modal=detail&selectedIssue=COE-604&search=wil¦https://hypatos.atlassian.net/jira/software/c/projects/COE/boards/137?modal=detail&selectedIssue=COE-604&search=wil¦smart-link] | stephan.kuche |  | []
SKK-22 | add sender country normalization to all gateway projecfts | Sub-task | [WIL] Studio App Setup | Done |  |  | {noformat} "normalization": [ { "type": "remove", "pattern": "[,]" }, { "type": "remove", "pattern": "^[\\s]" } ],{noformat} |  |  | []
SKK-21 | [WIL] IMP only for MY, MM, JP | Task |  | Done |  |  | Australia and NZ dont need IMP - schema has to be changed |  |  | []
SKK-20 | [WIL] MD Filter per project | Task |  | Done |  |  | *Add* "options": { "esIndex": "nameOfYourIndex", "companyId": "nameOfYourCompanyCode" |  |  | []
SKK-19 | apply validation rules | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-18 | reduce datapoints where they are not needed | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-17 | apply model to all projects | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-16 | [WIL] Validation RULES | Task |  | Done |  |  | ¦¦*Validation Rule*¦¦*Comment*¦¦ ¦¦ ¦Company Name Captured vs Project the invoice was uploaded to¦Use Regex to verify if company name is correct¦ ¦ ¦ ¦ ¦ ¦ |  |  | []
SKK-15 | check after CoE is done | Sub-task | [WIL] Studio App Setup | Done |  |  | * AUS normalization of currency * NZ normalization of currency * MY normalization of currency * JP normalization of currency * JP type normalizations (invoice, creditnote) * * Derivation according to requirementlist |  |  | []
SKK-14 | [KTM] Results Present | Task |  | Done |  |  | 0900: documents ids 64feeea06269a554341ec270 , 64fef939fcd512525a81f15f *64fef931cb11cf9b3ed379b5, 64feee9ee81c1d482e8a8957,* 64fef945994edcb6e189166f, 64feeea307197a31d043df31, 64feeeaf488efbf0dff6892f, 64fef934fef6b44fe17c05c1 |  |  | []
SKK-13 | roll out for all countries | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-12 | create routing rules | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-11 | add derivation rules | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-10 | apply normalization | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-9 | create schemas | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-8 | create projects | Sub-task | [WIL] Studio App Setup | Done | [5 empty] | []
SKK-7 | [WIL] Studio App Setup | Task |  | Done | [5 empty] | []
SKK-6 | [WIL] Date PostProcessor Normalizations | Task |  | Done |  |  | ¦¦*Country*¦¦*URL*¦¦*Issued AT*¦¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bc448eb05f6d04c9ffc6¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bc448eb05f6d04c9ffc6¦smart-link]¦2023 年 4 月 3 日¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64cd0889aa5fb7f02db05ce6¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64cd0889aa5fb7f02db05ce6¦smart-link]¦*2020 年 9 月 4 日*¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bcbd6e7ec29f901956d0¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bcbd6e7ec29f901956d0¦smart-link]¦令 和 5 年 2 月 6 日¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bbe5167dbc1ee55f2f13¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1bbe5167dbc1ee55f2f13¦smart-link]¦2023 年 2 月 28 日¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f181f2691a2ca4841e7e25¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f181f2691a2ca4841e7e25¦smart-link]¦2023 年 05 月 31 日¦ ¦JP¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1c2221edbc131f7ab8a23¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f1c2221edbc131f7ab8a23¦smart-link]¦2021 年 5 月 31 日¦ ¦MY¦[https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64dcd78c71d38bce0eea0af6¦https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64dcd78c71d38bce0eea0af6¦smart-link]¦03 Ogos 2023¦ ¦MY¦[https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64d4b417a821774d9fc04525¦https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64d4b417a821774d9fc04525¦smart-link]¦01 - DEC - 2022¦ ¦MY¦[https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd0538b001967ccc7614f¦https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd0538b001967ccc7614f¦smart-link]¦24 Mac 2022¦ ¦MY¦[https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd04c174120e26e8d2658¦https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd04c174120e26e8d2658¦smart-link]¦15 MAC 2022¦ ¦MY¦[https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd03f4b8b98f076559618¦https://cloud.hypatos.ai/projects/my-annotation-samples-3iy0fl37/64cfd03f4b8b98f076559618¦smart-link]¦22 Dis 2022¦ ¦ ¦ ¦ ¦ |  |  | []
SKK-5 | [WIL] IMP | Task |  | Done | [5 empty] | []
SKK-4 | [PlayGround] Transformer | Task |  | Blocked |  |  | cl-deployment-gpt-demo-production cl-deployment-gpt-demo-3-5-production * Stacking GPT and Image based: ** Create a ticket and assign it to He * *A “thought“ Datapoint* ** Input any business specific information about a specific document - business logic etc * *mechanismns in general* * *Undo changes* ** Just put the confirmed document in state edit ** Everytime we call OpenAI API - we iterate over a confirmed document to send the context |  |  | []
SKK-3 | [OKR] Meeting with Hé | Task |  | Done |  |  | *KR* * _Design a company-wide transition plan to migrate all accounts to google OCR within three months_ ** List all Companies including features (QR, languages) ** create migration tracking overview (assign owners) ** create step by step guide to enable IMs and CSM to migrate themselfes *Open Questions* * What do we need to retrain model? ** *using transformer* *** GT ? *** create QA projects *** High Volume of documents ** *using annotation*g *** high quality labels *** how many docs *** … * *How does the retraining look like?* ** ** create a qa project to test against * *Any Blockers you could think of ?* *Plan Proposal* * Beas - no line items * Adani - labelled already ~1000-2000 docs during the last 2 months - using Google OCR *Annotation WAY* 1. choose customer customer to pilot beierdorf /strabag / beas 2. setup up a testing project ( change) 200 documents when dp is significally drops if we see the troublemakers upload 2000 docs and then annotate and train the subset testing data set *Transformer Approach* * create ea project * no model needs to be provided * use google vision * copy docs and reprocess * link needs to be there (GTid) * min 10k documents - better 50 k documents ( Beas can be * Enrichment should be based on ocr *Next Steps* * check the monthly volume of beas, beiersdorf strabag, * create a small project - uploade a few docs * let He check - if checked * do the same but with the all docs * |  |  | []
SKK-2 | [WIL] Routing | Task |  | Done | [5 empty] | []
SKK-1 | [WIL] Normalizations JPY | Task |  | Done |  |  | ¦¦*Country*¦¦*Datapoint*¦¦*URL*¦¦*Comment*¦¦*Exp. Result*¦¦*Done*¦¦ ¦JP¦Currency¦[https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f183153236d7d78e7ca75f¦https://cloud.hypatos.ai/projects/jp-annotation-samples-i6jvtmw1/64f183153236d7d78e7ca75f¦smart-link]¦{{[^a-zA-Z]+([Jj]py¦JPY)+¦([Jj]py¦JPY)+[^a-zA-Z]+¦¥¦^([Jj]py¦JPY)+$}}¦JPY¦x¦ ¦JP¦Type¦ ¦add invoice and creditnote normalizations * クレジットノート (Kurejitto Nooto) - Credit Note * 請求書 (Seikyuusho) - Invoice¦{noformat}"pattern": "(?i)(請求書)", "replacement": "invoice"{noformat}¦x¦ ¦JP¦TYPE¦[https://cloud.hypatos.ai/projects/jp-annotation-o9la5o8m/64cfbe5500e2432016f150dc¦https://cloud.hypatos.ai/projects/jp-annotation-o9la5o8m/64cfbe5500e2432016f150dc¦smart-link]¦口座 振替 の お知らせ is this invoice? - no¦ ¦y¦ |  |  | []