## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
CustomerName | Account
Pilot | Project | CustomerName
Project Management | Epic | Pilot
Project Set up | Task | Project Management | Project Set up | Data Acquisition |  | 5
Create StakeholderMapping | Sub-task | Project Set up
Create Customer Documentation | Sub-task | Project Set up |  |  | Included in Handover from Sales
Document Project (confl.) | Sub-task | Project Set up
Sharepoint folder set-up | Sub-task | Project Set up |  |  | Including all relevant Files
Create Absence Planner | Sub-task | Project Set up
Create Weekly Report (based on template) | Sub-task | Project Set up
Teams Channel Setup | Sub-task | Project Set up
Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up
Teams Page Setup | Sub-task | Project Set up |  |  | Page with most relevant Links, StakeholderMapping and FAQ
Create JourFixe PMO and Steerco Series | Sub-task | Project Set up
Create Jira Work Mangagement Project | Sub-task | Project Set up
Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up
Create RAID Log | Sub-task | Project Set up
Create Project timeline | Sub-task | Project Set up
Create Jira Advanced roadmap | Sub-task | Project Set up |  |  | Optional
Create Project Plan | Sub-task | Project Set up
Identification of project deliverables | Sub-task | Project Set up
Create Kickoff Slidedeck | Sub-task | Project Set up
Create Assessment Workshop Slidedeck | Sub-task | Project Set up
Create Functional Workshop Slidedeck | Sub-task | Project Set up
Create Technical Workshop Slidedeck | Sub-task | Project Set up
Schedule Workshops (Assessment WS) | Sub-task | Project Set up
Schedule Workshops (Functional WS) | Sub-task | Project Set up
Schedule Workshops (Technical WS) | Sub-task | Project Set up
Assessment | Epic | Pilot
Data Acquisition | Task | Assessment | Data Acquisition | Requirement Analysis |  | 19
Prepare and send out data and documentation request | Sub-task | Data Acquisition
Create Studio Company | Sub-task | Data Acquisition |  |  | [TEST and [ML]
Create apiv2 credentials | Sub-task | Data Acquisition
Share apiv2 credentials | Sub-task | Data Acquisition
Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition |  |  | (R3, S4Hana)
Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition
Send SAP Addon InstallationPackages | Sub-task | Data Acquisition |  |  | (Install andService Packages SP1)
Send SAP Addon Documentation | Sub-task | Data Acquisition
Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition |  |  | invite SAP Basis and HY SAP engineers
Install SAP Addon | Sub-task | Data Acquisition
Configure SAP Addon | Sub-task | Data Acquisition
Get Posting and Master Data via SAP Addon | Sub-task | Data Acquisition
Data and documentation quality and completeness review | Sub-task | Data Acquisition
Requirement Analysis | Task | Assessment | Requirement Analysis | Functional Design |  | 17
Posting data analysis | Sub-task | Requirement Analysis |  |  | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template
Perform Master data analysis | Sub-task | Requirement Analysis |  |  | ERP master data
Perform PO data analysis | Sub-task | Requirement Analysis |  |  | ERP PO data
Perfrom Document analysis | Sub-task | Requirement Analysis |  |  | Documents (datapoints), Document types, document languages (regions) analysis
Create Document Processing Workflow | Sub-task | Requirement Analysis |  |  | Process documentation, Hypatos Studio Standard process template
Perform System analysis | Sub-task | Requirement Analysis |  |  | Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template
Prepare Assessement Workshop | Sub-task | Requirement Analysis |  |  | Update questions, Slidedeck
Perform Assessement Workshop | Sub-task | Requirement Analysis |  |  | Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis
Prepare Functional Workshop | Sub-task | Requirement Analysis
Perform Functional Workshop | Sub-task | Requirement Analysis
Prepare Technical Workshop | Sub-task | Requirement Analysis
Perform Technical Workshop | Sub-task | Requirement Analysis
Design | Epic | Pilot
Functional Design | Task | Design | Functional Design | Capturing Model Training,Enrichment_Model_Training,Document Inbound,Document Outbound,Posting data inbound,PO data inbound,Integration Rules Implementation,ReportingandMonitoring,Studio Configuration,Schema Configuration,Reporting and Monitoring |  | 14
Create and populate Datapoint Template | Sub-task | Functional Design
Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design
Add Validation Rules to Datapoint Template | Sub-task | Functional Design
Add Derivation Rules to Datapoint Template | Sub-task | Functional Design
Create EndUSer Process design | Sub-task | Functional Design
List of users and roles (permissions) | Sub-task | Functional Design |  |  | Customer to provide List
Create Studio companies and projects concept design | Sub-task | Functional Design
Document Inbound Integration | Sub-task | Functional Design
Document Outbound Integration | Sub-task | Functional Design
Posting Data Inbound Integration Documentation | Sub-task | Functional Design
Create Technical Datapoint Mapping | Sub-task | Functional Design
Create Integration rules | Sub-task | Functional Design
ReportingandMonitoring | Sub-task | Functional Design
Document reporting and monitoring concept | Sub-task | Functional Design
Create SoW | Sub-task | Functional Design
Sign SoW | Sub-task | Functional Design
Machine Learning | Epic | Pilot
Capturing Model Training | Task | Machine Learning |  |  |  | 21
Create Baseline Project | Sub-task | Capturing Model Training
Upload Training Data | Sub-task | Capturing Model Training
Annotation of Documents | Sub-task | Capturing Model Training
Perform Capturing Model QA | Sub-task | Capturing Model Training
Perform Capturing Model Results Analysis | Sub-task | Capturing Model Training
Capturing Model Development | Sub-task | Capturing Model Training
Capturing Model Evaluation | Sub-task | Capturing Model Training
Enrichment_Model_Training | Task | Machine Learning |  |  |  | 14
Create EM Ticket | Sub-task | Enrichment_Model_Training
Train EModel | Sub-task | Enrichment_Model_Training
QA Emodel | Sub-task | Enrichment_Model_Training
Emodel Results analyis | Sub-task | Enrichment_Model_Training
Integration Implementation | Epic | Pilot
Document Inbound | Task | Integration Implementation |  |  |  | 3
Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound
Support API Configuration | Sub-task | Document Inbound
Document Outbound | Task | Integration Implementation |  |  |  | 2
API Configuration Support OB | Sub-task | Document Outbound
Posting data inbound | Task | Integration Implementation |  |  |  | 2
API Configuration Support PDIB | Sub-task | Posting data inbound
PO data inbound | Task | Integration Implementation |  |  |  | 2
API Configuration Support PO | Sub-task | PO data inbound
Integration Rules Implementation | Task | Integration Implementation |  |  |  | 1
Middleware Configuration Support | Sub-task | Integration Rules Implementation
Application Implementation | Epic | Pilot
Reporting and Monitoring | Task | Application Implementation |  |  |  | 1
Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring |  |  | Insights Standard Collections for Reporting and Monitoring
Studio Configuration | Task | Application Implementation |  |  |  | 14
Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration
Creation of projects and assignment of users and models | Sub-task | Studio Configuration
Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration
Schema Configuration | Task | Application Implementation | Schema Configuration | Functional_Testing |  | 7
Create Composite Enrichment in Setup | Sub-task | Schema Configuration |  |  | Configure Attribute Prediction, Configure Master Data Enrichment
Update list of datapoints | Sub-task | Schema Configuration
Configure normalisation rules | Sub-task | Schema Configuration
Configure validation rules | Sub-task | Schema Configuration
Configure derived datapoints | Sub-task | Schema Configuration
Configure ReRouting Rules | Sub-task | Schema Configuration
Testing_Phase | Epic | Pilot
Functional_Testing | Task | Testing_Phase | Functional_Testing | System Integration Test (E2E) |  | 3
Create testing workbook | Sub-task | Functional_Testing
Share Testing Workbook and QandA Session | Sub-task | Functional_Testing
Hy to perform funct testing | Sub-task | Functional_Testing
CUS to perform funct. Testing | Sub-task | Functional_Testing
System Integration Test (E2E) | Task | Testing_Phase | System Integration Test (E2E) | User Acceptance Testing |  | 7
Run Document inbound load test | Sub-task | System Integration Test (E2E)
Run Posting Data inbound load test | Sub-task | System Integration Test (E2E)
Run Document outbound load test | Sub-task | System Integration Test (E2E)
Run Masterdata Test | Sub-task | System Integration Test (E2E)
Document inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E)
Document inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E)
Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E)
User Acceptance Testing | Task | Testing_Phase | User Acceptance Testing | Deployment |  | 21
Run Model UAT | Sub-task | User Acceptance Testing
Run Studio UAT | Sub-task | User Acceptance Testing
User Training | Epic | Pilot
User Onboarding | Task | User Training |  |  |  | 30
Request UserList | Sub-task | User Onboarding
Provide UserList | Sub-task | User Onboarding
Grant Access to HY Academy | Sub-task | User Onboarding
Finish HY Academy Training | Sub-task | User Onboarding
Intro HY continual learning tech and QandA session | Sub-task | User Onboarding |  |  | recommendations to improve model performance
Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding
Key User Admin Training and QandA | Sub-task | User Onboarding
Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding
Delivery | Epic | Pilot
Deployment | Task | Delivery | Deployment | Hypercare_Phase |  | 2
Configure reporting notifications audience and cadence | Sub-task | Deployment
Create and share the Cutover plan | Sub-task | Deployment
Cutover and Go Live | Sub-task | Deployment
Introduction Session to Hypercare Process | Sub-task | Deployment
Hypercare_Phase | Task | Delivery | Hypercare_Phase | Lessons learned |  | 21
Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase
Create Handover to CC page | Sub-task | Hypercare_Phase
Handover to Customer Care | Sub-task | Hypercare_Phase
Lessons learned | Task | Delivery |  |  |  | 1
Create lessons learned page | Sub-task | Lessons learned