## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-01-10 | R001 | Data Acquisition dependent on SAP addon release and installation - could break project timeline | High | A001 | FIE SAP DEV Team onboarding for integration implementation. FIE PM to raise ressource request to the respective team and actively following up. |  | Open
Open | 2024-01-10 | R002 | xSuite integration might take more ressources than expected | High | A002 | Discuss Solution Design extensively and support if needed |  | Open
 |  |  |  | High | A003 | Hypatos x FIE to revisit Integration and Project Timelines based on resource onboarding. Dependent on A001. Weekly follow ups. |  | Open
 |  |  |  | High | A004 | Allow a buffer for SIT |  | Open
Open | 2024-01-10 | R003 | PO Matching config and ML Training takes more ressources than expected | High | A005 | Schedule a session with HY SAP and Product Team to |  | Open
Open | 2024-01-10 | R004 | Poor PO Matching Enrichment Quality | Medium | A006 | Ensure that annoation of Line item is done right by providing annotation guideline |  | Open
Open | 2024-01-10 | R005 | Scope of Implementation not clear - customer expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-01-10 | R006 | Project Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in February 2025
Timeline subject to change – Assuming that Machine Learning Trainingdata is available on time.
Project Milestone
Go Live
SteerCo Meeting
Workshop
Oct
Nov
Dec
Jan
Feb
Mar
40
41
42
43
44
45
46
47
48
49
50
51
52
01
02
03
04
05
06
07
08
09
10
11
12
13
Today
UAT approved & Go Live decision
CUS, HY
Integration Implementation
HY
Application Implement (Studio Config.)
HY
Machine Learning ( Model training + Optimization)
CUS, HY
Design (Technical+Functional)
Ass. WS
SoW & Solution Design Sign-off
Responsible
CUS, HY
Assessment (Requirement + Data Gathering)
Activity
Training Data Confirm.
CUS, HY
Project Management
CUS, HY
User Training
CUS, HY
User Training Completed
CUS, HY
Wave 1,2,n (CompCode xx-xx)
Tech.WS
Hypercare Closing & Handover Cus. Care
CUS, HY
Delivery (GoLive & Hypercare)
Kickof WS
Func.WS
Testing (FT & SIT & UAT)
Deploy & Roll-out
Implement & Test
Assess & Design
Initiate & Plan
SOW = Statement of Work FT= Functional Testing
SIT= System Integration Testing
UAT= User Acceptance Testing

## Slide 10: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 11: Thank you
Melinda Braun
Project Manager
Melinda.braun@hypatos.ai
hypatos.ai
Dr. Ulrich Erxleben
Chief Executive Officer
uli.erxleben@hypatos.ai +49 157 736 362 22 hypatos.ai
Danail Delchev
Solution Manager
danail.delchev@hypatos.ai
hypatos.ai