## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
POC | Project
User Training | Epic | POC
User Onboarding | Task | User Training | User Onboarding | Milestone_Usertraining_completed |  | 60
Request UserList | Sub-task | User Onboarding
Provide UserList | Sub-task | User Onboarding
Grant Access to HY Academy | Sub-task | User Onboarding
Finish HY Academy Training | Sub-task | User Onboarding
Intro HY continual learning tech and QandA session | Sub-task | User Onboarding |  |  | recommendations to improve model performance
Insights Training and QandA | Sub-task | User Onboarding
Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding
Key User Admin Training and QandA | Sub-task | User Onboarding
Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding
Milestone_Usertraining_completed | Task | User Training |  |  |  | 1
Project Management | Epic | POC
Project Set up | Task | Project Management |  |  |  | 60
Create StakeholderMapping and Matrix | Sub-task | Project Set up |  |  | PM Deliverable
Create Project Governance Structure | Sub-task | Project Set up |  |  | PM Deliverable
Create Customer Documentation | Sub-task | Project Set up |  |  | Included in Handover from Sales
Document Project (confl.) | Sub-task | Project Set up
Sharepoint folder set-up | Sub-task | Project Set up |  |  | Including all relevant Files
Create Absence Planner | Sub-task | Project Set up
Create Executive Report (based on template) | Sub-task | Project Set up |  |  | PM Deliverable
Create Weekly Report (based on template) | Sub-task | Project Set up |  |  | PM Deliverable
Teams Channel Setup | Sub-task | Project Set up
Teams Page Setup | Sub-task | Project Set up |  |  | Page with most relevant Links, StakeholderMapping and FAQ
Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up
Create JourFixe PMO and Steerco Series | Sub-task | Project Set up
Create Jira Work Mangagement Project | Sub-task | Project Set up
Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up
Create RAID Log | Sub-task | Project Set up |  |  | PM Deliverable
Create Project timeline | Sub-task | Project Set up
Create Jira Advanced roadmap | Sub-task | Project Set up |  |  | Optional
Create Project Plan | Sub-task | Project Set up
Identification of project deliverables | Sub-task | Project Set up
Create Kickoff Slidedeck | Sub-task | Project Set up
Create Assessment Workshop Slidedeck | Sub-task | Project Set up |  |  | PM Deliverable
Create Functional Workshop Slidedeck | Sub-task | Project Set up |  |  | PM Deliverable
Schedule Executive Status Meetings | Sub-task | Project Set up |  |  | PM Deliverable (monthly)
Schedule JourFixe Meeting | Sub-task | Project Set up |  |  | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting)
Schedule Workshops (Assessment WS) | Sub-task | Project Set up
Schedule Workshops (Functional WS) | Sub-task | Project Set up
MileStone_Kickoff Workshop | Task | Project Management | MileStone_Kickoff Workshop | Data Acquisition,Requirement Analysis |  | 1
Assessment | Epic | POC
Data Acquisition | Task | Assessment |  |  |  | 17
Prepare and send out data and documentation request | Sub-task | Data Acquisition
Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition
Create Studio Company | Sub-task | Data Acquisition |  |  | [TEST]
Create apiv2 credentials | Sub-task | Data Acquisition
Create Training Data Schema | Sub-task | Data Acquisition
Create Training Data Project | Sub-task | Data Acquisition
Create QA Project | Sub-task | Data Acquisition
Create Basic CompEnrichment Config | Sub-task | Data Acquisition
Create Basic LLM Config | Sub-task | Data Acquisition
Ingest GL Account Data | Sub-task | Data Acquisition
Ingest CostCenter Data | Sub-task | Data Acquisition
Ingest Company Master Data | Sub-task | Data Acquisition
Ingest Purchase Order Data | Sub-task | Data Acquisition
Ingest Supplier Master Data | Sub-task | Data Acquisition
Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition
Data and documentation quality and completeness review | Sub-task | Data Acquisition
Create Sample Dataset for ML Training | Sub-task | Data Acquisition |  |  | Create a list of top vendorids, or companycodes in scope
Requirement Analysis | Task | Assessment | Requirement Analysis | MileStone_AI_Model_Training_Data_Confirmation |  | 17
Posting data analysis | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template
Perform Master data analysis | Sub-task | Requirement Analysis |  |  | ERP master data
Perform PO data analysis | Sub-task | Requirement Analysis |  |  | ERP PO data
Perform Document analysis | Sub-task | Requirement Analysis |  |  | Documents (datapoints), Document types, document languages (regions) analysis
Create Document Processing Workflow | Sub-task | Requirement Analysis |  |  | Process documentation, Hypatos Studio Standard process template
Perform System analysis | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template
Prepare Assessment Workshop | Sub-task | Requirement Analysis |  |  | Update questions, Slidedeck
Perform Assessment Workshop | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis
Prepare Functional Workshop | Sub-task | Requirement Analysis
Perform Functional Workshop | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable
Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis |  |  | CUS Deliverable
Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis |  |  | CUS Deliverable
MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | MileStone_AI_Model_Training_Data_Confirmation | Functional & Technical Solution Design |  | 1
Design | Epic | POC
Functional & Technical Solution Design | Task | Design | Functional & Technical Solution Design | MileStone_SoW and Solution Design Sign-Off |  | 14
Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design
Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design
Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design
Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design
Create EndUSer Process design | Sub-task | Functional & Technical Solution Design
List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design |  |  | CUS Deliverable - Customer to provide List of Users
Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design
Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design
Create Integration rules | Sub-task | Functional & Technical Solution Design
ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design
Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design
Update SoW | Sub-task | Functional & Technical Solution Design
Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design
MileStone_SoW and Solution Design Sign-Off | Task | Design | MileStone_SoW and Solution Design Sign-Off | Pre_trained_AI_Extraction_Model,Custom_trained_AI_Extraction_Model,Attribute_Prediction_Model_Configuration_Approver,Attribute_Prediction_Model_Configuration_GL_Account,Attribute_Prediction_Model_Configuration_CostCenter,Attribute_Prediction_Model_Configuration_COElement,Hypatos_Insights_Configuration,Hypatos_Studio_Configuration,Schema Configuration,Supplier_Master_Data_Enrichment,Company_Master_Data_Enrichment,PO_LINE_Matching_Enrichment |  | 1
Machine Learning | Epic | POC
Pre_trained_AI_Extraction_Model | Task | Machine Learning | Pre_trained_AI_Extraction_Model | Functional_Testing |  | 21
Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model
Custom_trained_AI_Extraction_Model | Task | Machine Learning |  |  |  | 21
Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model
Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model
Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model
Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model
Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model
Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model
Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model
Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning |  |  |  | 7
Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver
Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver
QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver
Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver
Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning |  |  |  | 7
Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account
Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account
QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account
Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account
Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning |  |  |  | 7
Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter
Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter
QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter
Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter
Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning |  |  |  | 7
Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement
Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement
QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement
Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement
Supplier_Master_Data_Enrichment | Task | Machine Learning |  |  |  | 2
Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment
Company_Master_Data_Enrichment | Task | Machine Learning |  |  |  | 2
Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment
PO_LINE_Matching_Enrichment | Task | Machine Learning |  |  |  | 2
CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment
Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment
Application Implementation | Epic | POC
Hypatos_Insights_Configuration | Task | Application Implementation |  |  |  | 1
Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Hypatos_Studio_Configuration | Task | Application Implementation |  |  |  | 14
Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration
Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration
Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration
Create LLM Config | Sub-task | Hypatos_Studio_Configuration
Configure Translation Service | Sub-task | Hypatos_Studio_Configuration
Schema Configuration | Task | Application Implementation |  |  |  | 7
Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration
Update list of datapoints | Sub-task | Schema Configuration
Configure normalisation rules | Sub-task | Schema Configuration
Configure validation rules | Sub-task | Schema Configuration
Configure derived datapoints | Sub-task | Schema Configuration
Testing | Epic | POC
Functional_Testing | Task | Testing | Functional_Testing | User Acceptance Testing |  | 2
Create testing plan workbook | Sub-task | Functional_Testing |  |  | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report
Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing
Hy to perform funct testing | Sub-task | Functional_Testing
CUS to perform funct. Testing | Sub-task | Functional_Testing
User Acceptance Testing | Task | Testing | User Acceptance Testing | MileStone_UAT approved |  | 5
Run Model UAT | Sub-task | User Acceptance Testing
Run Studio UAT | Sub-task | User Acceptance Testing
Create Results Overview Slidedeck | Sub-task | User Acceptance Testing
Present Results Overview Slidedeck | Sub-task | User Acceptance Testing
MileStone_UAT approved | Task | Testing | MileStone_UAT approved | Result_Presentation_Preperation |  | 1
Delivery | Epic | POC
Result_Presentation_Preperation | Task | Delivery | Result_Presentation_Preperation | MileStone_Result_Presentation |  | 2
Create Result_Presentation | Sub-task | Result_Presentation_Preperation
MileStone_Result_Presentation | Task | Delivery | MileStone_Result_Presentation | Lessons learned |  | 1
Lessons learned | Task | Delivery |  |  |  | 1
Create lessons learned page | Sub-task | Lessons learned