## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-6254 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2026-01-19 | 2026-01-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-6253 | Lessons learned | Task | Delivery | To Do | 2026-01-19 | 2026-01-20 |  | stephan.kuche |  | []
TD-6252 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2026-01-18 | 2026-01-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-6251 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2025-12-28 | 2026-01-18 |  | stephan.kuche |  | []
TD-6250 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2025-12-28 | 2026-01-18 |  | stephan.kuche |  | []
TD-6249 | Hypercare_Phase | Task | Delivery | To Do | 2025-12-28 | 2026-01-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-6248 | MileStone_Go Live | Task | Delivery | To Do | 2025-12-27 | 2025-12-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-6247 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2025-12-25 | 2025-12-27 |  | stephan.kuche |  | []
TD-6246 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2025-12-28 | 2026-01-18 |  | stephan.kuche |  | []
TD-6245 | Cutover and Go Live | Sub-task | Deployment | To Do | 2025-12-25 | 2025-12-27 |  | stephan.kuche |  | []
TD-6244 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2025-12-25 | 2025-12-27 |  | stephan.kuche |  | []
TD-6243 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2025-12-25 | 2025-12-27 |  | stephan.kuche |  | []
TD-6242 | Deployment | Task | Delivery | To Do | 2025-12-25 | 2025-12-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-6241 | Delivery | Epic | Pilot | To Do | 2025-12-25 | 2026-01-20 |  | stephan.kuche |  | []
TD-6240 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2025-12-24 | 2025-12-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-6239 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-12-03 | 2025-12-24 |  | stephan.kuche |  | []
TD-6238 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-12-03 | 2025-12-24 |  | stephan.kuche |  | []
TD-6237 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2025-12-03 | 2025-12-24 |  | stephan.kuche |  | []
TD-6236 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2025-12-03 | 2025-12-24 |  | stephan.kuche |  | []
TD-6235 | User Acceptance Testing | Task | Testing | To Do | 2025-12-03 | 2025-12-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-6234 | MileStone_SIT_approval | Task | Testing | To Do | 2025-12-02 | 2025-12-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-6233 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | []
TD-6232 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | []
TD-6231 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | []
TD-6230 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | []
TD-6229 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6228 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6227 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | []
TD-6226 | System Integration Test (E2E) | Task | Testing | To Do | 2025-11-25 | 2025-12-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-6225 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2025-11-22 | 2025-11-25 |  | stephan.kuche |  | []
TD-6224 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2025-11-22 | 2025-11-25 |  | stephan.kuche |  | []
TD-6223 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2025-11-22 | 2025-11-25 |  | stephan.kuche |  | []
TD-6222 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2025-11-22 | 2025-11-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-6221 | Functional_Testing | Task | Testing | To Do | 2025-11-22 | 2025-11-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}]
TD-6220 | Testing | Epic | Pilot | To Do | 2025-11-22 | 2025-12-25 |  | stephan.kuche |  | []
TD-6219 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6218 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6217 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6216 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6215 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6214 | Schema Configuration | Task | Application Implementation | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6213 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6212 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6211 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6210 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6209 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6208 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6207 | Configure Error Analysis Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-11-08 | 2025-11-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6206 | Configure QA Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-11-08 | 2025-11-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6205 | Configure Model Insights Dashboard | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-11-08 | 2025-11-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-6204 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2025-11-08 | 2025-11-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6203 | Application Implementation | Epic | Pilot | To Do | 2025-11-08 | 2025-11-22 |  | stephan.kuche |  | []
TD-6202 | Integration_API_Configured | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-29 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6201 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6200 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6199 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6198 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2025-11-08 | 2025-11-09 |  | stephan.kuche |  | []
TD-6197 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6196 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6195 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6194 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6193 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6192 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6191 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6190 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | []
TD-6189 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | []
TD-6188 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2025-11-08 | 2025-11-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6187 | Integration Implementation | Epic | Pilot | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6186 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6185 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6184 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6183 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6182 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6181 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | []
TD-6180 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6179 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6178 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6177 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6176 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6175 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6174 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6173 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6172 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6171 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6170 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6169 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6168 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6167 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6166 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6165 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6164 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6163 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6162 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6161 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | []
TD-6160 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6159 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6158 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6157 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6156 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6155 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6154 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6153 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6152 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6151 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6150 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-6149 | Machine Learning | Epic | Pilot | To Do | 2025-11-08 | 2025-11-29 |  | stephan.kuche |  | []
TD-6148 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2025-11-07 | 2025-11-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-6147 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6146 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6145 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6144 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6143 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6142 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6141 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6140 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6139 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6138 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6137 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-6136 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6135 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6134 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6133 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6132 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | []
TD-6131 | Functional & Technical Solution Design | Task | Design | To Do | 2025-10-24 | 2025-11-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TD-6130 | Design | Epic | Pilot | To Do | 2025-10-24 | 2025-11-08 |  | stephan.kuche |  | []
TD-6129 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2025-10-23 | 2025-10-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-6128 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6127 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6126 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | CUS Deliverable | stephan.kuche |  | []
TD-6125 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | CUS Deliverable | stephan.kuche |  | []
TD-6124 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-6123 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6122 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6121 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-6120 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6119 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-6118 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-6117 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | ERP PO data | stephan.kuche |  | []
TD-6116 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | ERP master data | stephan.kuche |  | []
TD-6115 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2025-10-06 | 2025-10-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-6114 | Requirement Analysis | Task | Assessment | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-6113 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-6112 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6111 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6110 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6109 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6108 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6107 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6106 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6105 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6104 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6103 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6102 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6101 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6100 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6099 | Create QA Project | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6098 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6097 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6096 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6095 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6094 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6093 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6092 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6091 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6090 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-6089 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6088 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-6087 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6086 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-6085 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6084 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6083 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 | [TEST] | stephan.kuche |  | []
TD-6082 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6081 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | []
TD-6080 | Data Acquisition | Task | Assessment | To Do | 2025-10-06 | 2025-10-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-6079 | Assessment | Epic | Pilot | To Do | 2025-10-06 | 2025-10-24 |  | stephan.kuche |  | []
TD-6078 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2025-10-01 | 2025-10-02 |  | stephan.kuche |  | []
TD-6077 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6076 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6075 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6074 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-6073 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-6072 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6071 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6070 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6069 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6068 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6067 | Create Project Plan | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6066 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | Optional | stephan.kuche |  | []
TD-6065 | Create Project timeline | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6064 | Create RAID Log | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6063 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6062 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6061 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6060 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6059 | Teams Page Setup | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-6058 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6057 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6056 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6055 | Create Absence Planner | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6054 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | Including all relevant Files | stephan.kuche |  | []
TD-6053 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6052 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-6051 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6050 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2025-10-01 | 2025-10-06 | PM Deliverable | stephan.kuche |  | []
TD-6049 | Project Set up | Task | Project Management | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-6048 | Project Management | Epic | Pilot | To Do | 2025-10-01 | 2025-10-06 |  | stephan.kuche |  | []
TD-6047 | Milestone_Usertraining_completed | Task | User Training | To Do | 2026-01-19 | 2026-01-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-6046 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6045 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6044 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6043 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6042 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 | recommendations to improve model performance | stephan.kuche |  | []
TD-6041 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6040 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6039 | Provide UserList | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6038 | Request UserList | Sub-task | User Onboarding | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | []
TD-6037 | User Onboarding | Task | User Training | To Do | 2025-10-01 | 2026-01-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-6036 | User Training | Epic | Pilot | To Do | 2025-10-01 | 2026-01-20 |  | stephan.kuche |  | []
TD-6035 | Pilot | Project |  | To Do | 2025-10-01 | 2026-01-20 |  | stephan.kuche |  | []
TD-6034 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2025-02-08 | 2025-02-09 |  | stephan.kuche |  | []
TD-6033 | Application Implementation | Epic | Pilot | To Do | 2025-02-08 | 2025-02-22 |  | stephan.kuche |  | []
TD-6032 | Integration_API_Configured | Task | Integration Implementation | To Do | 2025-02-08 | 2025-03-01 | CUS to create an API client | stephan.kuche |  | []
TD-6031 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6030 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6029 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6028 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2025-02-08 | 2025-02-09 |  | stephan.kuche |  | []
TD-6027 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-09 |  | stephan.kuche |  | []
TD-6026 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6025 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6024 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6023 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6022 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6021 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6020 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6019 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6018 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2025-02-08 | 2025-02-11 |  | stephan.kuche |  | []
TD-6017 | Integration Implementation | Epic | Pilot | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-6016 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6015 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6014 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6013 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6012 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6011 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6010 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-10 |  | stephan.kuche |  | []
TD-6009 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6008 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6007 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6006 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6005 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6004 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6003 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6002 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6001 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-6000 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5999 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5998 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5997 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5996 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5995 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5994 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5993 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5992 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5991 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5990 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2025-02-08 | 2025-02-15 |  | stephan.kuche |  | []
TD-5989 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5988 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5987 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5986 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5985 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5984 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5983 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5982 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5981 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5980 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5979 | Machine Learning | Epic | Pilot | To Do | 2025-02-08 | 2025-03-01 |  | stephan.kuche |  | []
TD-5978 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2025-02-07 | 2025-02-08 |  | stephan.kuche |  | []
TD-5977 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5976 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5975 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5974 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5973 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5972 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5971 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5970 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5969 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5968 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5967 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-5966 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5965 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5964 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5963 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5962 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5961 | Functional & Technical Solution Design | Task | Design | To Do | 2025-01-24 | 2025-02-07 |  | stephan.kuche |  | []
TD-5960 | Design | Epic | Pilot | To Do | 2025-01-24 | 2025-02-08 |  | stephan.kuche |  | []
TD-5959 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2025-01-23 | 2025-01-24 |  | stephan.kuche |  | []
TD-5958 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5957 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5956 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-5955 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-5954 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-5953 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5952 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5951 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-5950 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5949 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5948 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5947 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | ERP PO data | stephan.kuche |  | []
TD-5946 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | ERP master data | stephan.kuche |  | []
TD-5945 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2025-01-06 | 2025-01-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-5944 | Requirement Analysis | Task | Assessment | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5943 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-5942 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5941 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5940 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5939 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5938 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5937 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5936 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5935 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5934 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5933 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5932 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5931 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5930 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5929 | Create QA Project | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5928 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5927 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5926 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5925 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5924 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5923 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5922 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5921 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5920 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-5919 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5918 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-5917 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5916 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-5915 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5914 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5913 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 | [TEST] | stephan.kuche |  | []
TD-5912 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5911 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5910 | Data Acquisition | Task | Assessment | To Do | 2025-01-06 | 2025-01-23 |  | stephan.kuche |  | []
TD-5909 | Assessment | Epic | Pilot | To Do | 2025-01-06 | 2025-01-24 |  | stephan.kuche |  | []
TD-5908 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2025-01-01 | 2025-01-02 |  | stephan.kuche |  | []
TD-5907 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5906 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5905 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5904 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-5903 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-5902 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5901 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5900 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5899 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5898 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5897 | Create Project Plan | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5896 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | Optional | stephan.kuche |  | []
TD-5895 | Create Project timeline | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5894 | Create RAID Log | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5893 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5892 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5891 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5890 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5889 | Teams Page Setup | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-5888 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5887 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5886 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5885 | Create Absence Planner | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5884 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-5883 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5882 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-5881 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5880 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2025-01-01 | 2025-01-06 | PM Deliverable | stephan.kuche |  | []
TD-5879 | Project Set up | Task | Project Management | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5878 | Project Management | Epic | Pilot | To Do | 2025-01-01 | 2025-01-06 |  | stephan.kuche |  | []
TD-5877 | Milestone_Usertraining_completed | Task | User Training | To Do | 2025-04-21 | 2025-04-22 |  | stephan.kuche |  | []
TD-5876 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5875 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5874 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5873 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5872 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 | recommendations to improve model performance | stephan.kuche |  | []
TD-5871 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5870 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5869 | Provide UserList | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5868 | Request UserList | Sub-task | User Onboarding | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5867 | User Onboarding | Task | User Training | To Do | 2025-01-01 | 2025-04-21 |  | stephan.kuche |  | []
TD-5866 | User Training | Epic | Pilot | To Do | 2025-01-01 | 2025-04-22 |  | stephan.kuche |  | []
TD-5865 | Pilot | Project |  | To Do | 2025-01-01 | 2025-04-22 |  | stephan.kuche |  | []
TD-5864 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-12-20 | 2024-12-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5863 | Lessons learned | Task | Delivery | To Do | 2024-12-20 | 2024-12-21 |  | stephan.kuche |  | []
TD-5862 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-12-19 | 2024-12-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5861 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-11-28 | 2024-12-19 |  | stephan.kuche |  | []
TD-5860 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-11-28 | 2024-12-19 |  | stephan.kuche |  | []
TD-5859 | Hypercare_Phase | Task | Delivery | To Do | 2024-11-28 | 2024-12-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5858 | MileStone_Go Live | Task | Delivery | To Do | 2024-11-27 | 2024-11-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5857 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-11-25 | 2024-11-27 |  | stephan.kuche |  | []
TD-5856 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-11-28 | 2024-12-19 |  | stephan.kuche |  | []
TD-5855 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-11-25 | 2024-11-27 |  | stephan.kuche |  | []
TD-5854 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-11-25 | 2024-11-27 |  | stephan.kuche |  | []
TD-5853 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-11-25 | 2024-11-27 |  | stephan.kuche |  | []
TD-5852 | Deployment | Task | Delivery | To Do | 2024-11-25 | 2024-11-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5851 | Delivery | Epic | PILOT TO REVIEW | To Do | 2024-11-25 | 2024-12-21 |  | stephan.kuche |  | []
TD-5850 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-11-24 | 2024-11-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5849 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-11-03 | 2024-11-24 |  | stephan.kuche |  | []
TD-5848 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-11-03 | 2024-11-24 |  | stephan.kuche |  | []
TD-5847 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-11-03 | 2024-11-24 |  | stephan.kuche |  | []
TD-5846 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-11-03 | 2024-11-24 |  | stephan.kuche |  | []
TD-5845 | User Acceptance Testing | Task | Testing | To Do | 2024-11-03 | 2024-11-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-5844 | MileStone_SIT_approval | Task | Testing | To Do | 2024-11-02 | 2024-11-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5843 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | []
TD-5842 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | []
TD-5841 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | []
TD-5840 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | []
TD-5839 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5838 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5837 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | []
TD-5836 | System Integration Test (E2E) | Task | Testing | To Do | 2024-10-26 | 2024-11-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5835 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-10-23 | 2024-10-26 |  | stephan.kuche |  | []
TD-5834 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-10-23 | 2024-10-26 |  | stephan.kuche |  | []
TD-5833 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-10-23 | 2024-10-26 |  | stephan.kuche |  | []
TD-5832 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-10-23 | 2024-10-26 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-5831 | Functional_Testing | Task | Testing | To Do | 2024-10-23 | 2024-10-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5830 | Testing | Epic | PILOT TO REVIEW | To Do | 2024-10-23 | 2024-11-25 |  | stephan.kuche |  | []
TD-5829 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5828 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5827 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5826 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5825 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5824 | Schema Configuration | Task | Application Implementation | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5823 | Configure Translation Service | Sub-task | Studio Configuration | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5822 | Create LLM Config | Sub-task | Studio Configuration | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5821 | Configure ReRouting Rules | Sub-task | Studio Configuration | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5820 | Create projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5819 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5818 | Studio Configuration | Task | Application Implementation | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5817 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-10-09 | 2024-10-10 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5816 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-10-09 | 2024-10-10 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5815 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-10-09 | 2024-10-10 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5814 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-10-09 | 2024-10-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5813 | Application Implementation | Epic | PILOT TO REVIEW | To Do | 2024-10-09 | 2024-10-23 |  | stephan.kuche |  | []
TD-5812 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-30 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5811 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5810 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5809 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5808 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-10-09 | 2024-10-10 |  | stephan.kuche |  | []
TD-5807 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5806 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5805 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5804 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5803 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5802 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5801 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5800 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | []
TD-5799 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | []
TD-5798 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-10-09 | 2024-10-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5797 | Integration Implementation | Epic | PILOT TO REVIEW | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5796 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5795 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5794 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5793 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5792 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5791 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | []
TD-5790 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5789 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5788 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5787 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5786 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5785 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5784 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5783 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5782 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5781 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5780 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5779 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5778 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5777 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5776 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5775 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5774 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5773 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5772 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5771 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | []
TD-5770 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5769 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5768 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5767 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5766 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5765 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5764 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5763 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5762 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5761 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5760 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5759 | Machine Learning | Epic | PILOT TO REVIEW | To Do | 2024-10-09 | 2024-10-30 |  | stephan.kuche |  | []
TD-5758 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-10-08 | 2024-10-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-5757 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5756 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5755 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5754 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5753 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5752 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5751 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5750 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5749 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5748 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5747 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-5746 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5745 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5744 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5743 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5742 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | []
TD-5741 | Functional & Technical Solution Design | Task | Design | To Do | 2024-09-24 | 2024-10-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5740 | Design | Epic | PILOT TO REVIEW | To Do | 2024-09-24 | 2024-10-09 |  | stephan.kuche |  | []
TD-5739 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-09-23 | 2024-09-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5738 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5737 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5736 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | CUS Deliverable | stephan.kuche |  | []
TD-5735 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | CUS Deliverable | stephan.kuche |  | []
TD-5734 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-5733 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5732 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5731 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-5730 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5729 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5728 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5727 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | ERP PO data | stephan.kuche |  | []
TD-5726 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | ERP master data | stephan.kuche |  | []
TD-5725 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-09-06 | 2024-09-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-5724 | Requirement Analysis | Task | Assessment | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5723 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-5722 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5721 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5720 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5719 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5718 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5717 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5716 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5715 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5714 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5713 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5712 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5711 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5710 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5709 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5708 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5707 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5706 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5705 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5704 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5703 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5702 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5701 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5700 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-5699 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5698 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-5697 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5696 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-5695 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5694 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5693 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 | [TEST] | stephan.kuche |  | []
TD-5692 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5691 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | []
TD-5690 | Data Acquisition | Task | Assessment | To Do | 2024-09-06 | 2024-09-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5689 | Assessment | Epic | PILOT TO REVIEW | To Do | 2024-09-06 | 2024-09-24 |  | stephan.kuche |  | []
TD-5688 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-09-01 | 2024-09-02 |  | stephan.kuche |  | []
TD-5687 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5686 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5685 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5684 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-5683 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-5682 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5681 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5680 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5679 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5678 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5677 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5676 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | Optional | stephan.kuche |  | []
TD-5675 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5674 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5673 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5672 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5671 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5670 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5669 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-5668 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5667 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5666 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5665 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5664 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | Including all relevant Files | stephan.kuche |  | []
TD-5663 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5662 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-5661 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5660 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-09-01 | 2024-09-06 | PM Deliverable | stephan.kuche |  | []
TD-5659 | Project Set up | Task | Project Management | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5658 | Project Management | Epic | PILOT TO REVIEW | To Do | 2024-09-01 | 2024-09-06 |  | stephan.kuche |  | []
TD-5657 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-12-30 | 2024-12-31 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-5656 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5655 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5654 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5653 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5652 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 | recommendations to improve model performance | stephan.kuche |  | []
TD-5651 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5650 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5649 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5648 | Request UserList | Sub-task | User Onboarding | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | []
TD-5647 | User Onboarding | Task | User Training | To Do | 2024-09-01 | 2024-12-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-5646 | User Training | Epic | PILOT TO REVIEW | To Do | 2024-09-01 | 2024-12-31 |  | stephan.kuche |  | []
TD-5645 | PILOT TO REVIEW | Project |  | To Do | 2024-09-01 | 2024-12-31 |  | stephan.kuche |  | []
TD-5644 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-11-19 | 2024-11-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5643 | Lessons learned | Task | Delivery | To Do | 2024-11-19 | 2024-11-20 |  | stephan.kuche |  | []
TD-5642 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-11-18 | 2024-11-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5641 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | []
TD-5640 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | []
TD-5639 | Hypercare_Phase | Task | Delivery | To Do | 2024-10-28 | 2024-11-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5638 | MileStone_Go Live | Task | Delivery | To Do | 2024-10-27 | 2024-10-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5637 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5636 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5635 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5634 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | []
TD-5633 | Deployment | Task | Delivery | To Do | 2024-10-25 | 2024-10-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5632 | Delivery | Epic | Pilot | To Do | 2024-10-25 | 2024-11-20 |  | stephan.kuche |  | []
TD-5631 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-10-24 | 2024-10-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5630 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5629 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5628 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5627 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | []
TD-5626 | User Acceptance Testing | Task | Testing | To Do | 2024-10-03 | 2024-10-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-5625 | MileStone_SIT_approval | Task | Testing | To Do | 2024-10-02 | 2024-10-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5624 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5623 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5622 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5621 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5620 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5619 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5618 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | []
TD-5617 | System Integration Test (E2E) | Task | Testing | To Do | 2024-09-25 | 2024-10-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5616 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5615 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5614 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | []
TD-5613 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-09-22 | 2024-09-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-5612 | Functional_Testing | Task | Testing | To Do | 2024-09-22 | 2024-09-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5611 | Testing | Epic | Pilot | To Do | 2024-09-22 | 2024-10-25 |  | stephan.kuche |  | []
TD-5610 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5609 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5608 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5607 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5606 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5605 | Schema Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5604 | Configure Translation Service | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5603 | Create LLM Config | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5602 | Configure ReRouting Rules | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5601 | Create projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5600 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5599 | Studio Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5598 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5597 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5596 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-09-08 | 2024-09-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5595 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5594 | Application Implementation | Epic | Pilot | To Do | 2024-09-08 | 2024-09-22 |  | stephan.kuche |  | []
TD-5593 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-29 | CUS to create an API client | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5592 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5591 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-08-01 | 2024-08-04 |  | stephan.kuche |  | []
TD-5590 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5589 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | []
TD-5588 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5587 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5586 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5585 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5584 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5583 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5582 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5581 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | []
TD-5580 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | []
TD-5579 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-09-08 | 2024-09-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5578 | Integration Implementation | Epic | Pilot | To Do | 2024-08-01 | 2024-09-29 |  | stephan.kuche |  | []
TD-5577 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5576 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5575 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5574 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5573 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5572 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | []
TD-5571 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5570 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5569 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5568 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5567 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5566 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5565 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5564 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5563 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5562 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5561 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5560 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5559 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5558 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5557 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5556 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5555 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5554 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5553 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5552 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | []
TD-5551 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5550 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5549 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5548 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5547 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5546 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5545 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5544 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5543 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5542 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5541 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5540 | Machine Learning | Epic | Pilot | To Do | 2024-09-08 | 2024-09-29 |  | stephan.kuche |  | []
TD-5539 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-09-07 | 2024-09-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Boomi_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_Coupa_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_API_Configured'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-5538 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5537 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5536 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5535 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5534 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5533 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5532 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5531 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5530 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5529 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5528 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-5527 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5526 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5525 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5524 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5523 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | []
TD-5522 | Functional & Technical Solution Design | Task | Design | To Do | 2024-08-24 | 2024-09-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5521 | Design | Epic | Pilot | To Do | 2024-08-24 | 2024-09-08 |  | stephan.kuche |  | []
TD-5520 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-08-23 | 2024-08-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5519 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5518 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5517 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | CUS Deliverable | stephan.kuche |  | []
TD-5516 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | CUS Deliverable | stephan.kuche |  | []
TD-5515 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-5514 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5513 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5512 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-5511 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5510 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5509 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5508 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | ERP PO data | stephan.kuche |  | []
TD-5507 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | ERP master data | stephan.kuche |  | []
TD-5506 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-08-06 | 2024-08-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-5505 | Requirement Analysis | Task | Assessment | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5504 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-5503 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5502 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5501 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5500 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5499 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5498 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5497 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5496 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5495 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5494 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5493 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5492 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5491 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5490 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5489 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5488 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5487 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5486 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5485 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5484 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5483 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5482 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5481 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-5480 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5479 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-5478 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5477 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-5476 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5475 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5474 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 | [TEST] | stephan.kuche |  | []
TD-5473 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5472 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | []
TD-5471 | Data Acquisition | Task | Assessment | To Do | 2024-08-06 | 2024-08-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5470 | Assessment | Epic | Pilot | To Do | 2024-08-06 | 2024-08-24 |  | stephan.kuche |  | []
TD-5469 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-08-01 | 2024-08-02 |  | stephan.kuche |  | []
TD-5468 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5467 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5466 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5465 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-5464 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-5463 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5462 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5461 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5460 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5459 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5458 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5457 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Optional | stephan.kuche |  | []
TD-5456 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5455 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5454 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5453 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5452 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5451 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5450 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-5449 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5448 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5447 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5446 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5445 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Including all relevant Files | stephan.kuche |  | []
TD-5444 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5443 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-5442 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5441 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-08-01 | 2024-08-06 | PM Deliverable | stephan.kuche |  | []
TD-5440 | Project Set up | Task | Project Management | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5439 | Project Management | Epic | Pilot | To Do | 2024-08-01 | 2024-08-06 |  | stephan.kuche |  | []
TD-5438 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-11-29 | 2024-11-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-5437 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5436 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5435 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5434 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5433 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 | recommendations to improve model performance | stephan.kuche |  | []
TD-5432 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5431 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5430 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5429 | Request UserList | Sub-task | User Onboarding | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | []
TD-5428 | User Onboarding | Task | User Training | To Do | 2024-08-01 | 2024-11-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-5427 | User Training | Epic | Pilot | To Do | 2024-08-01 | 2024-11-30 |  | stephan.kuche |  | []
TD-5426 | Pilot | Project |  | To Do | 2024-08-01 | 2024-11-30 |  | stephan.kuche |  | []