## WilhIssueBluePrintRollout
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Roll-outWilhelmsen | Project
0.ProjectManagement | Epic | Roll-outWilhelmsen
0_1-Update_all_related_dates_in_this_project | Task | 0.ProjectManagement |  |  |  | 1
0_2-Update_roll-out_plan | Task | 0.ProjectManagement |  |  | File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E | 1
0_3-Internal_meetings | Task | 0.ProjectManagement |  |  | Task to log general internal meetings | 10
1.ProcessDiscovery | Epic | Roll-outWilhelmsen
1_1-Data_Acquisition | Task | 1.ProcessDiscovery | 1_1-Data_Acquisition | 1_2-Requirement_Gathering |  | 3
Training&PostingDataRequest | Sub-task | 1_1-Data_Acquisition
PostingDataAnalysis | Sub-task | 1_1-Data_Acquisition |  |  | Analyze posting data and determine top suppliers (>90% coverage)
TrainingDataAssessment | Sub-task | 1_1-Data_Acquisition |  |  | Check if all top suppliers has sample documents with specified naming convention
Requestadditionaldocumentsifrequired | Sub-task | 1_1-Data_Acquisition |  |  | Request if any top supplier document is missing
TrainingData/DocumentSetPreparation | Sub-task | 1_1-Data_Acquisition |  |  | Prepare training, annotation documents
Matchtrainingdocumentswithpostingdata | Sub-task | 1_1-Data_Acquisition |  |  | Match selected documents with posting data
1_2-Requirement_Gathering | Task | 1.ProcessDiscovery | 1_2-Requirement_Gathering | 2_1-Capturing_Model_Training,2_2-Enrichment_Model_Training |  | 3
ProvideDigitalizationDetailsformtoLocalFinanceTeamandaskexamplesforEdgecases | Sub-task | 1_2-Requirement_Gathering |  |  | EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y
ProvideAssessmentGatheringandTrainingDataFolders | Sub-task | 1_2-Requirement_Gathering |  |  | Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data
[ML]DemoProjectCreationforRequirementsGatheringMeeting | Sub-task | 1_2-Requirement_Gathering |  |  | Take the example from [ML] Project - [OC Entities][Phase 3] Oman
RequirementGatheringMeeting | Sub-task | 1_2-Requirement_Gathering
RequestexamplesforEdgecases | Sub-task | 1_2-Requirement_Gathering
Completefullset-upoftrainingdataforallofthetopsupplierswithEdgecasessharedduringrequirementssession | Sub-task | 1_2-Requirement_Gathering
UpdateWHLRequirementList | Sub-task | 1_2-Requirement_Gathering |  |  | https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
RequirementGatheringFinalization | Sub-task | 1_2-Requirement_Gathering
2.ModelTraining | Epic | Roll-outWilhelmsen
2_1-Capturing_Model_Training | Task | 2.ModelTraining | 2_1-Capturing_Model_Training | 2_3-Model_Fine_Tuning |  | 3
Createbaseline(groundtruth)projecttoannotate[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from [ML] Project - NZ_Annotation
Uploaddocumentsselectedforannotationtogroundtruthproject(TopsuppliersandEdgecases) | Sub-task | 2_1-Capturing_Model_Training
Createataskforannotation(adddetailsperrequirements) | Sub-task | 2_1-Capturing_Model_Training
Validateannotationresultswithpostingdata | Sub-task | 2_1-Capturing_Model_Training
Improveannotationqualitybasedonvalidationwithpostingdata | Sub-task | 2_1-Capturing_Model_Training
CreateTrainingProject[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from[ML] Project - [Training][PROD][NZ]
UploadselectedtrainingdocumentsfrombaselineprojecttoTrainingProject[ML] | Sub-task | 2_1-Capturing_Model_Training
CreateQAProject[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from [ML] Project - [QA] NZ
ConfigureQAprojectwithCompositeEnrichmentIndex | Sub-task | 2_1-Capturing_Model_Training
CreateLLMPromptingService[ML] | Sub-task | 2_1-Capturing_Model_Training
Uploadbaseline(groundtruth)documentstoQAProject[ML] | Sub-task | 2_1-Capturing_Model_Training
CreateErrorAnalysisDashboard | Sub-task | 2_1-Capturing_Model_Training
AnalyzeQAresultsandaccuracy | Sub-task | 2_1-Capturing_Model_Training
2_2-Enrichment_Model_Training | Task | 2.ModelTraining | 2_2-Enrichment_Model_Training | 2_3-Model_Fine_Tuning |  | 1
CreateIMPtrainingproject[TEST] | Sub-task | 2_2-Enrichment_Model_Training
ContactwithIMtoenableIMPpipeline | Sub-task | 2_2-Enrichment_Model_Training
UploaddocumentstoIMPtrainingproject | Sub-task | 2_2-Enrichment_Model_Training
TrainsuppliersusingdocumentsuploadedtoIMPproject | Sub-task | 2_2-Enrichment_Model_Training
2_3-Model_Fine_Tuning | Task | 2.ModelTraining | 2_3-Model_Fine_Tuning | 3_1-Create_Projects_[TEST] |  | 1
Improve/OptimizeLLMPromptingServicepromptwithErrorAnalysisresults | Sub-task | 2_3-Model_Fine_Tuning
AddadditionalsupplierstoIMPprojectifrequired | Sub-task | 2_3-Model_Fine_Tuning
3.StudioConfiguration | Epic | Roll-outWilhelmsen
3_1-Create_Projects_[TEST] | Task | 3.StudioConfiguration | 3_1-Create_Projects_[TEST] | 3_2-Configure_Projects_[TEST] |  | 1
Configureprojectschemawithagreeduponrequirementslistspoints | Sub-task | 3_1-Create_Projects_[TEST]
Add/Changeaccountingsupplier/customerparty | Sub-task | 3_1-Create_Projects_[TEST]
Add/Changecompanynamevalidation | Sub-task | 3_1-Create_Projects_[TEST]
Add/checkvatidvalidation | Sub-task | 3_1-Create_Projects_[TEST]
Check/changeduplicatesourcedatapoint | Sub-task | 3_1-Create_Projects_[TEST]
(Optional)Addtranslationdatapointsifrequired | Sub-task | 3_1-Create_Projects_[TEST]
3_2-Configure_Projects_[TEST] | Task | 3.StudioConfiguration | 3_2-Configure_Projects_[TEST] | 4_1-Testing_Set-up |  | 1
CreateaCOEtickettoconfigureReroutingrules | Sub-task | 3_2-Configure_Projects_[TEST] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
ContactIMforcompositeenrichmentset-upconfiguration | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtocreateandconfigureLLMpromptingservice | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoenablenewlycreated[TEST]outboundprojectsforduplicatecheckpipeline(ConnectprojectstoIMPpipeline) | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoaddoutboundprojectstoXMLUBL2.1endpoint[TEST] | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoenabletranslationforoutboundprojects | Sub-task | 3_2-Configure_Projects_[TEST]
4.Testing | Epic | Roll-outWilhelmsen
4_1-Testing_Set-up | Task | 4.Testing | 4_1-Testing_Set-up | 4_2-Functional_Testing_by_HY |  | 1
CopyandupdateTestWorkbookfornewphaseifneeded | Sub-task | 4_1-Testing_Set-up |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
4_2-Functional_Testing_by_HY | Task | 4.Testing | 4_2-Functional_Testing_by_HY | 4_3-Testing_by_Wilhelmsen |  | 1
Compareprojectset-upwithrequirementslistforspecificcountry | Sub-task | 4_2-Functional_Testing_by_HY |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
UploaddocumentstoGatewayprojectandtestrouting | Sub-task | 4_2-Functional_Testing_by_HY
Testadvancedduplicatetesting | Sub-task | 4_2-Functional_Testing_by_HY
Testifenrichmentisworkingproperlywithcompanycodefilter | Sub-task | 4_2-Functional_Testing_by_HY
TestifXMLendpointifavailableforoutboundprojects(Postman) | Sub-task | 4_2-Functional_Testing_by_HY
[Optional]Testtranslationfeature | Sub-task | 4_2-Functional_Testing_by_HY
4_3-Testing_by_Wilhelmsen | Task | 4.Testing | 4_3-Testing_by_Wilhelmsen | 5_1-Create_Projects_[PROD] |  | 3
AddprojectstoRequirementsList | Sub-task | 4_3-Testing_by_Wilhelmsen
ShareTestWorkbook | Sub-task | 4_3-Testing_by_Wilhelmsen |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Wilhelmsentoconfigureintegration&performSystemIntegrationTesting(SIT) | Sub-task | 4_3-Testing_by_Wilhelmsen
WilhelmsentoperformFunctionalTesting | Sub-task | 4_3-Testing_by_Wilhelmsen
WilhelmsentoperformUserAcceptanceTesting(UAT) | Sub-task | 4_3-Testing_by_Wilhelmsen
TestingSupportTasks(IssueResolution) | Sub-task | 4_3-Testing_by_Wilhelmsen
Analysis&FinalizationofTests | Sub-task | 4_3-Testing_by_Wilhelmsen
5.DeploymenttoProduction | Epic | Roll-outWilhelmsen
5_1-Create_Projects_[PROD] | Task | 5.DeploymenttoProduction | 5_1-Create_Projects_[PROD] | 5_2-Configure_Projects_[PROD] |  | 1
Configureprojectschemawithagreeduponrequirementslistspoints | Sub-task | 5_1-Create_Projects_[PROD]
Checkaccountingsupplier/customerparty | Sub-task | 5_1-Create_Projects_[PROD]
Checkcompanynamevalidation | Sub-task | 5_1-Create_Projects_[PROD]
CheckVatIdvalidation | Sub-task | 5_1-Create_Projects_[PROD]
Checkduplicatesourcedatapoint | Sub-task | 5_1-Create_Projects_[PROD]
(Optional)Checktranslationdatapointsifrequired | Sub-task | 5_1-Create_Projects_[PROD]
5_2-Configure_Projects_[PROD] | Task | 5.DeploymenttoProduction | 5_2-Configure_Projects_[PROD] | 5_3-Smoke_test |  | 1
CreateaCOEtickettoconfigureReroutingrules | Sub-task | 5_2-Configure_Projects_[PROD] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
ContactIMforcompositeenrichmentset-upconfiguration | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtocreateandconfigureLLMpromptingservice | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoenablenewlycreated[PROD]outboundprojectsforduplicatecheckpipeline(ConnectprojectstoIMPpipeline) | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoaddoutboundprojectstoXMLUBL2.1endpoint[PROD] | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoenabletranslationforoutboundprojects | Sub-task | 5_2-Configure_Projects_[PROD]
5_3-Smoke_test | Task | 5.DeploymenttoProduction | 5_3-Smoke_test | 5_4-Cutover_and_Go_Live |  | 1
Compareprojectset-upwith[TEST]project | Sub-task | 5_3-Smoke_test
UploaddocumentstoGatewayprojectandtestrouting | Sub-task | 5_3-Smoke_test
Testadvancedduplicatetesting | Sub-task | 5_3-Smoke_test
Testifenrichmentisworkingproperlywithcompanycodefilter | Sub-task | 5_3-Smoke_test
TestifXMLendpointifavailableforoutboundprojects(Postman) | Sub-task | 5_3-Smoke_test
[Optional]Testtranslationfeature | Sub-task | 5_3-Smoke_test
5_4-Cutover_and_Go_Live | Task | 5.DeploymenttoProduction | 5_4-Cutover_and_Go_Live | 6_1-Hypercare_Issues |  | 1
CreateandsharecutoverPlan | Sub-task | 5_4-Cutover_and_Go_Live |  |  | Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7
AddprojectstoRequirementsList | Sub-task | 5_4-Cutover_and_Go_Live |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
InformcustomerforProductionReadiness&initiateProductiondeployment | Sub-task | 5_4-Cutover_and_Go_Live
6.HypercarePhase | Epic | Roll-outWilhelmsen
6_1-Hypercare_Issues | Task | 6.HypercarePhase | 6_1-Hypercare_Issues | 6_2-Handover_to_Hypatos_Customer_Care |  | 5
CreateandshareHypercareIssueLog | Sub-task | 6_1-Hypercare_Issues |  |  | Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk
Hypercareissueresolutions | Sub-task | 6_1-Hypercare_Issues
6_2-Handover_to_Hypatos_Customer_Care | Task | 6.HypercarePhase | 6_2-Handover_to_Hypatos_Customer_Care | 7_1-Update_initial_design_sign-off_if_needed,7_2-Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint |  | 1
UpdateCCHandoverPage | Sub-task | 6_2-Handover_to_Hypatos_Customer_Care
7.DocumentationUpdate | Epic | Roll-outWilhelmsen
7_1-Update_initial_design_sign-off_if_needed | Task | 7.DocumentationUpdate |  |  |  | 1
7_2-Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint | Task | 7.DocumentationUpdate |  |  |  | 1

## Sheet1
Description
File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E
Task to log general internal meetings
Analyze posting data and determine top suppliers (>90% coverage)
Check if all top suppliers has sample documents with specified naming convention
Request if any top supplier document is missing
Prepare training, annotation documents
Match selected documents with posting data
EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y
Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data
Take the example from [ML] Project - [OC Entities][Phase 3] Oman
https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Take the example from [ML] Project - NZ_Annotation
Take the example from[ML] Project - [Training][PROD][NZ]
Take the example from [ML] Project - [QA] NZ
Example task : https://hypatos.atlassian.net/browse/WHL-825
Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Example task : https://hypatos.atlassian.net/browse/WHL-825
Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7
Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk