## Gantt
| 2024-07-10 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-10-31 | 2024-07-31 | 2024-08-15 | 2024-07-01
User Training | 2024-07-01 | 2024-09-04 | 2024-09-04
Project Management | 2024-07-01 | 2024-09-21
Assessment (Requirement + Data Gathering) | 2024-07-01 | 2024-07-20 | 2024-07-20
Design (Technical+Functional) | 2024-07-20 | 2024-07-30 | 2024-07-30
Machine Learning ( Model training + Optimization) | 2024-07-30 | 2024-08-14
Application Implement (Studio Config.) | 2024-07-30 | 2024-08-14
Integration Implementation | 2024-07-30 | 2024-08-14
Testing (FT & SIT & UAT) | 2024-08-14 | 2024-08-30 | 2024-08-30
Delivery (GoLive & Hypercare) | 2024-09-04 | 2024-09-21 | 2024-09-21
Wave 1,2,n (CompCode xx-xx) | 2024-09-21 | 2024-10-21
| Start | End | Milestone (activity level) | Milestone (activity level)
Only edit in yellow cells
| Today: | 2024-10-31
(1st row = milestone dates) Workshops |  |  | Comment
I1 | KickOff | 2024-07-01 | = start date Project management'
B1 | Assessment Workshop | 2024-07-10
C1 | Functional Workshop | 2024-07-15
D1 | Technical Workshop | 2024-07-20
E1 | SteerCo 1 | 2024-07-16 | = kickoff + 15d'
G1 | SteerCo 2 | 2024-07-31 | =1,steerco +15d'
H1 | SteerCo 3 | 2024-08-15 | = start date Project management'
| StartDate | EndData | Comment | Milestone | Date | Milestone | Date
User Training | 2024-07-01 | 2024-09-04 |  | Usertraining_completed | Enddate Usertraining
Project Management | 2024-07-01 | 2024-09-21 | Enddate= EnddateDelivery
Assessment (Requirement + Data Gathering) | 2024-07-01 | 2024-07-20 |  | Training Data Confirmation | Enddate Assessment (Requirement + Data Gathering)
Design (Technical+Functional) | 2024-07-20 | 2024-07-30 |  | SoW and Solution Design Sign-off | EndDate Design (Technical+Functional)
Machine Learning ( Model training + Optimization) | 2024-07-30 | 2024-08-14
Application Implement (Studio Config.) | 2024-07-30 | 2024-08-14
Integration Implementation | 2024-07-30 | 2024-08-14
Testing (FT & SIT & UAT) | 2024-08-14 | 2024-08-30 |  | MileStone_UAT approved_Go Live decision | EndDate Testing (FT & SIT & UAT)
Delivery (GoLive & Hypercare) | 2024-09-04 | 2024-09-21 |  | MileStone_Go Live | StartDate Delivery (GoLive & Hypercare) | MileStone_Hypercare Closing_Handover to Customer Care | Enddate Delivery (GoLive & Hypercare)
Wave 1,2,n (CompCode xx – xx) | 2024-09-21 | 2024-10-21
Wave Startdate = Enddate Delivery
Wave Enddate = Startdate Wave +30
Formulas:
End = [End, row above]+15
End = [Start]+30
Start = [End, row above]