## Gantt
| 2024-07-10 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-08 | 2024-07-31 | 2024-08-15 | 2024-07-01
User Training | 2024-07-01 | 2024-09-04 | 2024-09-04
Project Management | 2024-07-01 | 2024-09-07
Assessment (Requirement + Data Gathering) | 2024-07-01 | 2024-07-20 | 2024-07-20
Design (Technical+Functional) | 2024-07-20 | 2024-07-30 | 2024-07-30
Machine Learning ( Model training + Optimization) | 2024-07-30 | 2024-08-14
Application Implement (Studio Config.) | 2024-07-30 | 2024-08-14
Testing (FT & UAT) | 2024-08-14 | 2024-08-30 | 2024-08-30
Delivery (Presentation) | 2024-09-04 | 2024-09-07 | 2024-09-07
Pilot Project | 2024-09-07 | 2024-11-06
| Start | End | Milestone (activity level) | Milestone (activity level)
Only edit in yellow cells
| Today: | 2024-07-08
(1st row = milestone dates) Workshops |  |  | Comment
I1 | KickOff | 2024-07-01 | = start date Project management'
B1 | Assessment Workshop | 2024-07-10 | should be updated in the Jira project
C1 | Functional Workshop | 2024-07-15 | should be updated in the Jira project
D1 | Technical Workshop | 2024-07-20 | should be updated in the Jira project
E1 | SteerCo 1 | 2024-07-16 | = kickoff + 15d'
G1 | SteerCo 2 | 2024-07-31 | =1,steerco +15d'
H1 | SteerCo 3 | 2024-08-15 | = start date Project management'
| StartDate | EndData | Comment | Dates of Milestone are bind to Phases | Date | Dates of Milestone are bind to Phases | Date
User Training | 2024-07-01 | 2024-09-04 |  | Usertraining_completed | Enddate Usertraining
Project Management | 2024-07-01 | 2024-09-07 | Enddate= EnddateDelivery
Assessment (Requirement + Data Gathering) | 2024-07-01 | 2024-07-20 |  | Training Data Confirmation | Enddate Assessment (Requirement + Data Gathering)
Design (Technical+Functional) | 2024-07-20 | 2024-07-30 |  | SoW and Solution Design Sign-off | EndDate Design (Technical+Functional)
Machine Learning ( Model training + Optimization) | 2024-07-30 | 2024-08-14
Application Implement (Studio Config.) | 2024-07-30 | 2024-08-14
Testing (FT & SIT & UAT) | 2024-08-14 | 2024-08-30 |  | MileStone_UAT approved | EndDate Testing (FT & UAT)
Delivery (Presentation) | 2024-09-04 | 2024-09-07 |  | MileStone_Result_Presentation | StartDate Delivery (Presentation)
Pilot Project | 2024-09-07 | 2024-11-06
Pilot Startdate = Enddate Delivery
Pilot Enddate = Startdate Pilot +45
Formulas:
End = [End, row above]+15
End = [Start]+60
Start = [End, row above]