## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Roll-outWilhelmsen | Project
0.ProjectManagement | Epic | Roll-outWilhelmsen
0_1-Update_all_related_dates_in_this_project | Task | 0.ProjectManagement |  |  |  | 1
0_2-Update_roll-out_plan | Task | 0.ProjectManagement |  |  | File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E | 1
0_3-Internal_meetings | Task | 0.ProjectManagement |  |  | Task to log general internal meetings | 10
1.ProcessDiscovery | Epic | Roll-outWilhelmsen
1_1-Data_Acquisition | Task | 1.ProcessDiscovery |  |  |  | 3
Training&PostingDataRequest | Sub-task | 1_1-Data_Acquisition
PostingDataAnalysis | Sub-task | 1_1-Data_Acquisition |  |  | Analyze posting data and determine top suppliers (>90% coverage)
TrainingDataAssessment | Sub-task | 1_1-Data_Acquisition |  |  | Check if all top suppliers has sample documents with specified naming convention
Requestadditionaldocumentsifrequired | Sub-task | 1_1-Data_Acquisition |  |  | Request if any top supplier document is missing
TrainingData/DocumentSetPreparation | Sub-task | 1_1-Data_Acquisition |  |  | Prepare training, annotation documents
Matchtrainingdocumentswithpostingdata | Sub-task | 1_1-Data_Acquisition |  |  | Match selected documents with posting data
1_2-Requirement_Gathering | Task | 1.ProcessDiscovery |  |  |  | 3
ProvideDigitalizationDetailsformtoLocalFinanceTeamandaskexamplesforEdgecases | Sub-task | 1_2-Requirement_Gathering |  |  | EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y
ProvideAssessmentGatheringandTrainingDataFolders | Sub-task | 1_2-Requirement_Gathering |  |  | Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data
[ML]DemoProjectCreationforRequirementsGatheringMeeting | Sub-task | 1_2-Requirement_Gathering |  |  | Take the example from [ML] Project - [OC Entities][Phase 3] Oman
RequirementGatheringMeeting | Sub-task | 1_2-Requirement_Gathering
RequestexamplesforEdgecases | Sub-task | 1_2-Requirement_Gathering
Completefullset-upoftrainingdataforallofthetopsupplierswithEdgecasessharedduringrequirementssession | Sub-task | 1_2-Requirement_Gathering
UpdateWHLRequirementList | Sub-task | 1_2-Requirement_Gathering |  |  | https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
RequirementGatheringFinalization | Sub-task | 1_2-Requirement_Gathering
2.ModelTraining | Epic | Roll-outWilhelmsen
2_1-Capturing_Model_Training | Task | 2.ModelTraining |  |  |  | 3
Createbaseline(groundtruth)projecttoannotate[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from [ML] Project - NZ_Annotation
Uploaddocumentsselectedforannotationtogroundtruthproject(TopsuppliersandEdgecases) | Sub-task | 2_1-Capturing_Model_Training
Createataskforannotation(adddetailsperrequirements) | Sub-task | 2_1-Capturing_Model_Training
Validateannotationresultswithpostingdata | Sub-task | 2_1-Capturing_Model_Training
Improveannotationqualitybasedonvalidationwithpostingdata | Sub-task | 2_1-Capturing_Model_Training
CreateTrainingProject[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from[ML] Project - [Training][PROD][NZ]
UploadselectedtrainingdocumentsfrombaselineprojecttoTrainingProject[ML] | Sub-task | 2_1-Capturing_Model_Training
CreateQAProject[ML] | Sub-task | 2_1-Capturing_Model_Training |  |  | Take the example from [ML] Project - [QA] NZ
ConfigureQAprojectwithCompositeEnrichmentIndex | Sub-task | 2_1-Capturing_Model_Training
CreateLLMPromptingService[ML] | Sub-task | 2_1-Capturing_Model_Training
Uploadbaseline(groundtruth)documentstoQAProject[ML] | Sub-task | 2_1-Capturing_Model_Training
CreateErrorAnalysisDashboard | Sub-task | 2_1-Capturing_Model_Training
AnalyzeQAresultsandaccuracy | Sub-task | 2_1-Capturing_Model_Training
2_2-Enrichment_Model_Training | Task | 2.ModelTraining |  |  |  | 1
CreateIMPtrainingproject[TEST] | Sub-task | 2_2-Enrichment_Model_Training
ContactwithIMtoenableIMPpipeline | Sub-task | 2_2-Enrichment_Model_Training
UploaddocumentstoIMPtrainingproject | Sub-task | 2_2-Enrichment_Model_Training
TrainsuppliersusingdocumentsuploadedtoIMPproject | Sub-task | 2_2-Enrichment_Model_Training
2_3-Model_Fine_Tuning | Task | 2.ModelTraining |  |  |  | 1
Improve/OptimizeLLMPromptingServicepromptwithErrorAnalysisresults | Sub-task | 2_3-Model_Fine_Tuning
AddadditionalsupplierstoIMPprojectifrequired | Sub-task | 2_3-Model_Fine_Tuning
3.StudioConfiguration | Epic | Roll-outWilhelmsen
3_1-Create_Projects_[TEST] | Task | 3.StudioConfiguration |  |  |  | 1
Configureprojectschemawithagreeduponrequirementslistspoints | Sub-task | 3_1-Create_Projects_[TEST]
Add/Changeaccountingsupplier/customerparty | Sub-task | 3_1-Create_Projects_[TEST]
Add/Changecompanynamevalidation | Sub-task | 3_1-Create_Projects_[TEST]
Add/checkvatidvalidation | Sub-task | 3_1-Create_Projects_[TEST]
Check/changeduplicatesourcedatapoint | Sub-task | 3_1-Create_Projects_[TEST]
(Optional)Addtranslationdatapointsifrequired | Sub-task | 3_1-Create_Projects_[TEST]
3_2-Configure_Projects_[TEST] | Task | 3.StudioConfiguration |  |  |  | 1
CreateaCOEtickettoconfigureReroutingrules | Sub-task | 3_2-Configure_Projects_[TEST] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
ContactIMforcompositeenrichmentset-upconfiguration | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtocreateandconfigureLLMpromptingservice | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoenablenewlycreated[TEST]outboundprojectsforduplicatecheckpipeline(ConnectprojectstoIMPpipeline) | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoaddoutboundprojectstoXMLUBL2.1endpoint[TEST] | Sub-task | 3_2-Configure_Projects_[TEST]
ContactIMtoenabletranslationforoutboundprojects | Sub-task | 3_2-Configure_Projects_[TEST]
4.Testing | Epic | Roll-outWilhelmsen
4_1-Testing_Set-up | Task | 4.Testing |  |  |  | 1
CopyandupdateTestWorkbookfornewphaseifneeded | Sub-task | 4_1-Testing_Set-up |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
4_2-Functional_Testing_by_HY | Task | 4.Testing |  |  |  | 1
Compareprojectset-upwithrequirementslistforspecificcountry | Sub-task | 4_2-Functional_Testing_by_HY |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
UploaddocumentstoGatewayprojectandtestrouting | Sub-task | 4_2-Functional_Testing_by_HY
Testadvancedduplicatetesting | Sub-task | 4_2-Functional_Testing_by_HY
Testifenrichmentisworkingproperlywithcompanycodefilter | Sub-task | 4_2-Functional_Testing_by_HY
TestifXMLendpointifavailableforoutboundprojects(Postman) | Sub-task | 4_2-Functional_Testing_by_HY
[Optional]Testtranslationfeature | Sub-task | 4_2-Functional_Testing_by_HY
4_3-Testing_by_Wilhelmsen | Task | 4.Testing |  |  |  | 3
AddprojectstoRequirementsList | Sub-task | 4_3-Testing_by_Wilhelmsen
ShareTestWorkbook | Sub-task | 4_3-Testing_by_Wilhelmsen |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Wilhelmsentoconfigureintegration&performSystemIntegrationTesting(SIT) | Sub-task | 4_3-Testing_by_Wilhelmsen
WilhelmsentoperformFunctionalTesting | Sub-task | 4_3-Testing_by_Wilhelmsen
WilhelmsentoperformUserAcceptanceTesting(UAT) | Sub-task | 4_3-Testing_by_Wilhelmsen
TestingSupportTasks(IssueResolution) | Sub-task | 4_3-Testing_by_Wilhelmsen
Analysis&FinalizationofTests | Sub-task | 4_3-Testing_by_Wilhelmsen
5.DeploymenttoProduction | Epic | Roll-outWilhelmsen
5_1-Create_Projects_[PROD] | Task | 5.DeploymenttoProduction |  |  |  | 1
Configureprojectschemawithagreeduponrequirementslistspoints | Sub-task | 5_1-Create_Projects_[PROD]
Checkaccountingsupplier/customerparty | Sub-task | 5_1-Create_Projects_[PROD]
Checkcompanynamevalidation | Sub-task | 5_1-Create_Projects_[PROD]
CheckVatIdvalidation | Sub-task | 5_1-Create_Projects_[PROD]
Checkduplicatesourcedatapoint | Sub-task | 5_1-Create_Projects_[PROD]
(Optional)Checktranslationdatapointsifrequired | Sub-task | 5_1-Create_Projects_[PROD]
5_2-Configure_Projects_[PROD] | Task | 5.DeploymenttoProduction |  |  |  | 1
CreateaCOEtickettoconfigureReroutingrules | Sub-task | 5_2-Configure_Projects_[PROD] |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
ContactIMforcompositeenrichmentset-upconfiguration | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtocreateandconfigureLLMpromptingservice | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoenablenewlycreated[PROD]outboundprojectsforduplicatecheckpipeline(ConnectprojectstoIMPpipeline) | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoaddoutboundprojectstoXMLUBL2.1endpoint[PROD] | Sub-task | 5_2-Configure_Projects_[PROD]
ContactIMtoenabletranslationforoutboundprojects | Sub-task | 5_2-Configure_Projects_[PROD]
5_3-Smoke_test | Task | 5.DeploymenttoProduction |  |  |  | 1
Compareprojectset-upwith[TEST]project | Sub-task | 5_3-Smoke_test
UploaddocumentstoGatewayprojectandtestrouting | Sub-task | 5_3-Smoke_test
Testadvancedduplicatetesting | Sub-task | 5_3-Smoke_test
Testifenrichmentisworkingproperlywithcompanycodefilter | Sub-task | 5_3-Smoke_test
TestifXMLendpointifavailableforoutboundprojects(Postman) | Sub-task | 5_3-Smoke_test
[Optional]Testtranslationfeature | Sub-task | 5_3-Smoke_test
5_4-Cutover_and_Go_Live | Task | 5.DeploymenttoProduction |  |  |  | 1
CreateandsharecutoverPlan | Sub-task | 5_4-Cutover_and_Go_Live |  |  | Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7
AddprojectstoRequirementsList | Sub-task | 5_4-Cutover_and_Go_Live |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
InformcustomerforProductionReadiness&initiateProductiondeployment | Sub-task | 5_4-Cutover_and_Go_Live
6.HypercarePhase | Epic | Roll-outWilhelmsen
6_1-Hypercare_Issues | Task | 6.HypercarePhase |  |  |  | 5
CreateandshareHypercareIssueLog | Sub-task | 6_1-Hypercare_Issues |  |  | Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk
Hypercareissueresolutions | Sub-task | 6_1-Hypercare_Issues
6_2-Handover_to_Hypatos_Customer_Care | Task | 6.HypercarePhase |  |  |  | 1
UpdateCCHandoverPage | Sub-task | 6_2-Handover_to_Hypatos_Customer_Care
7.DocumentationUpdate | Epic | Roll-outWilhelmsen
7_1-Update_initial_design_sign-off_if_needed | Task | 7.DocumentationUpdate |  |  |  | 1
7_2-Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint | Task | 7.DocumentationUpdate |  |  |  | 1

## test
SummaryName | Blocks
1_1-Data_Acquisition | 1_2-Requirement_Gathering
1_2-Requirement_Gathering | 2_1-Capturing_Model_Training,2_2-Enrichment_Model_Training
2_1-Capturing_Model_Training | 2_3-Model_Fine_Tuning
2_2-Enrichment_Model_Training | 2_3-Model_Fine_Tuning
2_3-Model_Fine_Tuning | 3_1-Create_Projects_[TEST]
3_1-Create_Projects_[TEST] | 3_2-Configure_Projects_[TEST]
3_2-Configure_Projects_[TEST] | 4_1-Testing_Set-up
4_1-Testing_Set-up | 4_2-Functional_Testing_by_HY
4_2-Functional_Testing_by_HY | 4_3-Testing_by_Wilhelmsen
4_3-Testing_by_Wilhelmsen | 5_1-Create_Projects_[PROD]
5_1-Create_Projects_[PROD] | 5_2-Configure_Projects_[PROD]
5_2-Configure_Projects_[PROD] | 5_3-Smoke_test
5_3-Smoke_test | 5_4-Cutover_and_Go_Live
5_4-Cutover_and_Go_Live | 6_1-Hypercare_Issues
6_1-Hypercare_Issues | 6_2-Handover_to_Hypatos_Customer_Care
6_2-Handover_to_Hypatos_Customer_Care | 7_1-Update_initial_design_sign-off_if_needed,7_2-Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint