## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-7102 | Lessons learned | Task | Delivery | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-7101 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-04-19 | 2024-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-7100 | Hypercare_Phase | Task | Delivery | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-7099 | MileStone_Go Live | Task | Delivery | To Do | 2024-03-28 | 2024-03-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-7098 | Deployment | Task | Delivery | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-7097 | Delivery | Epic | Pilot | To Do | 2024-03-26 | 2024-04-21 |  | stephan.kuche |  | []
TD-7096 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-03-25 | 2024-03-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-7095 | User Acceptance Testing | Task | Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-7094 | MileStone_SIT approved | Task | Testing | To Do | 2024-03-03 | 2024-03-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-7093 | System Integration Test (E2E) | Task | Testing | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-7092 | Functional_Testing | Task | Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-7091 | Testing | Epic | Pilot | To Do | 2024-02-22 | 2024-03-26 |  | stephan.kuche |  | []
TD-7090 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7089 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7088 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7087 | Application Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-7086 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7085 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7084 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7083 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7082 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7081 | Integration Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-7080 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7079 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-7078 | Machine Learning | Epic | Pilot | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-7077 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-02-07 | 2024-02-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-7076 | Functional Design | Task | Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-7075 | Design | Epic | Pilot | To Do | 2024-01-24 | 2024-02-08 |  | stephan.kuche |  | []
TD-7074 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-01-23 | 2024-01-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-7073 | Requirement Analysis | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-7072 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-7071 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-24 |  | stephan.kuche |  | []
TD-7070 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-7069 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-7068 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-7067 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-7066 | User Training | Epic | Pilot | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-7065 | Pilot | Project |  | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []