## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-01-10 | R001 | Data Acquisition dependent on SAP addon release and installation - could break project timeline | High | A001 | KTM SAP DEV Team onboarding for integration implementation. KTM PM to raise ressource request to the respective team and actively following up. |  | Open
Open | 2024-01-10 | R002 | xSuite integration might take more ressources than expected | High | A002 | Discuss Solution Design extensively and support if needed |  | Open
 |  |  |  | High | A003 | Hypatos x KTM to revisit Integration and Project Timelines based on resource onboarding. Dependent on A001. Bi-Weekly follow ups. |  | Open
 |  |  |  | High | A004 | Allow a buffer for SIT |  | Open
Open | 2024-01-10 | R003 | PO Matching config and ML Training takes more ressources than expected | High | A005 | Schedule a session with HY SAP and Product Team to |  | Open
Open | 2024-01-10 | R004 | Poor PO Matching Enrichment Quality | Medium | A006 | Ensure that annoation of Line item is done right by providing annotation guideline |  | Open
Open | 2024-01-10 | R005 | Scope of Implementation not clear - customer expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-01-10 | R006 | Projekt Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in April 2024
Scope, Deliverables and Timeline
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
50
51
52
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Wave 1 (BUKRS xx – xx)
  KTM & HY
SIT
  KTM & HY
Wave 2 (BUKRS xx – xx)
  KTM & HY
Activities
  Responsible
System Integration implementation
  HY
Studio and Insights Configuration
Customer Care Support
Studio V2
Go/NoGo
Studio V1
  HY
ML model training and optimization
Testing Phase (SIT & UAT)
Model V2
Go-live & Continuous Improvement
Model V1
  KTM & HY
Assessment & Design of New AP Process
Hypercare
Tech Solution confirmed
  KTM
Providing of training data (images + posting data)
  KTM
Training data confirmed
  KTM & HY
User Onboarding & Training
Pilot Phase in Productive System
Kickoff 20.12.
Go-live Q&A
Leverage User Experience
User Onboarding
  KTM & HY
Project Management
Roll-out Go/NoGo
SOW Sign Off
Continuation decision
Go-live Data decision
UAT
Technical Workshop
SIT Approved
Functional Workshop
  KMT & HY
Assessment Workshop
Today 30.01.
Implementation Phase (2-3 months)
CW
  KTM & HY
Milestone
Project Deliverable
Meeting
SOW = Statement of Work SIT= System Integration Testing
UAT= User Acceptance Testing
Timeline subject to change – pending on Assessment, Functional & Technical Workshops outcomes
Deploy & Roll-out
Configure AI
Implementation & Validation
Design
PMO

## Slide 10: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 11: Thank you
Stephan Kuche
Sr. Implementation Manager
stephan.kuche@hypatos.ai
+49 179 340 36 49
hypatos.ai
Lucia Ferreiro Martinez
Sr. Customer Success Manager
lucia.ferreiro.martinez@hypatos.ai
+49 176 73573508
hypatos.ai
Dr. Ulrich Erxleben
Chief Executive Officer
uli.erxleben@hypatos.ai +49 157 736 362 22 hypatos.ai