## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-08-28 | R002 | Initial historical documents and data transfer is taking more time than expected | High | A001 | Escalate on KWS technical teams to resolve the issues Help team to enable integration | KWS/HY | Closed
Open | 2024-08-28 | R002 | xSuite integration might take more time than expected | High | A002 | Discuss Solution Design extensively and support if needed |  | Open
 |  |  |  | High | A003 | Hypatos x KWS to revisit Integration and Project Timelines based on resource onboarding. |  | Open
 |  |  |  | High | A004 | Allow a buffer for SIT |  | Open
Open | 2024-08-28 | R003 | PO Matching config and ML Training takes more resources than expected | High | A005 | Schedule a session with HY SAP and Product Team to expedite the process |  | Open
Open | 2024-08-28 | R004 | Poor PO Matching Enrichment Quality | Medium | A006 | Ensure that annotation of Line item is done right by providing annotation guideline |  | Open
Open | 2024-08-28 | R005 | Scope of Implementation not clear - customer expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-08-28 | R006 | Project Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: xSuite – Hypatos Solution Design
Master Data
Posting Data
PO Data
Attributes
Invoices
Archive
Hypatos cloud
Customer premise
1 https://studio-docs.hypatos.ai/user-guide/document-upload/email-service
2 https://hypatos.redoc.ly/#section/Introduction
3 https://studio-docs.hypatos.ai/integrations/sap-integration
xSuite: Create document
Extract
Enrich
Complete
Validate
Hypatos SAP Connector periodically collects master, PO and posting data (including archive images for initial model training) required for master data enrichment and attribute prediction in Hypatos Studio
Retrieved data is sent to Hypatos cloud via Hypatos REST API
Emailed and scanned invoices are inserted into Hypatos Studio for processing
Hypatos Studio extracts, enriches and completes the documents
Hypatos SAP Connector regularly triggers Hypatos REST API to fetch document data and invoice image from Hypatos Studio
Hypatos SAP Connector calls SAP BADI implementation passing in and mapping document data
BADI implementation calls xSuite function module for creation and archiving of invoice
KWS Matrix ticketing system calls HY API to get dunning letter/other documents information and images
1
3
4
5
6
7
5
BADI implementation
4
6
Hypatos REST API2
Email Inbox
Paper based invoices (scanned)
Email Service1
Emailed invoices
2
Document data and archive document
Hypatos SAP Connector3
1
2
3
7
8
Matrix
8

## Slide 10
Pilot High Level Project Plan
2024
Jul
Aug
Sep
Oct
Nov
Dec
System integration & technical in test system
Hy
IT
PMO + Tax & SME
Go-live decision
KWS/PWC & Hy
User training and UAT
KWS/PWC & Hy
Business & IT
Solution, integration design, SAP
connector installation
Productive pilot test phase
KWS/PWC & Hy
PMO
Pilot solution design approved
Hypercare
Hy
Activities
Responsible
Resources KWS/PWC
Business & IT
KWS/PWC & Hy
Project Management
Roll-out Decision
Prompt design and AI model training
Functional
Workshops
Hy
Technical
Workshop
Hypatos Studio & Insights configuration
Today
Requirements
Gathering
PMO + Tax & SME
Pilot
Kick-off
Hy & KWS/PWC
PMO
Pilot
Expansion
Roll-out

## Slide 11: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 12: Thank you
Yavuz Güney
Implementation Manager
yavuz.guney@hypatos.ai
+49 155 666 80146
hypatos.ai
Elena Kuhn
Customer Success Manager
elena.kuhn@hypatos.ai
hypatos.ai
Melinda Braun
Project Manager
melinda.braun@hypatos.ai
hypatos.ai