## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Pilot | Project
Project Management | Epic | Pilot
Project Set up | Task | Project Management | Project Set up | Data Acquisition |  | 5
Create StakeholderMapping and Matrix | Sub-task | Project Set up |  |  | PM Deliverable
Create Project Governance Structure | Sub-task | Project Set up |  |  | PM Deliverable
Create Customer Documentation | Sub-task | Project Set up |  |  | Included in Handover from Sales
Document Project (confl.) | Sub-task | Project Set up
Sharepoint folder set-up | Sub-task | Project Set up |  |  | Including all relevant Files
Create Absence Planner | Sub-task | Project Set up
Create Executive Report (based on template) | Sub-task | Project Set up |  |  | PM Deliverable
Create Weekly Report (based on template) | Sub-task | Project Set up |  |  | PM Deliverable
Teams Channel Setup | Sub-task | Project Set up
Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up
Teams Page Setup | Sub-task | Project Set up |  |  | Page with most relevant Links, StakeholderMapping and FAQ
Create JourFixe PMO and Steerco Series | Sub-task | Project Set up
Create Jira Work Mangagement Project | Sub-task | Project Set up
Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up
Create RAID Log | Sub-task | Project Set up |  |  | PM Deliverable
Create Project timeline | Sub-task | Project Set up
Create Jira Advanced roadmap | Sub-task | Project Set up |  |  | Optional
Create Project Plan | Sub-task | Project Set up
Identification of project deliverables | Sub-task | Project Set up
Create Kickoff Slidedeck | Sub-task | Project Set up
Create Assessment Workshop Slidedeck | Sub-task | Project Set up |  |  | PM Deliverable
Create Functional Workshop Slidedeck | Sub-task | Project Set up |  |  | PM Deliverable
Create Technical Workshop Slidedeck | Sub-task | Project Set up |  |  | PM Deliverable
Schedule Executive Status Meetings | Sub-task | Project Set up |  |  | PM Deliverable (monthly)
Schedule JourFixe Meeting | Sub-task | Project Set up |  |  | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting)
Schedule Workshops (Assessment WS) | Sub-task | Project Set up
Schedule Workshops (Functional WS) | Sub-task | Project Set up
Schedule Workshops (Technical WS) | Sub-task | Project Set up
MileStone_Kickoff Workshop | Task | Project Management |  |  |  | 1
Assessment | Epic | Pilot
Data Acquisition | Task | Assessment | Data Acquisition | MileStone_Training Data Confirmation |  | 19
Prepare and send out data and documentation request | Sub-task | Data Acquisition
Create Studio Company | Sub-task | Data Acquisition |  |  | [TEST and [ML]
Create apiv2 credentials | Sub-task | Data Acquisition
Share apiv2 credentials | Sub-task | Data Acquisition
Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition |  |  | (R3, S4Hana)
Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition
Send SAP Addon InstallationPackages | Sub-task | Data Acquisition |  |  | (Install andService Packages SP1)
Send SAP Addon Documentation | Sub-task | Data Acquisition
Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition |  |  | invite SAP Basis and HY SAP engineers
Install SAP Addon | Sub-task | Data Acquisition
Configure SAP Addon | Sub-task | Data Acquisition
Prepare Sample Dataset for ML Training | Sub-task | Data Acquisition |  |  | CUS Deliverable - create a list of top vendorids, or companycodes in scope
Get Posting Data inlc. Document Images via SAP Addon | Sub-task | Data Acquisition
Get Master Data via SAP Addon | Sub-task | Data Acquisition
Data and documentation quality and completeness review | Sub-task | Data Acquisition
MileStone_Training Data Confirmation | Task | Assessment | MileStone_Training Data Confirmation | Requirement Analysis |  | 1
Requirement Analysis | Task | Assessment | Requirement Analysis | Functional Design |  | 17
Posting data analysis | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template
Perform Master data analysis | Sub-task | Requirement Analysis |  |  | ERP master data
Perform PO data analysis | Sub-task | Requirement Analysis |  |  | ERP PO data
Perform Document analysis | Sub-task | Requirement Analysis |  |  | Documents (datapoints), Document types, document languages (regions) analysis
Create Document Processing Workflow | Sub-task | Requirement Analysis |  |  | Process documentation, Hypatos Studio Standard process template
Perform System analysis | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template
Prepare Assessement Workshop | Sub-task | Requirement Analysis |  |  | Update questions, Slidedeck
Perform Assessement Workshop | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis
Prepare Functional Workshop | Sub-task | Requirement Analysis
Perform Functional Workshop | Sub-task | Requirement Analysis |  |  | Requirement Gathering Deliverable
Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis |  |  | CUS Deliverable
Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis |  |  | CUS Deliverable
Prepare Technical Workshop | Sub-task | Requirement Analysis
Perform Technical Workshop | Sub-task | Requirement Analysis
Design | Epic | Pilot
Functional Design | Task | Design | Functional Design | MileStone_SoW and Solution Design Confirmation |  | 14
Create and populate Datapoint Template | Sub-task | Functional Design
Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design
Add Validation Rules to Datapoint Template | Sub-task | Functional Design
Add Derivation Rules to Datapoint Template | Sub-task | Functional Design
Create EndUSer Process design | Sub-task | Functional Design
List of users and roles (permissions) | Sub-task | Functional Design |  |  | CUS Deliverable - Customer to provide List of Users
Create Studio companies and projects concept design | Sub-task | Functional Design
Document Inbound Configuration Integration | Sub-task | Functional Design
Document Outbound Configuration Integration | Sub-task | Functional Design
Posting Data Inbound Integration Documentation | Sub-task | Functional Design
Create Technical Datapoint Mapping | Sub-task | Functional Design
Create Integration rules | Sub-task | Functional Design
ReportingandMonitoring Design | Sub-task | Functional Design
Document reporting and monitoring concept | Sub-task | Functional Design
Create SoW | Sub-task | Functional Design
Create Solution Design | Sub-task | Functional Design
MileStone_SoW and Solution Design Confirmation | Task | Design | MileStone_SoW and Solution Design Confirmation | Capturing Model Configuration,Enrichment_Model_Configuration,Document Inbound Configuration,Document Outbound Configuration,Posting_Data_Inbound_Configuration,PO_Data_Inbound_Configuration,Integration Rules Implementation,Reporting and Monitoring Configuration,Studio Configuration,Schema Configuration |  | 1
Machine Learning | Epic | Pilot
Capturing Model Configuration | Task | Machine Learning |  |  |  | 21
Create Baseline Project | Sub-task | Capturing Model Configuration
Upload Training Data | Sub-task | Capturing Model Configuration
Annotation of Documents | Sub-task | Capturing Model Configuration
Perform Capturing Model QA | Sub-task | Capturing Model Configuration
Perform Capturing Model Results Analysis | Sub-task | Capturing Model Configuration
Capturing Model Development | Sub-task | Capturing Model Configuration
Capturing Model Evaluation | Sub-task | Capturing Model Configuration
Enrichment_Model_Configuration | Task | Machine Learning |  |  |  | 14
Create EM Ticket | Sub-task | Enrichment_Model_Configuration
Train EModel | Sub-task | Enrichment_Model_Configuration
QA Emodel | Sub-task | Enrichment_Model_Configuration
Emodel Results analyis | Sub-task | Enrichment_Model_Configuration
Integration Implementation | Epic | Pilot
Document Inbound Configuration | Task | Integration Implementation |  |  |  | 3
Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration
Support API Configuration | Sub-task | Document Inbound Configuration
Document Outbound Configuration | Task | Integration Implementation |  |  |  | 2
API Configuration Support OB | Sub-task | Document Outbound Configuration
Posting_Data_Inbound_Configuration | Task | Integration Implementation |  |  |  | 2
API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration
PO_Data_Inbound_Configuration | Task | Integration Implementation |  |  |  | 2
API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration
Integration Rules Implementation | Task | Integration Implementation |  |  |  | 1
Middleware Configuration Support | Sub-task | Integration Rules Implementation
Application Implementation | Epic | Pilot
Reporting and Monitoring Configuration | Task | Application Implementation |  |  |  | 1
Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration |  |  | Insights Standard Collections for Reporting and Monitoring
Studio Configuration | Task | Application Implementation |  |  |  | 14
Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration
Creation of projects and assignment of users and models | Sub-task | Studio Configuration
Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration
Schema Configuration | Task | Application Implementation | Schema Configuration | Functional_Testing |  | 7
Create Composite Enrichment in Setup | Sub-task | Schema Configuration
Create Supplier Master Data Configuration | Sub-task | Schema Configuration
Create Company Master Data Configuration | Sub-task | Schema Configuration
Create PO Line Matching Configuration | Sub-task | Schema Configuration
Update list of datapoints | Sub-task | Schema Configuration
Configure normalisation rules | Sub-task | Schema Configuration
Configure validation rules | Sub-task | Schema Configuration
Configure derived datapoints | Sub-task | Schema Configuration
Configure ReRouting Rules | Sub-task | Schema Configuration
Testing | Epic | Pilot
Functional_Testing | Task | Testing | Functional_Testing | System Integration Test (E2E) |  | 3
Create testing plan workbook | Sub-task | Functional_Testing |  |  | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report
Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing
Hy to perform funct testing | Sub-task | Functional_Testing
CUS to perform funct. Testing | Sub-task | Functional_Testing
System Integration Test (E2E) | Task | Testing | System Integration Test (E2E) | MileStone_SIT approved |  | 7
Run Document Inbound load test | Sub-task | System Integration Test (E2E)
Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E)
Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E)
Run Masterdata Test | Sub-task | System Integration Test (E2E)
Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E)
Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E)
Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E)
MileStone_SIT approved | Task | Testing | MileStone_SIT approved | User Acceptance Testing |  | 1
User Acceptance Testing | Task | Testing | User Acceptance Testing | MileStone_UAT approved_Go Live decision |  | 21
Run Model UAT | Sub-task | User Acceptance Testing
Run Studio UAT | Sub-task | User Acceptance Testing
MileStone_UAT approved_Go Live decision | Task | Testing | MileStone_UAT approved_Go Live decision | Deployment |  | 1
User Training | Epic | Pilot
User Onboarding | Task | User Training |  |  |  | 120
Request UserList | Sub-task | User Onboarding
Provide UserList | Sub-task | User Onboarding
Grant Access to HY Academy | Sub-task | User Onboarding
Finish HY Academy Training | Sub-task | User Onboarding
Intro HY continual learning tech and QandA session | Sub-task | User Onboarding |  |  | recommendations to improve model performance
Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding
Key User Admin Training and QandA | Sub-task | User Onboarding
Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding
Delivery | Epic | Pilot
Deployment | Task | Delivery | Deployment | MileStone_Go Live |  | 2
Configure reporting notifications audience and cadence | Sub-task | Deployment
Create and share the Cutover plan | Sub-task | Deployment
Cutover and Go Live | Sub-task | Deployment
Introduction Session to Hypercare Process | Sub-task | Deployment
MileStone_Go Live | Task | Delivery | MileStone_Go Live | Hypercare_Phase |  | 1
Hypercare_Phase | Task | Delivery | Hypercare_Phase | MileStone_Hypercare Closing_Handover to Customer Care |  | 21
Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase
Create Handover to CC page | Sub-task | Hypercare_Phase
MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | MileStone_Hypercare Closing_Handover to Customer Care | Lessons learned |  | 1
Lessons learned | Task | Delivery |  |  |  | 1
Create lessons learned page | Sub-task | Lessons learned