## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-3546 | Lessons learned | Task | Delivery | To Do | 2025-01-31 | 2025-02-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-3545 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2025-01-30 | 2025-01-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-3544 | Hypercare_Phase | Task | Delivery | To Do | 2025-01-09 | 2025-01-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-3543 | MileStone_Go Live | Task | Delivery | To Do | 2025-01-08 | 2025-01-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-3542 | Deployment | Task | Delivery | To Do | 2025-01-06 | 2025-01-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-3541 | Delivery | Epic | Pilot | To Do | 2025-01-06 | 2025-02-01 |  | stephan.kuche |  | []
TD-3540 | User Onboarding | Task | User Training | To Do | 2024-10-01 | 2025-01-29 |  | stephan.kuche |  | []
TD-3539 | User Training | Epic | Pilot | To Do | 2024-10-01 | 2025-01-29 |  | stephan.kuche |  | []
TD-3538 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2025-01-05 | 2025-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-3537 | User Acceptance Testing | Task | Testing | To Do | 2024-12-15 | 2025-01-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-3536 | MileStone_SIT approved | Task | Testing | To Do | 2024-12-14 | 2024-12-15 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-3535 | System Integration Test (E2E) | Task | Testing | To Do | 2024-12-07 | 2024-12-14 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-3534 | Functional_Testing | Task | Testing | To Do | 2024-12-04 | 2024-12-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-3533 | Testing | Epic | Pilot | To Do | 2024-12-04 | 2025-01-06 |  | stephan.kuche |  | []
TD-3532 | Schema Configuration | Task | Application Implementation | To Do | 2024-11-27 | 2024-12-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3531 | Studio Configuration | Task | Application Implementation | To Do | 2024-11-27 | 2024-12-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3530 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-11-27 | 2024-11-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3529 | Application Implementation | Epic | Pilot | To Do | 2024-11-27 | 2024-12-11 |  | stephan.kuche |  | []
TD-3528 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-11-27 | 2024-11-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3527 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-11-27 | 2024-11-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3526 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-11-27 | 2024-11-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3525 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-11-27 | 2024-11-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3524 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-11-27 | 2024-11-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3523 | Integration Implementation | Epic | Pilot | To Do | 2024-11-27 | 2024-11-30 |  | stephan.kuche |  | []
TD-3522 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-11-27 | 2024-12-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3521 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-11-27 | 2024-12-18 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3520 | Machine Learning | Epic | Pilot | To Do | 2024-11-27 | 2024-12-18 |  | stephan.kuche |  | []
TD-3519 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-11-26 | 2024-11-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-3518 | Functional Design | Task | Design | To Do | 2024-11-12 | 2024-11-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-3517 | Design | Epic | Pilot | To Do | 2024-11-12 | 2024-11-27 |  | stephan.kuche |  | []
TD-3516 | Requirement Analysis | Task | Assessment | To Do | 2024-10-26 | 2024-11-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-3515 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-10-25 | 2024-10-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3514 | Data Acquisition | Task | Assessment | To Do | 2024-10-06 | 2024-10-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3513 | Assessment | Epic | Pilot | To Do | 2024-10-06 | 2024-11-12 |  | stephan.kuche |  | []
TD-3512 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-10-01 | 2024-10-02 |  | stephan.kuche |  | []
TD-3511 | Project Set up | Task | Project Management | To Do | 2024-10-01 | 2024-10-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3510 | Project Management | Epic | Pilot | To Do | 2024-10-01 | 2024-10-06 |  | stephan.kuche |  | []
TD-3509 | Pilot | Project |  | To Do | 2024-10-01 | 2024-10-01 |  | stephan.kuche |  | []
TD-3508 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-08-31 | 2024-09-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-3507 | Lessons learned | Task | Delivery | To Do | 2024-08-31 | 2024-09-01 |  | stephan.kuche |  | []
TD-3506 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-08-30 | 2024-08-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-3505 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-08-09 | 2024-08-30 |  | stephan.kuche |  | []
TD-3504 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-08-09 | 2024-08-30 |  | stephan.kuche |  | []
TD-3503 | Hypercare_Phase | Task | Delivery | To Do | 2024-08-09 | 2024-08-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-3502 | MileStone_Go Live | Task | Delivery | To Do | 2024-08-08 | 2024-08-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-3501 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-08-06 | 2024-08-08 |  | stephan.kuche |  | []
TD-3500 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-08-06 | 2024-08-08 |  | stephan.kuche |  | []
TD-3499 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-08-06 | 2024-08-08 |  | stephan.kuche |  | []
TD-3498 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-08-06 | 2024-08-08 |  | stephan.kuche |  | []
TD-3497 | Deployment | Task | Delivery | To Do | 2024-08-06 | 2024-08-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-3496 | Delivery | Epic | Pilot | To Do | 2024-08-06 | 2024-09-01 |  | stephan.kuche |  | []
TD-3495 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3494 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3493 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3492 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 | recommendations to improve model performance | stephan.kuche |  | []
TD-3491 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3490 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3489 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3488 | Request UserList | Sub-task | User Onboarding | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3487 | User Onboarding | Task | User Training | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3486 | User Training | Epic | Pilot | To Do | 2024-05-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-3485 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-08-05 | 2024-08-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-3484 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-07-15 | 2024-08-05 |  | stephan.kuche |  | []
TD-3483 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-07-15 | 2024-08-05 |  | stephan.kuche |  | []
TD-3482 | User Acceptance Testing | Task | Testing | To Do | 2024-07-15 | 2024-08-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-3481 | MileStone_SIT approved | Task | Testing | To Do | 2024-07-14 | 2024-07-15 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-3480 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | []
TD-3479 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | []
TD-3478 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | []
TD-3477 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | []
TD-3476 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3475 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3474 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | []
TD-3473 | System Integration Test (E2E) | Task | Testing | To Do | 2024-07-07 | 2024-07-14 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-3472 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-07-04 | 2024-07-07 |  | stephan.kuche |  | []
TD-3471 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-07-04 | 2024-07-07 |  | stephan.kuche |  | []
TD-3470 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-07-04 | 2024-07-07 |  | stephan.kuche |  | []
TD-3469 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-07-04 | 2024-07-07 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-3468 | Functional_Testing | Task | Testing | To Do | 2024-07-04 | 2024-07-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-3467 | Testing | Epic | Pilot | To Do | 2024-07-04 | 2024-08-06 |  | stephan.kuche |  | []
TD-3466 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3465 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3464 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3463 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3462 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3461 | Create PO Line Matching Configuration | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3460 | Create Company Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3459 | Create Supplier Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3458 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | []
TD-3457 | Schema Configuration | Task | Application Implementation | To Do | 2024-06-27 | 2024-07-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3456 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3455 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3454 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3453 | Studio Configuration | Task | Application Implementation | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3452 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-06-27 | 2024-06-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3451 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-06-27 | 2024-06-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3450 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-06-27 | 2024-06-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3449 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-06-27 | 2024-06-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3448 | Application Implementation | Epic | Pilot | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3447 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-06-27 | 2024-06-28 |  | stephan.kuche |  | []
TD-3446 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-06-27 | 2024-06-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3445 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | []
TD-3444 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3443 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | []
TD-3442 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | []
TD-3441 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | []
TD-3440 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-06-27 | 2024-06-29 |  | stephan.kuche |  | []
TD-3439 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-06-27 | 2024-06-30 |  | stephan.kuche |  | []
TD-3438 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-06-27 | 2024-06-30 |  | stephan.kuche |  | []
TD-3437 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-06-27 | 2024-06-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3436 | Integration Implementation | Epic | Pilot | To Do | 2024-06-27 | 2024-06-30 |  | stephan.kuche |  | []
TD-3435 | Emodel Results analyis | Sub-task | Enrichment_Model_Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3434 | QA Emodel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3433 | Train EModel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3432 | Create EM Ticket | Sub-task | Enrichment_Model_Configuration | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | []
TD-3431 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-06-27 | 2024-07-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3430 | Capturing Model Evaluation | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3429 | Capturing Model Development | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3428 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3427 | Perform Capturing Model QA | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3426 | Annotation of Documents | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3425 | Upload Training Data | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3424 | Create Baseline Project | Sub-task | Capturing Model Configuration | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3423 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3422 | Machine Learning | Epic | Pilot | To Do | 2024-06-27 | 2024-07-18 |  | stephan.kuche |  | []
TD-3421 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-06-26 | 2024-06-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-3420 | Create Solution Design | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3419 | Create SoW | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3418 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3417 | ReportingandMonitoring Design | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3416 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3415 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3414 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3413 | Document Outbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3412 | Document Inbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3411 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3410 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-3409 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3408 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3407 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3406 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3405 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | []
TD-3404 | Functional Design | Task | Design | To Do | 2024-06-12 | 2024-06-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-3403 | Design | Epic | Pilot | To Do | 2024-06-12 | 2024-06-27 |  | stephan.kuche |  | []
TD-3402 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 |  | stephan.kuche |  | []
TD-3401 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 |  | stephan.kuche |  | []
TD-3400 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | CUS Deliverable | stephan.kuche |  | []
TD-3399 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | CUS Deliverable | stephan.kuche |  | []
TD-3398 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-3397 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 |  | stephan.kuche |  | []
TD-3396 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3395 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Update questions, Slidedeck | stephan.kuche |  | []
TD-3394 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3393 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3392 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3391 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | ERP PO data | stephan.kuche |  | []
TD-3390 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | ERP master data | stephan.kuche |  | []
TD-3389 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-05-26 | 2024-06-12 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-3388 | Requirement Analysis | Task | Assessment | To Do | 2024-05-26 | 2024-06-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-3387 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-05-25 | 2024-05-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3386 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3385 | Get Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3384 | Get Posting Data inlc. Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3383 | Prepare Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 | CUS Deliverable - create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-3382 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3381 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3380 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-3379 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3378 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-3377 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3376 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 | (R3, S4Hana) | stephan.kuche |  | []
TD-3375 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3374 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3373 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 | [TEST and [ML] | stephan.kuche |  | []
TD-3372 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | []
TD-3371 | Data Acquisition | Task | Assessment | To Do | 2024-05-06 | 2024-05-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3370 | Assessment | Epic | Pilot | To Do | 2024-05-06 | 2024-06-12 |  | stephan.kuche |  | []
TD-3369 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-05-01 | 2024-05-02 |  | stephan.kuche |  | []
TD-3368 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3367 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3366 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3365 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-3364 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-3363 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3362 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3361 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3360 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3359 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3358 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3357 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | Optional | stephan.kuche |  | []
TD-3356 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3355 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3354 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3353 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3352 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3351 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-3350 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3349 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3348 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3347 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3346 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3345 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | Including all relevant Files | stephan.kuche |  | []
TD-3344 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3343 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-3342 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3341 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-05-01 | 2024-05-06 | PM Deliverable | stephan.kuche |  | []
TD-3340 | Project Set up | Task | Project Management | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3339 | Project Management | Epic | Pilot | To Do | 2024-05-01 | 2024-05-06 |  | stephan.kuche |  | []
TD-3338 | Pilot | Project |  | To Do | 2024-05-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-3337 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-05-02 | 2024-05-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-3336 | Lessons learned | Task | Delivery | To Do | 2024-05-02 | 2024-05-03 |  | stephan.kuche |  | []
TD-3335 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-05-01 | 2024-05-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-3334 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | []
TD-3333 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | []
TD-3332 | Hypercare_Phase | Task | Delivery | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-3331 | MileStone_Go Live | Task | Delivery | To Do | 2024-04-09 | 2024-04-10 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-3330 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3329 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3328 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3327 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3326 | Deployment | Task | Delivery | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-3325 | Delivery | Epic | Rollout | To Do | 2024-04-07 | 2024-05-03 |  | stephan.kuche |  | []
TD-3324 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3323 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3322 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3321 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 | recommendations to improve model performance | stephan.kuche |  | []
TD-3320 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3319 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3318 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3317 | Request UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3316 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3315 | User Training | Epic | Rollout | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-3314 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-04-06 | 2024-04-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-3313 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | []
TD-3312 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | []
TD-3311 | User Acceptance Testing | Task | Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-3310 | MileStone_SIT approved | Task | Testing | To Do | 2024-03-15 | 2024-03-16 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-3309 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3308 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3307 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3306 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3305 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3304 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3303 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3302 | System Integration Test (E2E) | Task | Testing | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-3301 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3300 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3299 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3298 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-3297 | Functional_Testing | Task | Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-3296 | Testing | Epic | Rollout | To Do | 2024-03-05 | 2024-04-07 |  | stephan.kuche |  | []
TD-3295 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3294 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3293 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3292 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3291 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3290 | Create PO Line Matching Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3289 | Create Company Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3288 | Create Supplier Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3287 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3286 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3285 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3284 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3283 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3282 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3281 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3280 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3279 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3278 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3277 | Application Implementation | Epic | Rollout | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3276 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | []
TD-3275 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3274 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3273 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3272 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3271 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3270 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3269 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3268 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3267 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3266 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3265 | Integration Implementation | Epic | Rollout | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3264 | Emodel Results analyis | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3263 | QA Emodel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3262 | Train EModel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3261 | Create EM Ticket | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3260 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3259 | Capturing Model Evaluation | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3258 | Capturing Model Development | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3257 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3256 | Perform Capturing Model QA | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3255 | Annotation of Documents | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3254 | Upload Training Data | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3253 | Create Baseline Project | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3252 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3251 | Machine Learning | Epic | Rollout | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3250 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-02-26 | 2024-02-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-3249 | Create Solution Design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3248 | Create SoW | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3247 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3246 | ReportingandMonitoring Design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3245 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3244 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3243 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3242 | Document Outbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3241 | Document Inbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3240 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3239 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-3238 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3237 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3236 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3235 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3234 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3233 | Functional Design | Task | Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-3232 | Design | Epic | Rollout | To Do | 2024-02-12 | 2024-02-27 |  | stephan.kuche |  | []
TD-3231 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3230 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3229 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | CUS Deliverable | stephan.kuche |  | []
TD-3228 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | CUS Deliverable | stephan.kuche |  | []
TD-3227 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-3226 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3225 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3224 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Update questions, Slidedeck | stephan.kuche |  | []
TD-3223 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3222 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3221 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3220 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | ERP PO data | stephan.kuche |  | []
TD-3219 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | ERP master data | stephan.kuche |  | []
TD-3218 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-3217 | Requirement Analysis | Task | Assessment | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-3216 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-01-25 | 2024-01-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3215 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3214 | Get Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3213 | Get Posting Data inlc. Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3212 | Prepare Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | CUS Deliverable - create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-3211 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3210 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3209 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-3208 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3207 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-3206 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3205 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (R3, S4Hana) | stephan.kuche |  | []
TD-3204 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3203 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3202 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | [TEST and [ML] | stephan.kuche |  | []
TD-3201 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3200 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3199 | Assessment | Epic | Rollout | To Do | 2024-01-06 | 2024-02-12 |  | stephan.kuche |  | []
TD-3198 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-3197 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3196 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3195 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3194 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-3193 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-3192 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3191 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3190 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3189 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3188 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3187 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3186 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Optional | stephan.kuche |  | []
TD-3185 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3184 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3183 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3182 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3181 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3180 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-3179 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3178 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3177 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3176 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3175 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3174 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-3173 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3172 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-3171 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3170 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3169 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3168 | Project Management | Epic | Rollout | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3167 | Rollout | Project |  | To Do | 2024-01-01 | 2024-01-01 |  | stephan.kuche |  | []
TD-3166 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-05-02 | 2024-05-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-3165 | Lessons learned | Task | Delivery | To Do | 2024-05-02 | 2024-05-03 |  | stephan.kuche |  | []
TD-3164 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-05-01 | 2024-05-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-3163 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | []
TD-3162 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | []
TD-3161 | Hypercare_Phase | Task | Delivery | To Do | 2024-04-10 | 2024-05-01 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-3160 | MileStone_Go Live | Task | Delivery | To Do | 2024-04-09 | 2024-04-10 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-3159 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3158 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3157 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3156 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | []
TD-3155 | Deployment | Task | Delivery | To Do | 2024-04-07 | 2024-04-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-3154 | Delivery | Epic | Rollout | To Do | 2024-04-07 | 2024-05-03 |  | stephan.kuche |  | []
TD-3153 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3152 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3151 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3150 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 | recommendations to improve model performance | stephan.kuche |  | []
TD-3149 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3148 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3147 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3146 | Request UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3145 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-3144 | User Training | Epic | Rollout | To Do | 2024-01-01 | 2024-05-03 |  | stephan.kuche |  | []
TD-3143 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-04-06 | 2024-04-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-3142 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | []
TD-3141 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | []
TD-3140 | User Acceptance Testing | Task | Testing | To Do | 2024-03-16 | 2024-04-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-3139 | MileStone_SIT approved | Task | Testing | To Do | 2024-03-15 | 2024-03-16 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-3138 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3137 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3136 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3135 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3134 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3133 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3132 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | []
TD-3131 | System Integration Test (E2E) | Task | Testing | To Do | 2024-03-08 | 2024-03-15 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-3130 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3129 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3128 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | []
TD-3127 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-03-05 | 2024-03-08 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-3126 | Functional_Testing | Task | Testing | To Do | 2024-03-05 | 2024-03-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-3125 | Testing | Epic | Rollout | To Do | 2024-03-05 | 2024-04-07 |  | stephan.kuche |  | []
TD-3124 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3123 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3122 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3121 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3120 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3119 | Create PO Line Matching Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3118 | Create Company Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3117 | Create Supplier Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3116 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | []
TD-3115 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-03-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3114 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3113 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3112 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3111 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3110 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3109 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3108 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-27 | 2024-02-28 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-3107 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3106 | Application Implementation | Epic | Rollout | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3105 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | []
TD-3104 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-28 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3103 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3102 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3101 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3100 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3099 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3098 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-02-29 |  | stephan.kuche |  | []
TD-3097 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3096 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3095 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3094 | Integration Implementation | Epic | Rollout | To Do | 2024-02-27 | 2024-03-01 |  | stephan.kuche |  | []
TD-3093 | Emodel Results analyis | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3092 | QA Emodel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3091 | Train EModel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3090 | Create EM Ticket | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | []
TD-3089 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-02-27 | 2024-03-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3088 | Capturing Model Evaluation | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3087 | Capturing Model Development | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3086 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3085 | Perform Capturing Model QA | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3084 | Annotation of Documents | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3083 | Upload Training Data | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3082 | Create Baseline Project | Sub-task | Capturing Model Configuration | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3081 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-3080 | Machine Learning | Epic | Rollout | To Do | 2024-02-27 | 2024-03-19 |  | stephan.kuche |  | []
TD-3079 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-02-26 | 2024-02-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-3078 | Create Solution Design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3077 | Create SoW | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3076 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3075 | ReportingandMonitoring Design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3074 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3073 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3072 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3071 | Document Outbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3070 | Document Inbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3069 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3068 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-3067 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3066 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3065 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3064 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3063 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | []
TD-3062 | Functional Design | Task | Design | To Do | 2024-02-12 | 2024-02-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-3061 | Design | Epic | Rollout | To Do | 2024-02-12 | 2024-02-27 |  | stephan.kuche |  | []
TD-3060 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3059 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3058 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | CUS Deliverable | stephan.kuche |  | []
TD-3057 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | CUS Deliverable | stephan.kuche |  | []
TD-3056 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-3055 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | []
TD-3054 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3053 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Update questions, Slidedeck | stephan.kuche |  | []
TD-3052 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3051 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-3050 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-3049 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | ERP PO data | stephan.kuche |  | []
TD-3048 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | ERP master data | stephan.kuche |  | []
TD-3047 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-26 | 2024-02-12 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-3046 | Requirement Analysis | Task | Assessment | To Do | 2024-01-26 | 2024-02-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-3045 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-01-25 | 2024-01-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-3044 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3043 | Get Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3042 | Get Posting Data inlc. Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3041 | Prepare Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | CUS Deliverable - create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-3040 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3039 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3038 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-3037 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3036 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-3035 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3034 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | (R3, S4Hana) | stephan.kuche |  | []
TD-3033 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3032 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3031 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 | [TEST and [ML] | stephan.kuche |  | []
TD-3030 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | []
TD-3029 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-3028 | Assessment | Epic | Rollout | To Do | 2024-01-06 | 2024-02-12 |  | stephan.kuche |  | []
TD-3027 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-3026 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3025 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3024 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3023 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-3022 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-3021 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3020 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3019 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3018 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3017 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3016 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3015 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Optional | stephan.kuche |  | []
TD-3014 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3013 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3012 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3011 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3010 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3009 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-3008 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3007 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3006 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3005 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-3004 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3003 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-3002 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-3001 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-3000 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-2999 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-2998 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-2997 | Project Management | Epic | Rollout | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-2996 | Rollout | Project |  | To Do | 2024-01-01 | 2024-01-01 |  | stephan.kuche |  | []