## Slide 1: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in {{YYYY MM}}
Timeline subject to change – Assuming that Machine Learning Trainingdata is available on time.
Project Milestone
Go Live
SteerCo Meeting
Workshop
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
01
02
03
04
05
06
07
08
09
10
11
12
13
Delivery (GoLive & Hypercare)
Ass. WS
Func.WS
CUS, HY
Tech.WS
Today
CUS, HY
Wave 1,2,n (CompCode xx-xx)
CUS, HY
Kickof WS
Activity
User Training Completed
CUS, HY
Testing (FT & SIT & UAT)
User Training
UAT approved & Go Live decision
CUS, HY
CUS, HY
Integration Implementation
Project Management
HY
Application Implement (Studio Config.)
CUS, HY
HY
Machine Learning ( Model training + Optimization)
Responsible
CUS, HY
Design (Technical+Functional)
Assessment (Requirement + Data Gathering)
SoW & Solution Design Sign-off
Training Data Confirm.
Hypercare Closing & Handover Cus. Care
Deploy & Roll-out
Implement & Test
Assess & Design
Initiate & Plan
SOW = Statement of Work FT= Functional Testing
SIT= System Integration Testing
UAT= User Acceptance Testing