## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Pilot | Project
User Training | Epic | Pilot
User Onboarding | Task | User Training |  |  |  | 120
Project Management | Epic | Pilot
Project Set up | Task | Project Management | Project Set up | Data Acquisition,Requirement Analysis |  | 5
MileStone_Kickoff Workshop | Task | Project Management |  |  |  | 1
Assessment | Epic | Pilot
Data Acquisition | Task | Assessment |  |  |  | 17
Requirement Analysis | Task | Assessment | Requirement Analysis | MileStone_Training Data Confirmation |  | 17
MileStone_Training Data Confirmation | Task | Assessment | MileStone_Training Data Confirmation | Functional Design |  | 1
Design | Epic | Pilot
Functional Design | Task | Design | Functional Design | MileStone_SoW and Solution Design Confirmation |  | 14
MileStone_SoW and Solution Design Confirmation | Task | Design | MileStone_SoW and Solution Design Confirmation | Capturing Model Configuration,Enrichment_Model_Configuration,Document Inbound Configuration,Document Outbound Configuration,Posting_Data_Inbound_Configuration,PO_Data_Inbound_Configuration,Integration Rules Implementation,Reporting and Monitoring Configuration,Studio Configuration,Schema Configuration |  | 1
Machine Learning | Epic | Pilot
Capturing Model Configuration | Task | Machine Learning |  |  |  | 21
Enrichment_Model_Configuration | Task | Machine Learning |  |  |  | 14
Integration Implementation | Epic | Pilot
Document Inbound Configuration | Task | Integration Implementation |  |  |  | 3
Document Outbound Configuration | Task | Integration Implementation |  |  |  | 2
Posting_Data_Inbound_Configuration | Task | Integration Implementation |  |  |  | 2
PO_Data_Inbound_Configuration | Task | Integration Implementation |  |  |  | 2
Integration Rules Implementation | Task | Integration Implementation |  |  |  | 1
Application Implementation | Epic | Pilot
Reporting and Monitoring Configuration | Task | Application Implementation |  |  |  | 1
Studio Configuration | Task | Application Implementation | Studio Configuration | Functional_Testing |  | 14
Schema Configuration | Task | Application Implementation |  |  |  | 7
Testing | Epic | Pilot
Functional_Testing | Task | Testing | Functional_Testing | System Integration Test (E2E) |  | 3
System Integration Test (E2E) | Task | Testing | System Integration Test (E2E) | MileStone_SIT approved |  | 7
MileStone_SIT approved | Task | Testing | MileStone_SIT approved | User Acceptance Testing |  | 1
User Acceptance Testing | Task | Testing | User Acceptance Testing | MileStone_UAT approved_Go Live decision |  | 21
MileStone_UAT approved_Go Live decision | Task | Testing | MileStone_UAT approved_Go Live decision | Deployment |  | 1
Delivery | Epic | Pilot
Deployment | Task | Delivery | Deployment | MileStone_Go Live |  | 2
MileStone_Go Live | Task | Delivery | MileStone_Go Live | Hypercare_Phase |  | 1
Hypercare_Phase | Task | Delivery | Hypercare_Phase | MileStone_Hypercare Closing_Handover to Customer Care |  | 21
MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | MileStone_Hypercare Closing_Handover to Customer Care | Lessons learned |  | 1
Lessons learned | Task | Delivery |  |  |  | 1