## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-5052 | Lessons learned | Task | Delivery | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5051 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-04-19 | 2024-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5050 | Hypercare_Phase | Task | Delivery | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5049 | MileStone_Go Live | Task | Delivery | To Do | 2024-03-28 | 2024-03-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5048 | Deployment | Task | Delivery | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5047 | Delivery | Epic | Pilot | To Do | 2024-03-26 | 2024-04-21 |  | stephan.kuche |  | []
TD-5046 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-03-25 | 2024-03-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5045 | User Acceptance Testing | Task | Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-5044 | MileStone_SIT approved | Task | Testing | To Do | 2024-03-03 | 2024-03-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5043 | System Integration Test (E2E) | Task | Testing | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5042 | Functional_Testing | Task | Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5041 | Testing | Epic | Pilot | To Do | 2024-02-22 | 2024-03-26 |  | stephan.kuche |  | []
TD-5040 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5039 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5038 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5037 | Application Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-5036 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5035 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5034 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5033 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5032 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5031 | Integration Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-5030 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5029 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5028 | Machine Learning | Epic | Pilot | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-5027 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-02-07 | 2024-02-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-5026 | Functional Design | Task | Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5025 | Design | Epic | Pilot | To Do | 2024-01-24 | 2024-02-08 |  | stephan.kuche |  | []
TD-5024 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-01-23 | 2024-01-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5023 | Requirement Analysis | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5022 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5021 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-24 |  | stephan.kuche |  | []
TD-5020 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-5019 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5018 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-5017 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-5016 | User Training | Epic | Pilot | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-5015 | Pilot | Project | TEST | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-5014 | TEST | Account |  | To Do |  |  |  | stephan.kuche |  | []
TD-5013 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5012 | Lessons learned | Task | Delivery | To Do | 2024-04-20 | 2024-04-21 |  | stephan.kuche |  | []
TD-5011 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-04-19 | 2024-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5010 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | []
TD-5009 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | []
TD-5008 | Hypercare_Phase | Task | Delivery | To Do | 2024-03-29 | 2024-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5007 | MileStone_Go Live | Task | Delivery | To Do | 2024-03-28 | 2024-03-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5006 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-5005 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-5004 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-5003 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | []
TD-5002 | Deployment | Task | Delivery | To Do | 2024-03-26 | 2024-03-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5001 | Delivery | Epic | Pilot | To Do | 2024-03-26 | 2024-04-21 |  | stephan.kuche |  | []
TD-5000 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-03-25 | 2024-03-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-4999 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-4998 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | []
TD-4997 | User Acceptance Testing | Task | Testing | To Do | 2024-03-04 | 2024-03-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-4996 | MileStone_SIT approved | Task | Testing | To Do | 2024-03-03 | 2024-03-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-4995 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-4994 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-4993 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-4992 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-4991 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4990 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4989 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | []
TD-4988 | System Integration Test (E2E) | Task | Testing | To Do | 2024-02-25 | 2024-03-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-4987 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-4986 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-4985 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | []
TD-4984 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-02-22 | 2024-02-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-4983 | Functional_Testing | Task | Testing | To Do | 2024-02-22 | 2024-02-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-4982 | Testing | Epic | Pilot | To Do | 2024-02-22 | 2024-03-26 |  | stephan.kuche |  | []
TD-4981 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4980 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4979 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4978 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4977 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4976 | Create PO Line Matching Configuration | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4975 | Create Company Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4974 | Create Supplier Master Data Configuration | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4973 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | []
TD-4972 | Schema Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4971 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4970 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4969 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4968 | Studio Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4967 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-4966 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-4965 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-02-08 | 2024-02-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-4964 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4963 | Application Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4962 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | []
TD-4961 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4960 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-4959 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4958 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-4957 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-4956 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-4955 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-10 |  | stephan.kuche |  | []
TD-4954 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-4953 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-4952 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4951 | Integration Implementation | Epic | Pilot | To Do | 2024-02-08 | 2024-02-11 |  | stephan.kuche |  | []
TD-4950 | Emodel Results analyis | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4949 | QA Emodel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4948 | Train EModel | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4947 | Create EM Ticket | Sub-task | Enrichment_Model_Configuration | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | []
TD-4946 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-22 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4945 | Capturing Model Evaluation | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4944 | Capturing Model Development | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4943 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4942 | Perform Capturing Model QA | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4941 | Annotation of Documents | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4940 | Upload Training Data | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4939 | Create Baseline Project | Sub-task | Capturing Model Configuration | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4938 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-4937 | Machine Learning | Epic | Pilot | To Do | 2024-02-08 | 2024-02-29 |  | stephan.kuche |  | []
TD-4936 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-02-07 | 2024-02-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-4935 | Create Solution Design | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4934 | Create SoW | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4933 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4932 | ReportingandMonitoring Design | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4931 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4930 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4929 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4928 | Document Outbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4927 | Document Inbound Configuration Integration | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4926 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4925 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-4924 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4923 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4922 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4921 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4920 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | []
TD-4919 | Functional Design | Task | Design | To Do | 2024-01-24 | 2024-02-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-4918 | Design | Epic | Pilot | To Do | 2024-01-24 | 2024-02-08 |  | stephan.kuche |  | []
TD-4917 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-01-23 | 2024-01-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-4916 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4915 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4914 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-4913 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | CUS Deliverable | stephan.kuche |  | []
TD-4912 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-4911 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4910 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-4909 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-4908 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-4907 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-4906 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-4905 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | ERP PO data | stephan.kuche |  | []
TD-4904 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | ERP master data | stephan.kuche |  | []
TD-4903 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-01-06 | 2024-01-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-4902 | Requirement Analysis | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-4901 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4900 | Get Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4899 | Get Posting Data inlc. Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4898 | Prepare Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | CUS Deliverable - create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-4897 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4896 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4895 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-4894 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4893 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-4892 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4891 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-4890 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4889 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4888 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 | [TEST and [ML] | stephan.kuche |  | []
TD-4887 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | []
TD-4886 | Data Acquisition | Task | Assessment | To Do | 2024-01-06 | 2024-01-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-4885 | Assessment | Epic | Pilot | To Do | 2024-01-06 | 2024-01-24 |  | stephan.kuche |  | []
TD-4884 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-01-01 | 2024-01-02 |  | stephan.kuche |  | []
TD-4883 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4882 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4881 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4880 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-4879 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-4878 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4877 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4876 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4875 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4874 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4873 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4872 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Optional | stephan.kuche |  | []
TD-4871 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4870 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4869 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4868 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4867 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4866 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-4865 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4864 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4863 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4862 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4861 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4860 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Including all relevant Files | stephan.kuche |  | []
TD-4859 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4858 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-4857 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4856 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-01-01 | 2024-01-06 | PM Deliverable | stephan.kuche |  | []
TD-4855 | Project Set up | Task | Project Management | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-4854 | Project Management | Epic | Pilot | To Do | 2024-01-01 | 2024-01-06 |  | stephan.kuche |  | []
TD-4853 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4852 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4851 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4850 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 | recommendations to improve model performance | stephan.kuche |  | []
TD-4849 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4848 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4847 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4846 | Request UserList | Sub-task | User Onboarding | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4845 | User Onboarding | Task | User Training | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []
TD-4844 | User Training | Epic | Pilot | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche | Cus | []
TD-4843 | Pilot | Project |  | To Do | 2024-01-01 | 2024-04-30 |  | stephan.kuche |  | []