## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-476 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-07-26 | 2024-07-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-475 | Lessons learned | Task | Delivery | To Do | 2024-07-26 | 2024-07-27 |  | stephan.kuche |  | []
TD-474 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-07-05 | 2024-07-26 |  | stephan.kuche |  | []
TD-473 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-07-05 | 2024-07-26 |  | stephan.kuche |  | []
TD-472 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-07-05 | 2024-07-26 |  | stephan.kuche |  | []
TD-471 | Hypercare_Phase | Task | Delivery | To Do | 2024-07-05 | 2024-07-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-470 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-07-03 | 2024-07-05 |  | stephan.kuche |  | []
TD-469 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-07-03 | 2024-07-05 |  | stephan.kuche |  | []
TD-468 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-07-03 | 2024-07-05 |  | stephan.kuche |  | []
TD-467 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-07-03 | 2024-07-05 |  | stephan.kuche |  | []
TD-466 | Deployment | Task | Delivery | To Do | 2024-07-03 | 2024-07-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-465 | Delivery | Epic | Rollout | To Do | 2024-07-03 | 2024-07-27 |  | stephan.kuche |  | []
TD-464 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-463 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-462 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-461 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 | recommendations to improve model performance | stephan.kuche |  | []
TD-460 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-459 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-458 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-457 | Request UserList | Sub-task | User Onboarding | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-456 | User Onboarding | Task | User Training | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-455 | User Training | Epic | Rollout | To Do | 2024-04-01 | 2024-05-01 |  | stephan.kuche |  | []
TD-454 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-06-12 | 2024-07-03 |  | stephan.kuche |  | []
TD-453 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-06-12 | 2024-07-03 |  | stephan.kuche |  | []
TD-452 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-06-12 | 2024-07-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-451 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-450 | Document inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-449 | Document inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-448 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-447 | Run Document outbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-446 | Run Posting Data inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-445 | Run Document inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | []
TD-444 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-06-05 | 2024-06-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-443 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-06-02 | 2024-06-05 |  | stephan.kuche |  | []
TD-442 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-06-02 | 2024-06-05 |  | stephan.kuche |  | []
TD-441 | Share Testing Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-06-02 | 2024-06-05 |  | stephan.kuche |  | []
TD-440 | Create testing workbook | Sub-task | Functional_Testing | To Do | 2024-06-02 | 2024-06-05 |  | stephan.kuche |  | []
TD-439 | Functional_Testing | Task | Testing_Phase | To Do | 2024-06-02 | 2024-06-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-438 | Testing_Phase | Epic | Rollout | To Do | 2024-06-02 | 2024-07-03 |  | stephan.kuche |  | []
TD-437 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | []
TD-436 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | []
TD-435 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | []
TD-434 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | []
TD-433 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | []
TD-432 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-05-26 | 2024-06-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-431 | Schema Configuration | Task | Application Implementation | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-430 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-429 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-428 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-427 | Studio Configuration | Task | Application Implementation | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-426 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-05-26 | 2024-05-27 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-425 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-05-26 | 2024-05-27 |  | stephan.kuche |  | []
TD-424 | Application Implementation | Epic | Rollout | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-423 | Emodel Results analyis | Sub-task | Enrichment_Model_Training | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-422 | QA Emodel | Sub-task | Enrichment_Model_Training | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-421 | Train EModel | Sub-task | Enrichment_Model_Training | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-420 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | []
TD-419 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-05-26 | 2024-06-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-418 | Capturing Model Evaluation | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-417 | Capturing Model Development | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-416 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-415 | Perform Capturing Model QA | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-414 | Annotation of Documents | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-413 | Upload Training Data | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-412 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-411 | Capturing Model Training | Task | Machine Learning | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-410 | Machine Learning | Epic | Rollout | To Do | 2024-05-26 | 2024-06-16 |  | stephan.kuche |  | []
TD-409 | Sign SoW | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-408 | Create SoW | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-407 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-406 | ReportingandMonitoring | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-405 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-404 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-403 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-402 | Document Outbound Integration | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-401 | Document Inbound Integration | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-400 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-399 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 | Customer to provide List | stephan.kuche |  | []
TD-398 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-397 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-396 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-395 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-394 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-393 | Functional Design | Task | Design | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'ReportingandMonitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Key User Reporting and Monitoring Training and QandA'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-392 | Design | Epic | Rollout | To Do | 2024-05-12 | 2024-05-26 |  | stephan.kuche |  | []
TD-391 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 |  | stephan.kuche |  | []
TD-390 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 |  | stephan.kuche |  | []
TD-389 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 |  | stephan.kuche |  | []
TD-388 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 |  | stephan.kuche |  | []
TD-387 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-386 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | Update questions, Slidedeck | stephan.kuche |  | []
TD-385 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-384 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-383 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | ERP PO data | stephan.kuche |  | []
TD-382 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | ERP master data | stephan.kuche |  | []
TD-381 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-04-25 | 2024-05-12 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-380 | Requirement Analysis | Task | Assessment | To Do | 2024-04-25 | 2024-05-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-379 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-04-06 | 2024-04-25 |  | stephan.kuche |  | []
TD-378 | Get Posting and Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-04-06 | 2024-04-25 |  | stephan.kuche |  | []
TD-377 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-04-06 | 2024-04-25 |  | stephan.kuche |  | []
TD-376 | Data Acquisition | Task | Assessment | To Do | 2024-04-06 | 2024-04-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-375 | Assessment | Epic | Rollout | To Do | 2024-04-06 | 2024-05-12 |  | stephan.kuche |  | []
TD-374 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-373 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-372 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-371 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-370 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-369 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-368 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-367 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-366 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-365 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 | Optional | stephan.kuche |  | []
TD-364 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-363 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-362 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-361 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-360 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-359 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-358 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-357 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-356 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-355 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-354 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 | Including all relevant Files | stephan.kuche |  | []
TD-353 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-352 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-351 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-350 | Project Set up | Task | Project Management | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-349 | Project Management | Epic | Rollout | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-348 | Rollout | Project | CustomerName | To Do | 2024-04-01 | 2024-04-01 |  | stephan.kuche |  | []
TD-347 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-06-25 | 2024-06-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-346 | Lessons learned | Task | Delivery | To Do | 2024-06-25 | 2024-06-26 |  | stephan.kuche |  | []
TD-345 | Handover to Customer Care | Sub-task | Hypercare_Phase | To Do | 2024-06-04 | 2024-06-25 |  | stephan.kuche |  | []
TD-344 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-06-04 | 2024-06-25 |  | stephan.kuche |  | []
TD-343 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-06-04 | 2024-06-25 |  | stephan.kuche |  | []
TD-342 | Hypercare_Phase | Task | Delivery | To Do | 2024-06-04 | 2024-06-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-341 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-06-02 | 2024-06-04 |  | stephan.kuche |  | []
TD-340 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-06-02 | 2024-06-04 |  | stephan.kuche |  | []
TD-339 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-06-02 | 2024-06-04 |  | stephan.kuche |  | []
TD-338 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-06-02 | 2024-06-04 |  | stephan.kuche |  | []
TD-337 | Deployment | Task | Delivery | To Do | 2024-06-02 | 2024-06-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-336 | Delivery | Epic | Pilot | To Do | 2024-06-02 | 2024-06-26 |  | stephan.kuche |  | []
TD-335 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-334 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-333 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-332 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 | recommendations to improve model performance | stephan.kuche |  | []
TD-331 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-330 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-329 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-328 | Request UserList | Sub-task | User Onboarding | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-327 | User Onboarding | Task | User Training | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-326 | User Training | Epic | Pilot | To Do | 2024-03-01 | 2024-03-31 |  | stephan.kuche |  | []
TD-325 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-05-12 | 2024-06-02 |  | stephan.kuche |  | []
TD-324 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-05-12 | 2024-06-02 |  | stephan.kuche |  | []
TD-323 | User Acceptance Testing | Task | Testing_Phase | To Do | 2024-05-12 | 2024-06-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-322 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | []
TD-321 | Document inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-320 | Document inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | []
TD-319 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | []
TD-318 | Run Document outbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | []
TD-317 | Run Posting Data inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-316 | Run Document inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | []
TD-315 | System Integration Test (E2E) | Task | Testing_Phase | To Do | 2024-05-05 | 2024-05-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-314 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-05-02 | 2024-05-05 |  | stephan.kuche |  | []
TD-313 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-05-02 | 2024-05-05 |  | stephan.kuche |  | []
TD-312 | Share Testing Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-05-02 | 2024-05-05 |  | stephan.kuche |  | []
TD-311 | Create testing workbook | Sub-task | Functional_Testing | To Do | 2024-05-02 | 2024-05-05 |  | stephan.kuche |  | []
TD-310 | Functional_Testing | Task | Testing_Phase | To Do | 2024-05-02 | 2024-05-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Schema Configuration'}]
TD-309 | Testing_Phase | Epic | Pilot | To Do | 2024-05-02 | 2024-06-02 |  | stephan.kuche |  | []
TD-308 | Configure ReRouting Rules | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | []
TD-307 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | []
TD-306 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | []
TD-305 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | []
TD-304 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | []
TD-303 | Create Composite Enrichment in Setup | Sub-task | Schema Configuration | To Do | 2024-04-25 | 2024-05-02 | Configure Attribute Prediction, Configure Master Data Enrichment | stephan.kuche |  | []
TD-302 | Schema Configuration | Task | Application Implementation | To Do | 2024-04-25 | 2024-05-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-301 | Send Masterdata via API to autocreate indexes | Sub-task | Studio Configuration | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-300 | Creation of projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-299 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-298 | Studio Configuration | Task | Application Implementation | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-297 | Configure dashboards in Insights according to template | Sub-task | Reporting and Monitoring | To Do | 2024-03-01 | 2024-03-02 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-296 | Reporting and Monitoring | Task | Application Implementation | To Do | 2024-03-01 | 2024-03-02 |  | stephan.kuche |  | []
TD-295 | Application Implementation | Epic | Pilot | To Do | 2024-03-01 | 2024-05-09 |  | stephan.kuche |  | []
TD-294 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-04-25 | 2024-04-26 |  | stephan.kuche |  | []
TD-293 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-04-25 | 2024-04-26 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-292 | API Configuration Support PO | Sub-task | PO data inbound | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | []
TD-291 | PO data inbound | Task | Integration Implementation | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-290 | API Configuration Support PDIB | Sub-task | Posting data inbound | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | []
TD-289 | Posting data inbound | Task | Integration Implementation | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | []
TD-288 | API Configuration Support OB | Sub-task | Document Outbound | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | []
TD-287 | Document Outbound | Task | Integration Implementation | To Do | 2024-04-25 | 2024-04-27 |  | stephan.kuche |  | []
TD-286 | Support API Configuration | Sub-task | Document Inbound | To Do | 2024-04-25 | 2024-04-28 |  | stephan.kuche |  | []
TD-285 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound | To Do | 2024-04-25 | 2024-04-28 |  | stephan.kuche |  | []
TD-284 | Document Inbound | Task | Integration Implementation | To Do | 2024-04-25 | 2024-04-28 |  | stephan.kuche |  | []
TD-283 | Integration Implementation | Epic | Pilot | To Do | 2024-04-25 | 2024-04-28 |  | stephan.kuche |  | []
TD-282 | Emodel Results analyis | Sub-task | Enrichment_Model_Training | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-281 | QA Emodel | Sub-task | Enrichment_Model_Training | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-280 | Train EModel | Sub-task | Enrichment_Model_Training | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-279 | Create EM Ticket | Sub-task | Enrichment_Model_Training | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | []
TD-278 | Enrichment_Model_Training | Task | Machine Learning | To Do | 2024-04-25 | 2024-05-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-277 | Capturing Model Evaluation | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-276 | Capturing Model Development | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-275 | Perform Capturing Model Results Analysis | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-274 | Perform Capturing Model QA | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-273 | Annotation of Documents | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-272 | Upload Training Data | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-271 | Create Baseline Project | Sub-task | Capturing Model Training | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-270 | Capturing Model Training | Task | Machine Learning | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-269 | Machine Learning | Epic | Pilot | To Do | 2024-04-25 | 2024-05-16 |  | stephan.kuche |  | []
TD-268 | Sign SoW | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-267 | Create SoW | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-266 | Document reporting and monitoring concept | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-265 | ReportingandMonitoring | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-264 | Create Integration rules | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-263 | Create Technical Datapoint Mapping | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-262 | Posting Data Inbound Integration Documentation | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-261 | Document Outbound Integration | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-260 | Document Inbound Integration | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-259 | Create Studio companies and projects concept design | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-258 | List of users and roles (permissions) | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 | Customer to provide List | stephan.kuche |  | []
TD-257 | Create EndUSer Process design | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-256 | Add Derivation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-255 | Add Validation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-254 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-253 | Create and populate Datapoint Template | Sub-task | Functional Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-252 | Functional Design | Task | Design | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'ReportingandMonitoring'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Training'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO data inbound'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting Data inbound load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document inbound and outbound penny test in PROD env'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-251 | Design | Epic | Pilot | To Do | 2024-04-11 | 2024-04-25 |  | stephan.kuche |  | []
TD-250 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 |  | stephan.kuche |  | []
TD-249 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 |  | stephan.kuche |  | []
TD-248 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 |  | stephan.kuche |  | []
TD-247 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 |  | stephan.kuche |  | []
TD-246 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-245 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | Update questions, Slidedeck | stephan.kuche |  | []
TD-244 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-243 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-242 | Perfrom Document analysis | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-241 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | ERP PO data | stephan.kuche |  | []
TD-240 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | ERP master data | stephan.kuche |  | []
TD-239 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-03-25 | 2024-04-11 | ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-238 | Requirement Analysis | Task | Assessment | To Do | 2024-03-25 | 2024-04-11 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-237 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-236 | Get Posting and Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-235 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-234 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-233 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-232 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-231 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-230 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-229 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 | (R3, S4Hana) | stephan.kuche |  | []
TD-228 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-227 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-226 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 | [TEST and [ML] | stephan.kuche |  | []
TD-225 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | []
TD-224 | Data Acquisition | Task | Assessment | To Do | 2024-03-06 | 2024-03-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-223 | Assessment | Epic | Pilot | To Do | 2024-03-06 | 2024-04-11 |  | stephan.kuche |  | []
TD-222 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-221 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-220 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-219 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-218 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-217 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-216 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-215 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-214 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-213 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 | Optional | stephan.kuche |  | []
TD-212 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-211 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-210 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-209 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-208 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-207 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-206 | Clone Sharepoint folder to CUS MS env | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-205 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-204 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-203 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-202 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 | Including all relevant Files | stephan.kuche |  | []
TD-201 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-200 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-199 | Create StakeholderMapping | Sub-task | Project Set up | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-198 | Project Set up | Task | Project Management | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}]
TD-197 | Project Management | Epic | Pilot | To Do | 2024-03-01 | 2024-03-06 |  | stephan.kuche |  | []
TD-196 | Pilot | Project | CustomerName | To Do | 2024-03-01 | 2024-03-01 |  | stephan.kuche |  | []
TD-195 | CustomerName | Account |  | To Do | 2024-03-01 | 2024-03-01 |  | stephan.kuche |  | []