## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
BLG-781 | Lessons learned Page | Task | Delivery | To Do | 2025-06-27 | 2025-06-28 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
BLG-780 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2025-06-26 | 2025-06-27 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned Page'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
BLG-779 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2025-06-05 | 2025-06-26 |  |  |  | []
BLG-778 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2025-06-05 | 2025-06-26 |  |  |  | []
BLG-777 | Hypercare_Phase | Task | Delivery | To Do | 2025-06-05 | 2025-06-26 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
BLG-776 | MileStone_Go Live | Task | Delivery | To Do | 2025-06-04 | 2025-06-05 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
BLG-775 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2025-06-02 | 2025-06-04 |  |  |  | []
BLG-774 | Cutover and Go Live | Sub-task | Deployment | To Do | 2025-06-02 | 2025-06-04 |  |  |  | []
BLG-773 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2025-06-02 | 2025-06-04 |  |  |  | []
BLG-772 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2025-06-02 | 2025-06-04 |  |  |  | []
BLG-771 | Deployment | Task | Delivery | To Do | 2025-06-02 | 2025-06-04 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
BLG-770 | Delivery | Epic | [PILOT] | To Do | 2025-06-02 | 2025-06-28 |  |  |  | []
BLG-769 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2025-06-01 | 2025-06-02 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
BLG-768 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-05-11 | 2025-06-01 |  |  |  | []
BLG-767 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-05-11 | 2025-06-01 |  |  |  | []
BLG-766 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2025-05-11 | 2025-06-01 |  |  |  | []
BLG-765 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2025-05-11 | 2025-06-01 |  |  |  | []
BLG-764 | User Acceptance Testing | Task | Testing | To Do | 2025-05-11 | 2025-06-01 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
BLG-763 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-04 | 2025-05-11 |  |  |  | []
BLG-762 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-04 | 2025-05-11 |  |  |  | []
BLG-761 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-04 | 2025-05-11 |  |  |  | []
BLG-760 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2025-05-04 | 2025-05-11 |  |  |  | []
BLG-759 | System Integration Test (E2E) | Task | Testing | To Do | 2025-05-04 | 2025-05-11 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
BLG-758 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2025-05-01 | 2025-05-04 |  |  |  | []
BLG-757 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2025-05-01 | 2025-05-04 |  |  |  | []
BLG-756 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2025-05-01 | 2025-05-04 |  |  |  | []
BLG-755 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2025-05-01 | 2025-05-04 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report |  |  | []
BLG-754 | Functional_Testing | Task | Testing | To Do | 2025-05-01 | 2025-05-04 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration_SAP_Configured'}]
BLG-753 | Testing | Epic | [PILOT] | To Do | 2025-05-01 | 2025-06-02 |  |  |  | []
BLG-752 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2025-04-30 | 2025-05-01 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Document Outbound Configuration'}]
BLG-751 | Configure SAP Connector Document Transfer to workflow | Sub-task | Document Outbound Configuration | To Do | 2025-04-16 | 2025-04-30 |  |  |  | []
BLG-750 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2025-04-16 | 2025-04-30 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
BLG-749 | Configuration Support MD PO | Sub-task | Master_Data_Inbound_Configuration | To Do | 2025-04-16 | 2025-04-17 |  |  |  | []
BLG-748 | Master_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-04-16 | 2025-04-17 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
BLG-747 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2025-04-16 | 2025-04-17 |  |  |  | []
BLG-746 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-04-16 | 2025-04-17 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
BLG-745 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2025-04-15 | 2025-04-16 |  |  |  | []
BLG-744 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2025-04-15 | 2025-04-16 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Master_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
BLG-743 | Configure Email forwarding or redirecting | Sub-task | Document Inbound Configuration | To Do | 2025-04-15 | 2025-04-17 | CUS to create rules and test |  |  | []
BLG-742 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2025-04-15 | 2025-04-17 |  |  |  | []
BLG-741 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2025-04-15 | 2025-04-17 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
BLG-740 | Integration Implementation | Epic | [PILOT] | To Do | 2025-04-15 | 2025-05-01 |  |  |  | []
BLG-739 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-04-09 | 2025-04-11 |  |  |  | []
BLG-738 | CreatePO Line Config or add agentic workflow to config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-04-09 | 2025-04-11 |  |  |  | []
BLG-737 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-11 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-736 | Create Composite Enrichment in Step Company MD or add agentic workflow to config | Sub-task | Company_Master_Data_Enrichment | To Do | 2025-04-09 | 2025-04-11 |  |  |  | []
BLG-735 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-11 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-734 | Create Composite Enrichment in Step Supplier MD or add agentic workflow to config | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2025-04-09 | 2025-04-11 |  |  |  | []
BLG-733 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-11 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-732 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-731 | Add Costcenter Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-730 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-16 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-729 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-728 | Add GL Account Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-727 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-16 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-726 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-725 | Add Approver Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-04-09 | 2025-04-16 |  |  |  | []
BLG-724 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2025-04-09 | 2025-04-16 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
BLG-723 | Extraction Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-02 | 2025-04-09 |  |  |  | []
BLG-722 | Perform Extraction Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-02 | 2025-04-09 |  |  |  | []
BLG-721 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-02 | 2025-04-09 |  |  |  | []
BLG-720 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-02 | 2025-04-09 |  |  |  | []
BLG-719 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-02 | 2025-04-09 |  |  |  | []
BLG-718 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-04-02 | 2025-04-09 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
BLG-717 | Add LLM to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2025-04-01 | 2025-04-02 |  |  |  | []
BLG-716 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-04-01 | 2025-04-02 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
BLG-715 | Machine Learning | Epic | [PILOT] | To Do | 2025-04-01 | 2025-04-16 |  |  |  | []
BLG-714 | MileStone_Studio_Configured | Task | Application Implementation | To Do | 2025-04-14 | 2025-04-15 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}]
BLG-713 | Configure Insights Dashboards | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-04-13 | 2025-04-14 | Insights Standard Collections |  |  | []
BLG-712 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2025-04-13 | 2025-04-14 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}]
BLG-711 | Configure Schema accroding to datapoint_list | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-710 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-709 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-708 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-707 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-706 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-01 | 2025-04-13 |  |  |  | []
BLG-705 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2025-04-01 | 2025-04-13 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
BLG-704 | Application Implementation | Epic | [PILOT] | To Do | 2025-04-01 | 2025-04-15 |  |  |  | []
BLG-703 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2025-03-31 | 2025-04-01 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
BLG-702 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-701 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-700 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-699 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-698 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-697 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-696 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-695 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-694 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-693 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 | CUS Deliverable - Customer to provide List of Users |  |  | []
BLG-692 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-691 | Add Normalisation, Validation, Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-690 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | []
BLG-689 | Functional & Technical Solution Design | Task | Design | To Do | 2025-03-17 | 2025-03-31 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
BLG-688 | Design | Epic | [PILOT] | To Do | 2025-03-17 | 2025-04-01 |  |  |  | []
BLG-687 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2025-03-16 | 2025-03-17 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
BLG-686 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-685 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-684 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | CUS Deliverable |  |  | []
BLG-683 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | CUS Deliverable |  |  | []
BLG-682 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Requirement Gathering Deliverable |  |  | []
BLG-681 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-680 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis |  |  | []
BLG-679 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Update questions, Slidedeck |  |  | []
BLG-678 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template |  |  | []
BLG-677 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Process documentation, Hypatos Studio Standard process template |  |  | []
BLG-676 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Documents (datapoints), Document types, document languages (regions) analysis |  |  | []
BLG-675 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | ERP PO data |  |  | []
BLG-674 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | ERP master data |  |  | []
BLG-673 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2025-02-27 | 2025-03-16 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template |  |  | []
BLG-672 | Requirement Analysis | Task | Assessment | To Do | 2025-02-27 | 2025-03-16 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
BLG-671 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 | Create a list of top vendorids, or companycodes in scope |  |  | []
BLG-670 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-669 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-668 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-667 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-666 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-665 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-664 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-663 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-662 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-661 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-660 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-659 | Create QA Project | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-658 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-657 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-656 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-655 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-654 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-653 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 | (Install and Service Packages) |  |  | []
BLG-652 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-651 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 | (R3, S4Hana) |  |  | []
BLG-650 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-649 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-648 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 | [TEST] |  |  | []
BLG-647 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-646 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2025-02-27 | 2025-03-16 |  |  |  | []
BLG-645 | Data Acquisition | Task | Assessment | To Do | 2025-02-27 | 2025-03-16 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
BLG-644 | Assessment | Epic | [PILOT] | To Do | 2025-02-27 | 2025-03-17 |  |  |  | []
BLG-643 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2025-02-26 | 2025-02-27 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
BLG-642 | Schedule Workshops (Discovery, Technical, Solution Design) | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-641 | Allocate_Time_for_Tests_Testing team UAT | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | CUS |  |  | []
BLG-640 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) |  |  | []
BLG-639 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable (monthly) |  |  | []
BLG-638 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-637 | Create Solution Design Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-636 | Create Discovery Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-635 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-634 | Create Project timeline | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-633 | Create RAID Log | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-632 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-631 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-630 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-629 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-628 | Teams Channel & Page Setup | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-627 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-626 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-625 | Create Absence Planner | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-624 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | Including all relevant Files |  |  | []
BLG-623 | Create Confluence Space and update Documentation | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | Included in Handover from Sales |  |  | []
BLG-622 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-621 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2025-02-26 | 2025-06-16 | PM Deliverable |  |  | []
BLG-620 | Project Set up | Task | Project Management | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-619 | JourFix | Sub-task | Meetings | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-618 | SteerCo | Sub-task | Meetings | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-617 | Adhoc | Sub-task | Meetings | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-616 | Meetings | Task | Project Management | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-615 | Project Management | Epic | [PILOT] | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-614 | Milestone_Usertraining_completed | Task | User Training | To Do | 2025-06-16 | 2025-06-17 |  |  |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
BLG-613 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-612 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-611 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-610 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-609 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 | recommendations to improve model performance |  |  | []
BLG-608 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-607 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-606 | Provide UserList | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-605 | Request UserList | Sub-task | User Onboarding | To Do | 2025-02-26 | 2025-06-16 |  |  |  | []
BLG-604 | User Onboarding | Task | User Training | To Do | 2025-02-26 | 2025-06-16 |  |  |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
BLG-603 | User Training | Epic | [PILOT] | To Do | 2025-02-26 | 2025-06-17 |  |  |  | []
BLG-602 | [PILOT] | Project | BLG | To Do | 2025-02-26 | 2025-06-28 |  |  |  | []
BLG-2 | [BLG] - Pilot | Project | BLG | To Do | 2025-02-17 | 2025-07-31 | Description: * Similar to FNK * SAP x-suite ** Migrate recently to SAP SANA Scope: * IN: ** only Non-PO ** Doc AI ** VMD, CMD ** AP (account prediction) * Out of scope: ** PO Matching * Inbound: ** email listener - to confirm * Outbound: ** HY SAP connector? * HY Studio for doc validation | michael.misterka |  | []
BLG-1 | BLG | Account |  | Backlog |  |  |  | Alex Menuet |  | []