## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TMP-398 | Lessons learned Page | Task | Delivery | To Do | 2025-06-30 | 2025-07-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TMP-397 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2025-06-29 | 2025-06-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned Page'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TMP-396 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2025-06-08 | 2025-06-29 |  | stephan.kuche |  | []
TMP-395 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2025-06-08 | 2025-06-29 |  | stephan.kuche |  | []
TMP-394 | Hypercare_Phase | Task | Delivery | To Do | 2025-06-08 | 2025-06-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TMP-393 | MileStone_Go Live | Task | Delivery | To Do | 2025-06-07 | 2025-06-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TMP-392 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2025-06-05 | 2025-06-07 |  | stephan.kuche |  | []
TMP-391 | Cutover and Go Live | Sub-task | Deployment | To Do | 2025-06-05 | 2025-06-07 |  | stephan.kuche |  | []
TMP-390 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2025-06-05 | 2025-06-07 |  | stephan.kuche |  | []
TMP-389 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2025-06-05 | 2025-06-07 |  | stephan.kuche |  | []
TMP-388 | Deployment | Task | Delivery | To Do | 2025-06-05 | 2025-06-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TMP-387 | Delivery | Epic | [PILOT][TMP][SAP] | To Do | 2025-06-05 | 2025-07-01 |  | stephan.kuche |  | []
TMP-386 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2025-06-04 | 2025-06-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TMP-385 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-05-14 | 2025-06-04 |  | stephan.kuche |  | []
TMP-384 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-05-14 | 2025-06-04 |  | stephan.kuche |  | []
TMP-383 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2025-05-14 | 2025-06-04 |  | stephan.kuche |  | []
TMP-382 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2025-05-14 | 2025-06-04 |  | stephan.kuche |  | []
TMP-381 | User Acceptance Testing | Task | Testing | To Do | 2025-05-14 | 2025-06-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TMP-380 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-07 | 2025-05-14 |  | stephan.kuche |  | []
TMP-379 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-07 | 2025-05-14 |  | stephan.kuche |  | []
TMP-378 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2025-05-07 | 2025-05-14 |  | stephan.kuche |  | []
TMP-377 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2025-05-07 | 2025-05-14 |  | stephan.kuche |  | []
TMP-376 | System Integration Test (E2E) | Task | Testing | To Do | 2025-05-07 | 2025-05-14 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TMP-375 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2025-05-04 | 2025-05-07 |  | stephan.kuche |  | []
TMP-374 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2025-05-04 | 2025-05-07 |  | stephan.kuche |  | []
TMP-373 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2025-05-04 | 2025-05-07 |  | stephan.kuche |  | []
TMP-372 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2025-05-04 | 2025-05-07 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TMP-371 | Functional_Testing | Task | Testing | To Do | 2025-05-04 | 2025-05-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration_SAP_Configured'}]
TMP-370 | Testing | Epic | [PILOT][TMP][SAP] | To Do | 2025-05-04 | 2025-06-05 |  | stephan.kuche |  | []
TMP-369 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2025-05-03 | 2025-05-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Document Outbound Configuration'}]
TMP-368 | Configure SAP Connector Document Transfer to workflow | Sub-task | Document Outbound Configuration | To Do | 2025-04-19 | 2025-05-03 |  | stephan.kuche |  | []
TMP-367 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2025-04-19 | 2025-05-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-366 | Configuration Support MD PO | Sub-task | Master_Data_Inbound_Configuration | To Do | 2025-04-19 | 2025-04-20 |  | stephan.kuche |  | []
TMP-365 | Master_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-04-19 | 2025-04-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-364 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2025-04-19 | 2025-04-20 |  | stephan.kuche |  | []
TMP-363 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-04-19 | 2025-04-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-362 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2025-04-18 | 2025-04-19 |  | stephan.kuche |  | []
TMP-361 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2025-04-18 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Master_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
TMP-360 | Configure Email forwarding or redirecting | Sub-task | Document Inbound Configuration | To Do | 2025-04-18 | 2025-04-20 | CUS to create rules and test | stephan.kuche |  | []
TMP-359 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2025-04-18 | 2025-04-20 |  | stephan.kuche |  | []
TMP-358 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2025-04-18 | 2025-04-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
TMP-357 | Integration Implementation | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-18 | 2025-05-04 |  | stephan.kuche |  | []
TMP-356 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | []
TMP-355 | CreatePO Line Config or add agentic workflow to config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | []
TMP-354 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-353 | Create Composite Enrichment in Step Company MD or add agentic workflow to config | Sub-task | Company_Master_Data_Enrichment | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | []
TMP-352 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-351 | Create Composite Enrichment in Step Supplier MD or add agentic workflow to config | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | []
TMP-350 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-14 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-349 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-348 | Add Costcenter Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-347 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-346 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-345 | Add GL Account Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-344 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-343 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-342 | Add Approver Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | []
TMP-341 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2025-04-12 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-340 | Extraction Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | []
TMP-339 | Perform Extraction Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | []
TMP-338 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | []
TMP-337 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | []
TMP-336 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | []
TMP-335 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-04-05 | 2025-04-12 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
TMP-334 | Add LLM to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2025-04-04 | 2025-04-05 |  | stephan.kuche |  | []
TMP-333 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-04-04 | 2025-04-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TMP-332 | Machine Learning | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-04 | 2025-04-19 |  | stephan.kuche |  | []
TMP-331 | MileStone_Studio_Configured | Task | Application Implementation | To Do | 2025-04-17 | 2025-04-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}]
TMP-330 | Configure Insights Dashboards | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-04-16 | 2025-04-17 | Insights Standard Collections | stephan.kuche |  | []
TMP-329 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2025-04-16 | 2025-04-17 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}]
TMP-328 | Configure Schema accroding to datapoint_list | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-327 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-326 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-325 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-324 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-323 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | []
TMP-322 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2025-04-04 | 2025-04-16 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TMP-321 | Application Implementation | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-04 | 2025-04-18 |  | stephan.kuche |  | []
TMP-320 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2025-04-03 | 2025-04-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TMP-319 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-318 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-317 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-316 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-315 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-314 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-313 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-312 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-311 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-310 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TMP-309 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-308 | Add Normalisation, Validation, Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-307 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | []
TMP-306 | Functional & Technical Solution Design | Task | Design | To Do | 2025-03-20 | 2025-04-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TMP-305 | Design | Epic | [PILOT][TMP][SAP] | To Do | 2025-03-20 | 2025-04-04 |  | stephan.kuche |  | []
TMP-304 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2025-03-19 | 2025-03-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TMP-303 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-302 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-301 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | CUS Deliverable | stephan.kuche |  | []
TMP-300 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | CUS Deliverable | stephan.kuche |  | []
TMP-299 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Requirement Gathering Deliverable | stephan.kuche |  | []
TMP-298 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-297 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TMP-296 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Update questions, Slidedeck | stephan.kuche |  | []
TMP-295 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TMP-294 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TMP-293 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TMP-292 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | ERP PO data | stephan.kuche |  | []
TMP-291 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | ERP master data | stephan.kuche |  | []
TMP-290 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2025-03-02 | 2025-03-19 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TMP-289 | Requirement Analysis | Task | Assessment | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TMP-288 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TMP-287 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-286 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-285 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-284 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-283 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-282 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-281 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-280 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-279 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-278 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-277 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-276 | Create QA Project | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-275 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-274 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-273 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-272 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-271 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-270 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 | (Install and Service Packages) | stephan.kuche |  | []
TMP-269 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-268 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 | (R3, S4Hana) | stephan.kuche |  | []
TMP-267 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-266 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-265 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 | [TEST] | stephan.kuche |  | []
TMP-264 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-263 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | []
TMP-262 | Data Acquisition | Task | Assessment | To Do | 2025-03-02 | 2025-03-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TMP-261 | Assessment | Epic | [PILOT][TMP][SAP] | To Do | 2025-03-02 | 2025-03-20 |  | stephan.kuche |  | []
TMP-260 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2025-03-01 | 2025-03-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TMP-259 | Schedule Workshops (Discovery, Technical, Solution Design) | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-258 | Allocate_Time_for_Tests_Testing team UAT | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | CUS | stephan.kuche |  | []
TMP-257 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TMP-256 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable (monthly) | stephan.kuche |  | []
TMP-255 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-254 | Create Solution Design Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-253 | Create Discovery Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-252 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-251 | Create Project timeline | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-250 | Create RAID Log | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-249 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-248 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-247 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-246 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-245 | Teams Channel & Page Setup | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-244 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-243 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-242 | Create Absence Planner | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-241 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | Including all relevant Files | stephan.kuche |  | []
TMP-240 | Create Confluence Space and update Documentation | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | Included in Handover from Sales | stephan.kuche |  | []
TMP-239 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-238 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2025-03-01 | 2025-06-19 | PM Deliverable | stephan.kuche |  | []
TMP-237 | Project Set up | Task | Project Management | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-236 | JourFix | Sub-task | Meetings | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-235 | SteerCo | Sub-task | Meetings | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-234 | Adhoc | Sub-task | Meetings | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-233 | Meetings | Task | Project Management | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-232 | Project Management | Epic | [PILOT][TMP][SAP] | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-231 | Milestone_Usertraining_completed | Task | User Training | To Do | 2025-06-19 | 2025-06-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TMP-230 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-229 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-228 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-227 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-226 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 | recommendations to improve model performance | stephan.kuche |  | []
TMP-225 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-224 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-223 | Provide UserList | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-222 | Request UserList | Sub-task | User Onboarding | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | []
TMP-221 | User Onboarding | Task | User Training | To Do | 2025-03-01 | 2025-06-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TMP-220 | User Training | Epic | [PILOT][TMP][SAP] | To Do | 2025-03-01 | 2025-06-20 |  | stephan.kuche |  | []
TMP-219 | [PILOT][TMP][SAP] | Project |  | To Do | 2025-03-01 | 2025-07-01 |  | stephan.kuche |  | []
TMP-1 | TMP | Account |  | To Do |  |  |  | stephan.kuche |  | []