## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TMP-578 | Lessons learned Page | Task | Delivery | To Do | 2025-07-31 | 2025-08-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TMP-577 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2025-07-30 | 2025-07-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned Page'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TMP-576 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2025-07-09 | 2025-07-30 |  | stephan.kuche |  | []
TMP-575 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2025-07-09 | 2025-07-30 |  | stephan.kuche |  | []
TMP-574 | Hypercare_Phase | Task | Delivery | To Do | 2025-07-09 | 2025-07-30 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TMP-573 | MileStone_Go Live | Task | Delivery | To Do | 2025-07-08 | 2025-07-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TMP-572 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2025-07-06 | 2025-07-08 |  | stephan.kuche |  | []
TMP-571 | Cutover and Go Live | Sub-task | Deployment | To Do | 2025-07-06 | 2025-07-08 |  | stephan.kuche |  | []
TMP-570 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2025-07-06 | 2025-07-08 |  | stephan.kuche |  | []
TMP-569 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2025-07-06 | 2025-07-08 |  | stephan.kuche |  | []
TMP-568 | Deployment | Task | Delivery | To Do | 2025-07-06 | 2025-07-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TMP-567 | Delivery | Epic | [PILOT][TMP][SAP] | To Do | 2025-07-06 | 2025-08-01 |  | stephan.kuche |  | []
TMP-566 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2025-07-05 | 2025-07-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TMP-565 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-06-14 | 2025-07-05 |  | stephan.kuche |  | []
TMP-564 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2025-06-14 | 2025-07-05 |  | stephan.kuche |  | []
TMP-563 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2025-06-14 | 2025-07-05 |  | stephan.kuche |  | []
TMP-562 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2025-06-14 | 2025-07-05 |  | stephan.kuche |  | []
TMP-561 | User Acceptance Testing | Task | Testing | To Do | 2025-06-14 | 2025-07-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TMP-560 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-06-07 | 2025-06-14 |  | stephan.kuche |  | []
TMP-559 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2025-06-07 | 2025-06-14 |  | stephan.kuche |  | []
TMP-558 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2025-06-07 | 2025-06-14 |  | stephan.kuche |  | []
TMP-557 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2025-06-07 | 2025-06-14 |  | stephan.kuche |  | []
TMP-556 | System Integration Test (E2E) | Task | Testing | To Do | 2025-06-07 | 2025-06-14 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TMP-555 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2025-06-04 | 2025-06-07 |  | stephan.kuche |  | []
TMP-554 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2025-06-04 | 2025-06-07 |  | stephan.kuche |  | []
TMP-553 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2025-06-04 | 2025-06-07 |  | stephan.kuche |  | []
TMP-552 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2025-06-04 | 2025-06-07 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TMP-551 | Functional_Testing | Task | Testing | To Do | 2025-06-04 | 2025-06-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration_SAP_Configured'}]
TMP-550 | Testing | Epic | [PILOT][TMP][SAP] | To Do | 2025-06-04 | 2025-07-06 |  | stephan.kuche |  | []
TMP-549 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2025-06-03 | 2025-06-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Document Outbound Configuration'}]
TMP-548 | Configure SAP Connector Document Transfer to workflow | Sub-task | Document Outbound Configuration | To Do | 2025-05-20 | 2025-06-03 |  | stephan.kuche |  | []
TMP-547 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2025-05-20 | 2025-06-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration_SAP_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-546 | Configuration Support MD PO | Sub-task | Master_Data_Inbound_Configuration | To Do | 2025-05-20 | 2025-05-21 |  | stephan.kuche |  | []
TMP-545 | Master_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-05-20 | 2025-05-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-544 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2025-05-20 | 2025-05-21 |  | stephan.kuche |  | []
TMP-543 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2025-05-20 | 2025-05-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Integration Rules Implementation'}]
TMP-542 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2025-05-19 | 2025-05-20 |  | stephan.kuche |  | []
TMP-541 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2025-05-19 | 2025-05-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Master_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
TMP-540 | Configure Email forwarding or redirecting | Sub-task | Document Inbound Configuration | To Do | 2025-05-19 | 2025-05-21 | CUS to create rules and test | stephan.kuche |  | []
TMP-539 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2025-05-19 | 2025-05-21 |  | stephan.kuche |  | []
TMP-538 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2025-05-19 | 2025-05-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}]
TMP-537 | Integration Implementation | Epic | [PILOT][TMP][SAP] | To Do | 2025-05-19 | 2025-06-04 |  | stephan.kuche |  | []
TMP-536 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | []
TMP-535 | CreatePO Line Config or add agentic workflow to config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | []
TMP-534 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-533 | Create Composite Enrichment in Step Company MD or add agentic workflow to config | Sub-task | Company_Master_Data_Enrichment | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | []
TMP-532 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-531 | Create Composite Enrichment in Step Supplier MD or add agentic workflow to config | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | []
TMP-530 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-529 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-528 | Add Costcenter Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-527 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-526 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-525 | Add GL Account Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-524 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-523 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-522 | Add Approver Prediction Agent/Prompt to Config | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | []
TMP-521 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2025-05-13 | 2025-05-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}]
TMP-520 | Extraction Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | []
TMP-519 | Perform Extraction Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | []
TMP-518 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | []
TMP-517 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | []
TMP-516 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | []
TMP-515 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-05-06 | 2025-05-13 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}]
TMP-514 | Add LLM to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2025-05-05 | 2025-05-06 |  | stephan.kuche |  | []
TMP-513 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2025-05-05 | 2025-05-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TMP-512 | Machine Learning | Epic | [PILOT][TMP][SAP] | To Do | 2025-05-05 | 2025-05-20 |  | stephan.kuche |  | []
TMP-511 | MileStone_Studio_Configured | Task | Application Implementation | To Do | 2025-05-18 | 2025-05-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}]
TMP-510 | Configure Insights Dashboards | Sub-task | Hypatos_Insights_Configuration | To Do | 2025-05-17 | 2025-05-18 | Insights Standard Collections | stephan.kuche |  | []
TMP-509 | Hypatos_Insights_Configuration | Task | Application Implementation | To Do | 2025-05-17 | 2025-05-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Studio_Configured'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}]
TMP-508 | Configure Schema accroding to datapoint_list | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-507 | Configure Translation Service | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-506 | Create LLM Config | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-505 | Configure ReRouting Rules | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-504 | Create projects and assignment of users and models | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-503 | Add Users to Studio ( according to roles ) | Sub-task | Hypatos_Studio_Configuration | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | []
TMP-502 | Hypatos_Studio_Configuration | Task | Application Implementation | To Do | 2025-05-05 | 2025-05-17 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Insights_Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TMP-501 | Application Implementation | Epic | [PILOT][TMP][SAP] | To Do | 2025-05-05 | 2025-05-19 |  | stephan.kuche |  | []
TMP-500 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2025-05-04 | 2025-05-05 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypatos_Studio_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Pre_trained_AI_Extraction_Model'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TMP-499 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-498 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-497 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-496 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-495 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-494 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-493 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-492 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-491 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-490 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TMP-489 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-488 | Add Normalisation, Validation, Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-487 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | []
TMP-486 | Functional & Technical Solution Design | Task | Design | To Do | 2025-04-20 | 2025-05-04 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}]
TMP-485 | Design | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-20 | 2025-05-05 |  | stephan.kuche |  | []
TMP-484 | MileStone_AI_Model_Training_Data_Confirmation | Task | Assessment | To Do | 2025-04-19 | 2025-04-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TMP-483 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-482 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-481 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | CUS Deliverable | stephan.kuche |  | []
TMP-480 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | CUS Deliverable | stephan.kuche |  | []
TMP-479 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Requirement Gathering Deliverable | stephan.kuche |  | []
TMP-478 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-477 | Perform Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TMP-476 | Prepare Assessment Workshop | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Update questions, Slidedeck | stephan.kuche |  | []
TMP-475 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TMP-474 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TMP-473 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TMP-472 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | ERP PO data | stephan.kuche |  | []
TMP-471 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | ERP master data | stephan.kuche |  | []
TMP-470 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2025-04-02 | 2025-04-19 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TMP-469 | Requirement Analysis | Task | Assessment | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_AI_Model_Training_Data_Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TMP-468 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TMP-467 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-466 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-465 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-464 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-463 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-462 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-461 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-460 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-459 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-458 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-457 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-456 | Create QA Project | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-455 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-454 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-453 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-452 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-451 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-450 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 | (Install and Service Packages) | stephan.kuche |  | []
TMP-449 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-448 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 | (R3, S4Hana) | stephan.kuche |  | []
TMP-447 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-446 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-445 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 | [TEST] | stephan.kuche |  | []
TMP-444 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-443 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | []
TMP-442 | Data Acquisition | Task | Assessment | To Do | 2025-04-02 | 2025-04-19 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Kickoff Workshop'}]
TMP-441 | Assessment | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-02 | 2025-04-20 |  | stephan.kuche |  | []
TMP-440 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2025-04-01 | 2025-04-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TMP-439 | Schedule Workshops (Discovery, Technical, Solution Design) | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-438 | Allocate_Time_for_Tests_Testing team UAT | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | CUS | stephan.kuche |  | []
TMP-437 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TMP-436 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable (monthly) | stephan.kuche |  | []
TMP-435 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-434 | Create Solution Design Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-433 | Create Discovery Workshop Slidedeck | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-432 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-431 | Create Project timeline | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-430 | Create RAID Log | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-429 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-428 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-427 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-426 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-425 | Teams Channel & Page Setup | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-424 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-423 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-422 | Create Absence Planner | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-421 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | Including all relevant Files | stephan.kuche |  | []
TMP-420 | Create Confluence Space and update Documentation | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | Included in Handover from Sales | stephan.kuche |  | []
TMP-419 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-418 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2025-04-01 | 2025-07-20 | PM Deliverable | stephan.kuche |  | []
TMP-417 | Project Set up | Task | Project Management | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-416 | JourFix | Sub-task | Meetings | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-415 | SteerCo | Sub-task | Meetings | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-414 | Adhoc | Sub-task | Meetings | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-413 | Meetings | Task | Project Management | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-412 | Project Management | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-411 | Milestone_Usertraining_completed | Task | User Training | To Do | 2025-07-20 | 2025-07-21 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TMP-410 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-409 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-408 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-407 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-406 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 | recommendations to improve model performance | stephan.kuche |  | []
TMP-405 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-404 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-403 | Provide UserList | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-402 | Request UserList | Sub-task | User Onboarding | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | []
TMP-401 | User Onboarding | Task | User Training | To Do | 2025-04-01 | 2025-07-20 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TMP-400 | User Training | Epic | [PILOT][TMP][SAP] | To Do | 2025-04-01 | 2025-07-21 |  | stephan.kuche |  | []
TMP-399 | [PILOT][TMP][SAP] | Project | TMP | To Do | 2025-04-01 | 2025-08-01 |  | stephan.kuche |  | []
TMP-1 | TMP | Account |  | To Do |  |  |  | stephan.kuche |  | []