## Slide 1: Next Generation AI for Document Automation – Accounts Payables
Weekly Report CW
January 2024
#placeholder

## Slide 3: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 4: Risks – Focus on Open / In Response
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Open at | Id | Description | Priority | Action Id | Action Description | Action Responsible | Action Status
Open | 2024-01-10 | R001 | Data Acquisition dependent on SAP addon release and installation - could break project timeline | High | A001 | KTM SAP DEV Team onboarding for integration implementation. KTM PM to raise ressource request to the respective team and actively following up. |  | Open
Open | 2024-01-10 | R002 | xSuite integration might take more ressources than expected | High | A002 | Discuss Solution Design extensively and support if needed |  | Open
 |  |  |  | High | A003 | Hypatos x KTM to revisit Integration and Project Timelines based on resource onboarding. Dependent on A001. Bi-Weekly follow ups. |  | Open
 |  |  |  | High | A004 | Allow a buffer for SIT |  | Open
Open | 2024-01-10 | R003 | PO Matching config and ML Training takes more ressources than expected | High | A005 | Schedule a session with HY SAP and Product Team to |  | Open
Open | 2024-01-10 | R004 | Poor PO Matching Enrichment Quality | Medium | A006 | Ensure that annoation of Line item is done right by providing annotation guideline |  | Open
Open | 2024-01-10 | R005 | Scope of Implementation not clear - customer expectations are not aligned with HY | High | A007 | Create and Sign SoW |  | Open
Open | 2024-01-10 | R006 | Projekt Closing Date not able to achieve due to vacation of important stakeholders | Medium | A008 | Create Absence Planning and Backups for PMs and Key Stakeholders |  | Open
* Update since last week Live Update

## Slide 5: Issues
RAID (Risks, Actions, Issues & Decisions) Follow-up
Status | Opened at | Closed at | Id | Description | Priority | Risk Id | Risk Description | Action Id | Action Description | Action Status
* Update since last week Live Update

## Slide 6: Decisions
RAID (Risks, Actions, Issues & Decisions) Follow-up
Id | Decision Detail | Decision Impact | Decision Date | Proposed by | Approved by | Alternatives Considered
D001​ |  |  |  |  |  | 
D002​ |  |  |  |  |  | 
D003​ |  |  |  |  |  | 
D004​ |  |  |  |  |  | 
* Update since last week Live Update

## Slide 7: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 8: Weekly Report –
-
  …
Achievements
G
…
Next Steps
Projects Status & Timeline Review
#CWPlaceHolder

## Slide 9: Indicative Timeline to evaluate Hypatos AccountingGPT potential with target Go Live in April 2024
Project Status & Timeline Review
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
50
51
52
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
  Responsible
  HY
Application Implement. (Studio Configuration)
  HY
ML Model Training & Optimization
  CUS & HY
Design of New AP Process
  CUS & HY
SoW & Solution Design Confirmation
  Label
Data Acquisition & Requirement Analysis
Activities
Testing (FT & SIT & UAT)
  CUS & HY
User Onboarding
Go-live Q&A
Leverage User Experience
User Onboarding
  CUS & HY
Project Setup & Mgmt
  Label
Kickoff 20.12.
Wave 2 (CompCode xx – xx)
Continuation decision
System Integration Implementation
Go-live Data decision
  CUS & HY
  CUS & HY
Today 09.02.
Wave 1 (CompCode xx – xx)
UAT approved
GO Live Decision
Technical Workshop
SIT Approved
  CUS & HY
Functional Workshop
Go-live & Hypercare & Continuous Improvement
Hypercare Closing
Handover Customer Care
Assessment Workshop
Implementation Phase (2-3 months)
CW
Go Live
Training Data Confirmation
Milestone
Meeting
SOW = Statement of Work FT= Functional Testing
SIT= System Integration Testing
UAT= User Acceptance Testing
Timeline subject to change – pending on Assessment, Functional & Technical Workshops outcomes
Deployment
& Roll-out
Configure AI
Implementation
Design & Assessment
PMO & User Training
Testing

## Slide 10: Agenda
Project Status & Timeline Review
RAID (Risks, Actions, Issues & Decisions) Follow-up
Highlight Topics

## Slide 11: Thank you
Stephan Kuche
Sr. Implementation Manager
stephan.kuche@hypatos.ai
+49 179 340 36 49
hypatos.ai
Lucia Ferreiro Martinez
Sr. Customer Success Manager
lucia.ferreiro.martinez@hypatos.ai
+49 176 73573508
hypatos.ai
Dr. Ulrich Erxleben
Chief Executive Officer
uli.erxleben@hypatos.ai +49 157 736 362 22 hypatos.ai