## Sheet1
Summary | IssueType | Parent | SummaryName | Blocks | Description | Duration
Roll-out_Wilhelmsen | Project
0_Project_Management | Epic | Roll-out_Wilhelmsen
0_1_-_Update_all_related_dates_in_this_project | Task | 0_Project_Management |  |  |  | 1
0_2_-_Update_roll-out_plan | Task | 0_Project_Management |  |  | File : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/PMO/Rollout%20Plan?csf=1&web=1&e=eIf44E | 1
0_3_-_Internal_meetings | Task | 0_Project_Management |  |  | Task to log general internal meetings | 10
1_Process_Discovery | Epic | Roll-out_Wilhelmsen
1_1_-_Data_Acquisition | Task | 1_Process_Discovery | 1_1_-_Data_Acquisition | 1_2_-_Requirement_Gathering |  | 3
Training_&_Posting_Data_Request | Sub-task | 1_1_-_Data_Acquisition
Posting_Data_Analysis | Sub-task | 1_1_-_Data_Acquisition |  |  | Analyze posting data and determine top suppliers (>90% coverage)
Training_Data_Assessment | Sub-task | 1_1_-_Data_Acquisition |  |  | Check if all top suppliers has sample documents with specified naming convention
Request_additional_documents_if_required | Sub-task | 1_1_-_Data_Acquisition |  |  | Request if any top supplier document is missing
Training_Data/Document_Set_Preparation | Sub-task | 1_1_-_Data_Acquisition |  |  | Prepare training, annotation documents
Match_training_documents_with_posting_data | Sub-task | 1_1_-_Data_Acquisition |  |  | Match selected documents with posting data
1_2_-_Requirement_Gathering | Task | 1_Process_Discovery | 1_2_-_Requirement_Gathering | 2_1_-_Capturing_Model_Training,2_2_-_Enrichment_Model_Training |  | 3
Provide_Digitalization_Details_form_to_Local_Finance_Team_and_ask_examples_for_Edge_cases | Sub-task | 1_2_-_Requirement_Gathering |  |  | EXAMPLE DOCUMENT https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop/Digitalization%20details%20for%20Hypatos_Country.xlsx?d=w1f4142a7ac7a4094a18dd8c9455cf25d&csf=1&web=1&e=DJWR4y
Provide_Assessment_Gathering__and_Training__Data__Folders | Sub-task | 1_2_-_Requirement_Gathering |  |  | Assessment Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/2.%20-%20Workshops/Assessment%20Workshop Training Data Folders : https://wilhelmsen.sharepoint.com/:f:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design%202024/Training%20Data
(ML)_Demo_Project_Creation_for_Requirements_Gathering_Meeting | Sub-task | 1_2_-_Requirement_Gathering |  |  | Take the example from (ML) Project - (OC Entities)(Phase 3) Oman
Requirement_Gathering_Meeting | Sub-task | 1_2_-_Requirement_Gathering
Request_examples_for_Edge_cases | Sub-task | 1_2_-_Requirement_Gathering
Complete_full_set-up_of_training_data_for_all_of_the_top_suppliers_with_Edge_cases_shared_during_requirements_session | Sub-task | 1_2_-_Requirement_Gathering
Update_WHL_Requirement_List | Sub-task | 1_2_-_Requirement_Gathering |  |  | https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Requirement_Gathering_Finalization | Sub-task | 1_2_-_Requirement_Gathering
2_Model_Training | Epic | Roll-out_Wilhelmsen
2_1_-_Capturing_Model_Training | Task | 2_Model_Training | 2_1_-_Capturing_Model_Training | 2_3_-_Model_Fine_Tuning |  | 3
Create_baseline_(groundtruth)_project_to_annotate_(ML) | Sub-task | 2_1_-_Capturing_Model_Training |  |  | Take the example from (ML) Project - NZ_Annotation
Upload_documents_selected_for_annotation_to_groundtruth_project_(Top_suppliers_and_Edge_cases) | Sub-task | 2_1_-_Capturing_Model_Training
Create_a_task_for_annotation_(add_details_per_requirements) | Sub-task | 2_1_-_Capturing_Model_Training
Validate_annotation_results_with_posting_data | Sub-task | 2_1_-_Capturing_Model_Training
Improve_annotation_quality_based_on_validation_with_posting_data | Sub-task | 2_1_-_Capturing_Model_Training
Create_Training__Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training |  |  | Take the example from(ML) Project - (Training)(PROD)(NZ)
Upload_selected_training_documents_from_baseline_project_to_Training_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training
Create__QA_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training |  |  | Take the example from (ML) Project - (QA) NZ
Configure_QA_project_with_Composite_Enrichment_Index | Sub-task | 2_1_-_Capturing_Model_Training
Create_LLM_Prompting_Service_(ML) | Sub-task | 2_1_-_Capturing_Model_Training
Upload_baseline_(groundtruth)_documents_to_QA_Project_(ML) | Sub-task | 2_1_-_Capturing_Model_Training
Create_Error_Analysis_Dashboard | Sub-task | 2_1_-_Capturing_Model_Training
Analyze_QA_results_and_accuracy | Sub-task | 2_1_-_Capturing_Model_Training
2_2_-_Enrichment_Model_Training | Task | 2_Model_Training |  |  |  | 1
Create_IMP_training_project_(TEST) | Sub-task | 2_2_-_Enrichment_Model_Training
Contact_with_IM_to_enable_IMP_pipeline | Sub-task | 2_2_-_Enrichment_Model_Training
Upload_documents_to_IMP_training_project | Sub-task | 2_2_-_Enrichment_Model_Training
Train_suppliers_using_documents_uploaded_to_IMP_project | Sub-task | 2_2_-_Enrichment_Model_Training
2_3_-_Model_Fine_Tuning | Task | 2_Model_Training | 2_3_-_Model_Fine_Tuning | 3_1_-_Create_Projects_(TEST) |  | 1
Improve/Optimize__LLM_Prompting_Service_prompt_with_Error_Analysis_results | Sub-task | 2_3_-_Model_Fine_Tuning
Add_additional_suppliers_to_IMP_project_if_required | Sub-task | 2_3_-_Model_Fine_Tuning
3_Studio_Configuration | Epic | Roll-out_Wilhelmsen
3_1_-_Create_Projects_(TEST) | Task | 3_Studio_Configuration | 3_1_-_Create_Projects_(TEST) | 3_2_-_Configure_Projects_(TEST) |  | 1
Configure_project_schema_with_agreed_upon_requirements_lists_points | Sub-task | 3_1_-_Create_Projects_(TEST)
Add/Change_accounting_supplier/customer__party | Sub-task | 3_1_-_Create_Projects_(TEST)
Add/Change__company_name_validation | Sub-task | 3_1_-_Create_Projects_(TEST)
Add/check_vat_id_validation | Sub-task | 3_1_-_Create_Projects_(TEST)
Check/change_duplicate_source_data_point | Sub-task | 3_1_-_Create_Projects_(TEST)
(Optional)_Add_translation_data_points_if_required | Sub-task | 3_1_-_Create_Projects_(TEST)
3_2_-_Configure_Projects_(TEST) | Task | 3_Studio_Configuration | 3_2_-_Configure_Projects_(TEST) | 4_1_-_Testing_Set-up |  | 1
Create_a_COE_ticket_to_configure_Rerouting_rules | Sub-task | 3_2_-_Configure_Projects_(TEST) |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
Contact_IM_for_composite_enrichment_set-up_configuration | Sub-task | 3_2_-_Configure_Projects_(TEST)
Contact_IM_to_create_and_configure_LLM_prompting_service | Sub-task | 3_2_-_Configure_Projects_(TEST)
Contact_IM_to_enable_newly_created_(TEST)_outbound_projects_for_duplicate_check_pipeline_(Connect_projects_to_IMP_pipeline) | Sub-task | 3_2_-_Configure_Projects_(TEST)
Contact_IM_to_add_outbound_projects_to_XML_UBL_21_endpoint_(TEST) | Sub-task | 3_2_-_Configure_Projects_(TEST)
Contact_IM_to_enable_translation_for_outbound_projects | Sub-task | 3_2_-_Configure_Projects_(TEST)
4_Testing | Epic | Roll-out_Wilhelmsen
4_1_-_Testing_Set-up | Task | 4_Testing | 4_1_-_Testing_Set-up | 4_2_-_Functional_Testing_by_HY |  | 1
Copy_and_update_Test_Workbook_for_new_phase_if_needed | Sub-task | 4_1_-_Testing_Set-up |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
4_2_-_Functional_Testing_by_HY | Task | 4_Testing | 4_2_-_Functional_Testing_by_HY | 4_3_-_Testing_by_Wilhelmsen |  | 1
Compare_project_set-up_with_requirements_list_for_specific_country | Sub-task | 4_2_-_Functional_Testing_by_HY |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Upload_documents_to_Gateway_project_and_test_routing | Sub-task | 4_2_-_Functional_Testing_by_HY
Test_advanced_duplicate_testing | Sub-task | 4_2_-_Functional_Testing_by_HY
Test_if_enrichment_is_working_properly_with_company_code_filter | Sub-task | 4_2_-_Functional_Testing_by_HY
Test_if_XML_endpoint_if_available_for_outbound_projects_(Postman) | Sub-task | 4_2_-_Functional_Testing_by_HY
(Optional)_Test_translation_feature | Sub-task | 4_2_-_Functional_Testing_by_HY
4_3_-_Testing_by_Wilhelmsen | Task | 4_Testing | 4_3_-_Testing_by_Wilhelmsen | 5_1_-_Create_Projects_(PROD) |  | 3
Add_projects_to_Requirements_List | Sub-task | 4_3_-_Testing_by_Wilhelmsen
Share_Test_Workbook | Sub-task | 4_3_-_Testing_by_Wilhelmsen |  |  | Example Workbook: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Testing/20240219_WILH_TestWorkbook.xlsx?d=w69cb18348f0b4ca7b8673d2b6069bc2d&csf=1&web=1&e=XKhJvy
Wilhelmsen_to_configure_integration_&_perform_System_Integration_Testing_(SIT) | Sub-task | 4_3_-_Testing_by_Wilhelmsen
Wilhelmsen_to_perform_Functional_Testing | Sub-task | 4_3_-_Testing_by_Wilhelmsen
Wilhelmsen_to_perform_User_Acceptance_Testing_(UAT) | Sub-task | 4_3_-_Testing_by_Wilhelmsen
Testing_Support_Tasks_(Issue_Resolution) | Sub-task | 4_3_-_Testing_by_Wilhelmsen
Analysis_&_Finalization_of_Tests | Sub-task | 4_3_-_Testing_by_Wilhelmsen
5_Deployment_to_Production | Epic | Roll-out_Wilhelmsen
5_1_-_Create_Projects_(PROD) | Task | 5_Deployment_to_Production | 5_1_-_Create_Projects_(PROD) | 5_2_-_Configure_Projects_(PROD) |  | 1
Configure_project_schema_with_agreed_upon_requirements_lists_points | Sub-task | 5_1_-_Create_Projects_(PROD)
Check_accounting_supplier/customer__party | Sub-task | 5_1_-_Create_Projects_(PROD)
Check__company_name_validation | Sub-task | 5_1_-_Create_Projects_(PROD)
Check_Vat_Id_validation | Sub-task | 5_1_-_Create_Projects_(PROD)
Check__duplicate_source_data_point | Sub-task | 5_1_-_Create_Projects_(PROD)
(Optional)_Check__translation_data_points_if_required | Sub-task | 5_1_-_Create_Projects_(PROD)
5_2_-_Configure_Projects_(PROD) | Task | 5_Deployment_to_Production | 5_2_-_Configure_Projects_(PROD) | 5_3_-_Smoke_test |  | 1
Create_a_COE_ticket_to_configure_Rerouting_rules | Sub-task | 5_2_-_Configure_Projects_(PROD) |  |  | Example task : https://hypatos.atlassian.net/browse/WHL-825
Contact_IM_for_composite_enrichment_set-up_configuration | Sub-task | 5_2_-_Configure_Projects_(PROD)
Contact_IM_to_create_and_configure_LLM_prompting_service | Sub-task | 5_2_-_Configure_Projects_(PROD)
Contact_IM_to_enable_newly_created_(PROD)_outbound_projects_for_duplicate_check_pipeline_(Connect_projects_to_IMP_pipeline) | Sub-task | 5_2_-_Configure_Projects_(PROD)
Contact_IM_to_add_outbound_projects_to_XML_UBL_21_endpoint_(PROD) | Sub-task | 5_2_-_Configure_Projects_(PROD)
Contact_IM_to_enable_translation_for_outbound_projects | Sub-task | 5_2_-_Configure_Projects_(PROD)
5_3_-_Smoke_test | Task | 5_Deployment_to_Production | 5_3_-_Smoke_test | 5_4_-_Cutover_and_Go_Live |  | 1
Compare_project_set-up_with_(TEST)_project | Sub-task | 5_3_-_Smoke_test
Upload_documents_to_Gateway_project_and_test_routing | Sub-task | 5_3_-_Smoke_test
Test_advanced_duplicate_testing | Sub-task | 5_3_-_Smoke_test
Test_if_enrichment_is_working_properly_with_company_code_filter | Sub-task | 5_3_-_Smoke_test
Test_if_XML_endpoint_if_available_for_outbound_projects_(Postman) | Sub-task | 5_3_-_Smoke_test
(Optional)_Test_translation_feature | Sub-task | 5_3_-_Smoke_test
5_4_-_Cutover_and_Go_Live | Task | 5_Deployment_to_Production | 5_4_-_Cutover_and_Go_Live | 6_1_-_Hypercare_Issues |  | 1
Create_and_share_cutover_Plan | Sub-task | 5_4_-_Cutover_and_Go_Live |  |  | Example File : https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/General/3.%20-%20Go%20Live/20240321%20WILH%20Cut-Over%20Plan.xlsx?d=we02eb91a059b4632ace3cf0acc7f696a&csf=1&web=1&e=RxxUQ7
Add_projects_to_Requirements_List | Sub-task | 5_4_-_Cutover_and_Go_Live |  |  | Requirements Sheet: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Solution%20Design/Datapoint_Requirements/20230803%20WHL%20Requirement%20List.xlsx?d=wa1d0a15e28594d848e8def48ff3796e2&csf=1&web=1&e=hxnCwT
Inform_customer_for_Production_Readiness_&__initiate_Production_deployment | Sub-task | 5_4_-_Cutover_and_Go_Live
6_Hypercare_Phase | Epic | Roll-out_Wilhelmsen
6_1_-_Hypercare_Issues | Task | 6_Hypercare_Phase | 6_1_-_Hypercare_Issues | 6_2_-_Handover_to_Hypatos_Customer_Care |  | 5
Create_and_share_Hypercare_Issue_Log | Sub-task | 6_1_-_Hypercare_Issues |  |  | Example File: https://wilhelmsen.sharepoint.com/:x:/r/sites/Wilhelmsen-HypatosDigitalization/Shared%20Documents/Hypercare%20after%20v1.0%20release/Hypercare%20Issue%20Log.xlsx?d=wfe2e122f9ba146bdaef47f39241aef7e&csf=1&web=1&e=Q4aEIk
Hypercare_issue_resolutions | Sub-task | 6_1_-_Hypercare_Issues
6_2_-_Handover_to_Hypatos_Customer_Care | Task | 6_Hypercare_Phase | 6_2_-_Handover_to_Hypatos_Customer_Care | 7_1_-_Update_initial_design_sign-off_if_needed,7_2_-_Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint |  | 1
Update_CC_Handover_Page | Sub-task | 6_2_-_Handover_to_Hypatos_Customer_Care
7_Documentation_Update | Epic | Roll-out_Wilhelmsen
7_1_-_Update_initial_design_sign-off_if_needed | Task | 7_Documentation_Update |  |  |  | 1
7_2_-_Syncronize_Wilhelmsen_Sharepoint_with_Hypatos_Sharepoint | Task | 7_Documentation_Update |  |  |  | 1