## IssueOverview
IssueKey | Summary | IssueType | ParentSummary | Status | StartDate | DueDate | Description | Assignee | ExternalAssignee | IssueLinks
TD-5425 | Create lessons learned page | Sub-task | Lessons learned | To Do | 2024-10-19 | 2024-10-20 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5424 | Lessons learned | Task | Delivery | To Do | 2024-10-19 | 2024-10-20 |  | stephan.kuche |  | []
TD-5423 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-10-18 | 2024-10-19 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Create lessons learned page '}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5422 | Create Handover to CC page | Sub-task | Hypercare_Phase | To Do | 2024-09-27 | 2024-10-18 |  | stephan.kuche |  | []
TD-5421 | Allocate time for Hypercare Issue Handling | Sub-task | Hypercare_Phase | To Do | 2024-09-27 | 2024-10-18 |  | stephan.kuche |  | []
TD-5420 | Hypercare_Phase | Task | Delivery | To Do | 2024-09-27 | 2024-10-18 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5419 | MileStone_Go Live | Task | Delivery | To Do | 2024-09-26 | 2024-09-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5418 | Introduction Session to Hypercare Process | Sub-task | Deployment | To Do | 2024-09-24 | 2024-09-26 |  | stephan.kuche |  | []
TD-5417 | Create and Share Hypercare Issuelog | Sub-task | Hypercare_Phase | To Do | 2024-09-27 | 2024-10-18 |  | stephan.kuche |  | []
TD-5416 | Cutover and Go Live | Sub-task | Deployment | To Do | 2024-09-24 | 2024-09-26 |  | stephan.kuche |  | []
TD-5415 | Create and share the Cutover plan | Sub-task | Deployment | To Do | 2024-09-24 | 2024-09-26 |  | stephan.kuche |  | []
TD-5414 | Configure reporting notifications audience and cadence | Sub-task | Deployment | To Do | 2024-09-24 | 2024-09-26 |  | stephan.kuche |  | []
TD-5413 | Deployment | Task | Delivery | To Do | 2024-09-24 | 2024-09-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5412 | Delivery | Epic | Pilot | To Do | 2024-09-24 | 2024-10-20 |  | stephan.kuche |  | []
TD-5411 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-09-23 | 2024-09-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5410 | Present Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-09-02 | 2024-09-23 |  | stephan.kuche |  | []
TD-5409 | Create Results Overview Slidedeck | Sub-task | User Acceptance Testing | To Do | 2024-09-02 | 2024-09-23 |  | stephan.kuche |  | []
TD-5408 | Run Studio UAT | Sub-task | User Acceptance Testing | To Do | 2024-09-02 | 2024-09-23 |  | stephan.kuche |  | []
TD-5407 | Run Model UAT | Sub-task | User Acceptance Testing | To Do | 2024-09-02 | 2024-09-23 |  | stephan.kuche |  | []
TD-5406 | User Acceptance Testing | Task | Testing | To Do | 2024-09-02 | 2024-09-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT_approval'}]
TD-5405 | MileStone_SIT_approval | Task | Testing | To Do | 2024-09-01 | 2024-09-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5404 | Regression testing of E2E flow in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | []
TD-5403 | Document Inbound and outbound penny test in PROD env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | []
TD-5402 | Document Inbound and outbound penny test in TEST env | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | []
TD-5401 | Run Masterdata Test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | []
TD-5400 | Run Document Outbound Configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5399 | Run Posting data inbound configuration load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5398 | Run Document Inbound load test | Sub-task | System Integration Test (E2E) | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | []
TD-5397 | System Integration Test (E2E) | Task | Testing | To Do | 2024-08-25 | 2024-09-01 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT_approval'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5396 | CUS to perform funct. Testing | Sub-task | Functional_Testing | To Do | 2024-08-22 | 2024-08-25 |  | stephan.kuche |  | []
TD-5395 | Hy to perform funct testing | Sub-task | Functional_Testing | To Do | 2024-08-22 | 2024-08-25 |  | stephan.kuche |  | []
TD-5394 | Share Testplan Workbook and QandA Session | Sub-task | Functional_Testing | To Do | 2024-08-22 | 2024-08-25 |  | stephan.kuche |  | []
TD-5393 | Create testing plan workbook | Sub-task | Functional_Testing | To Do | 2024-08-22 | 2024-08-25 | PM Deliverable - including teststrategy, testplan and testsummary, uat findings, report, exit report | stephan.kuche |  | []
TD-5392 | Functional_Testing | Task | Testing | To Do | 2024-08-22 | 2024-08-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5391 | Testing | Epic | Pilot | To Do | 2024-08-22 | 2024-09-24 |  | stephan.kuche |  | []
TD-5390 | Configure derived datapoints | Sub-task | Schema Configuration | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5389 | Configure validation rules | Sub-task | Schema Configuration | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5388 | Configure normalisation rules | Sub-task | Schema Configuration | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5387 | Update list of datapoints | Sub-task | Schema Configuration | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5386 | Add Composite Enrichment Id to Schema | Sub-task | Schema Configuration | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5385 | Schema Configuration | Task | Application Implementation | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5384 | Configure Translation Service | Sub-task | Studio Configuration | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5383 | Create LLM Config | Sub-task | Studio Configuration | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5382 | Configure ReRouting Rules | Sub-task | Studio Configuration | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5381 | Create projects and assignment of users and models | Sub-task | Studio Configuration | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5380 | Add Users to Studio ( according to roles ) | Sub-task | Studio Configuration | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5379 | Studio Configuration | Task | Application Implementation | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5378 | Configure Error Analysis Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-08-08 | 2024-08-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5377 | Configure QA Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-08-08 | 2024-08-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5376 | Configure Model Insights Dashboard | Sub-task | Reporting and Monitoring Configuration | To Do | 2024-08-08 | 2024-08-09 | Insights Standard Collections for Reporting and Monitoring | stephan.kuche |  | []
TD-5375 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-08-08 | 2024-08-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5374 | Application Implementation | Epic | Pilot | To Do | 2024-08-08 | 2024-08-22 |  | stephan.kuche |  | []
TD-5373 | Integration_API_Configured | Task | Integration Implementation | To Do | 2024-07-01 | 2024-07-22 | CUS to create an API client | stephan.kuche |  | []
TD-5372 | Integration_Coupa_Configured | Task | Integration Implementation | To Do | 2024-07-01 | 2024-07-04 |  | stephan.kuche |  | []
TD-5371 | Integration_SAP_Configured | Task | Integration Implementation | To Do | 2024-07-01 | 2024-07-04 |  | stephan.kuche |  | []
TD-5370 | Integration_Boomi_Configured | Task | Integration Implementation | To Do | 2024-07-01 | 2024-07-04 |  | stephan.kuche |  | []
TD-5369 | Middleware Configuration Support | Sub-task | Integration Rules Implementation | To Do | 2024-08-08 | 2024-08-09 |  | stephan.kuche |  | []
TD-5368 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-08-08 | 2024-08-09 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5367 | API Configuration Support PO | Sub-task | PO_Data_Inbound_Configuration | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5366 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5365 | API Configuration Support PDIB | Sub-task | Posting_Data_Inbound_Configuration | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5364 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5363 | API Configuration Support OB | Sub-task | Document Outbound Configuration | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5362 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5361 | Support API Configuration | Sub-task | Document Inbound Configuration | To Do | 2024-08-08 | 2024-08-11 |  | stephan.kuche |  | []
TD-5360 | Add Inbound Projects (ids and emailaddress) to Project List | Sub-task | Document Inbound Configuration | To Do | 2024-08-08 | 2024-08-11 |  | stephan.kuche |  | []
TD-5359 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-08-08 | 2024-08-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5358 | Integration Implementation | Epic | Pilot | To Do | 2024-07-01 | 2024-08-11 |  | stephan.kuche |  | []
TD-5357 | Create Composite Enrichment in Step PO | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5356 | CreatePO Line Config | Sub-task | PO_LINE_Matching_Enrichment | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5355 | PO_LINE_Matching_Enrichment | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5354 | Create Composite Enrichment in Step Company MD | Sub-task | Company_Master_Data_Enrichment | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5353 | Company_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5352 | Create Composite Enrichment in Step Supplier MD | Sub-task | Supplier_Master_Data_Enrichment | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | []
TD-5351 | Supplier_Master_Data_Enrichment | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5350 | Deploy CoElement_Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5349 | QA CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5348 | Train CoElement Model | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5347 | Create CoElement Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_COElement | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5346 | Attribute_Prediction_Model_Configuration_COElement | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5345 | Deploy CostCenter_Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5344 | QA CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5343 | Train CostCenter Model | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5342 | Create CostCenter Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_CostCenter | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5341 | Attribute_Prediction_Model_Configuration_CostCenter | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5340 | Deploy GlAccount_Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5339 | QA GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5338 | Train GlAccount Model | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5337 | Create GlAccount Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_GL_Account | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5336 | Attribute_Prediction_Model_Configuration_GL_Account | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5335 | Deploy Approver_Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5334 | QA Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5333 | Train Approver Model | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5332 | Create Approver Model Ticket | Sub-task | Attribute_Prediction_Model_Configuration_Approver | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | []
TD-5331 | Attribute_Prediction_Model_Configuration_Approver | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-15 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5330 | Capturing Model Deployment | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5329 | Capturing Model Evaluation | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5328 | Perform Capturing Model Results Analysis | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5327 | Perform Capturing Model QA | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5326 | Annotate Documents | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5325 | Copy documents to in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5324 | Create Annotation in Context Learning Project | Sub-task | Custom_trained_AI_Extraction_Model | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | []
TD-5323 | Custom_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-08-08 | 2024-08-29 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}]
TD-5322 | Add Capturing Model to Project | Sub-task | Pre_trained_AI_Extraction_Model | To Do | 2024-07-01 | 2024-07-22 |  | stephan.kuche |  | []
TD-5321 | Pre_trained_AI_Extraction_Model | Task | Machine Learning | To Do | 2024-07-01 | 2024-07-22 |  | stephan.kuche |  | []
TD-5320 | Machine Learning | Epic | Pilot | To Do | 2024-07-01 | 2024-08-29 |  | stephan.kuche |  | []
TD-5319 | MileStone_SoW and Solution Design Sign-Off | Task | Design | To Do | 2024-08-07 | 2024-08-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Custom_trained_AI_Extraction_Model'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_Approver'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_GL_Account'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_CostCenter'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Attribute_Prediction_Model_Configuration_COElement'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Supplier_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Company_Master_Data_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_LINE_Matching_Enrichment'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Posting data inbound configuration load test'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Run Document Outbound Configuration load test'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}]
TD-5318 | Create Solution Design Proposal | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5317 | Update SoW | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5316 | Document reporting and monitoring concept | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5315 | ReportingandMonitoring Design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5314 | Create Integration rules | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5313 | Create Technical Datapoint Mapping | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5312 | Posting Data Inbound Integration Documentation | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5311 | Document Outbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5310 | Document Inbound Configuration Integration | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5309 | Create Studio companies and projects concept design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5308 | List of users and roles (permissions) | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 | CUS Deliverable - Customer to provide List of Users | stephan.kuche |  | []
TD-5307 | Create EndUSer Process design | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5306 | Add Derivation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5305 | Add Validation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5304 | Add Normalisation Rules to Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5303 | Create and populate Datapoint Template | Sub-task | Functional & Technical Solution Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | []
TD-5302 | Functional & Technical Solution Design | Task | Design | To Do | 2024-07-24 | 2024-08-07 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Sign-Off'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5301 | Design | Epic | Pilot | To Do | 2024-07-24 | 2024-08-08 |  | stephan.kuche |  | []
TD-5300 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-07-23 | 2024-07-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional & Technical Solution Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5299 | Perform Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5298 | Prepare Technical Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5297 | Prepare Sample Documents for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | CUS Deliverable | stephan.kuche |  | []
TD-5296 | Prepare Business requirements for Custom Datapoints | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | CUS Deliverable | stephan.kuche |  | []
TD-5295 | Perform Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Requirement Gathering Deliverable | stephan.kuche |  | []
TD-5294 | Prepare Functional Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5293 | Perform Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Requirement Gathering Deliverable - Document Processing Workflow, Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5292 | Prepare Assessement Workshop | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Update questions, Slidedeck | stephan.kuche |  | []
TD-5291 | Perform System analysis | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Requirement Gathering Deliverable - Current P2P System Architecture / Integration Architecture, Architecture documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5290 | Create Document Processing Workflow | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Process documentation, Hypatos Studio Standard process template | stephan.kuche |  | []
TD-5289 | Perform Document analysis | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Documents (datapoints), Document types, document languages (regions) analysis | stephan.kuche |  | []
TD-5288 | Perform PO data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | ERP PO data | stephan.kuche |  | []
TD-5287 | Perform Master data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | ERP master data | stephan.kuche |  | []
TD-5286 | Posting data analysis | Sub-task | Requirement Analysis | To Do | 2024-07-06 | 2024-07-23 | Requirement Gathering Deliverable - ERP posting data, Hypatos Enrichment dashboard, Descriptive Statistics Analysis template | stephan.kuche |  | []
TD-5285 | Requirement Analysis | Task | Assessment | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5284 | Create Sample Dataset for ML Training | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 | Create a list of top vendorids, or companycodes in scope | stephan.kuche |  | []
TD-5283 | Data and documentation quality and completeness review | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5282 | Export Cost Center Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5281 | Export GL Account Data from Customer ERP | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5280 | Ingest Posting Data including Document Images via Ingestion Tool | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5279 | Transfer Posting Data including Document Images via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5278 | Transfer Supplier Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5277 | Transfer Purchase Order Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5276 | Transfer Company Master Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5275 | Ingest Master Data via Tool (Ingestion Tool) | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5274 | Transfer CostCenter Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5273 | Transfer GL Account Data via SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5272 | Create Basic LLM Config | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5271 | Create Basic CompEnrichment Config | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5270 | Create QA Project | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5269 | Create Training Data Project | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5268 | Create Training Data Schema | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5267 | Configure Coupa Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5266 | Install_Coupa_Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5265 | Schedule Coupa Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5264 | Send Coupa Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5263 | Configure SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5262 | Install SAP Addon | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5261 | Schedule SAP Addon FAQ Session | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 | invite SAP Basis and HY SAP engineers | stephan.kuche |  | []
TD-5260 | Send SAP Addon Documentation | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5259 | Send SAP Addon InstallationPackages | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 | (Install andService Packages SP1) | stephan.kuche |  | []
TD-5258 | Add CUS to SAP list, provide email for certificate renewal to devops | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5257 | Gather Information about current SAP system and Relevant Stakeholder for certificates | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 | (R3, S4Hana) | stephan.kuche |  | []
TD-5256 | Share apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5255 | Create apiv2 credentials | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5254 | Create Studio Company | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 | [TEST] | stephan.kuche |  | []
TD-5253 | Create DatapointList (Standard SAP Datapoints) | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5252 | Prepare and send out data and documentation request | Sub-task | Data Acquisition | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | []
TD-5251 | Data Acquisition | Task | Assessment | To Do | 2024-07-06 | 2024-07-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5250 | Assessment | Epic | Pilot | To Do | 2024-07-06 | 2024-07-24 |  | stephan.kuche |  | []
TD-5249 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-07-01 | 2024-07-02 |  | stephan.kuche |  | []
TD-5248 | Schedule Workshops (Technical WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5247 | Schedule Workshops (Functional WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5246 | Schedule Workshops (Assessment WS) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5245 | Schedule JourFixe Meeting | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable .- weekly / bi weekly ( Regular Project KPIs Reporting) | stephan.kuche |  | []
TD-5244 | Schedule Executive Status Meetings | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable (monthly) | stephan.kuche |  | []
TD-5243 | Create Technical Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5242 | Create Functional Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5241 | Create Assessment Workshop Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5240 | Create Kickoff Slidedeck | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5239 | Identification of project deliverables | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5238 | Create Project Plan | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5237 | Create Jira Advanced roadmap | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | Optional | stephan.kuche |  | []
TD-5236 | Create Project timeline | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5235 | Create RAID Log | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5234 | Grant Access to JWM Project (Int and ext SH) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5233 | Create Jira Work Mangagement Project | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5232 | Create JourFixe PMO and Steerco Series | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5231 | Grant Access to Hy Sharepoint and Teams | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5230 | Teams Page Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | Page with most relevant Links, StakeholderMapping and FAQ | stephan.kuche |  | []
TD-5229 | Teams Channel Setup | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5228 | Create Weekly Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5227 | Create Executive Report (based on template) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5226 | Create Absence Planner | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5225 | Sharepoint folder set-up | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | Including all relevant Files | stephan.kuche |  | []
TD-5224 | Document Project (confl.) | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5223 | Create Customer Documentation | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | Included in Handover from Sales | stephan.kuche |  | []
TD-5222 | Create Project Governance Structure | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5221 | Create StakeholderMapping and Matrix | Sub-task | Project Set up | To Do | 2024-07-01 | 2024-07-06 | PM Deliverable | stephan.kuche |  | []
TD-5220 | Project Set up | Task | Project Management | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5219 | Project Management | Epic | Pilot | To Do | 2024-07-01 | 2024-07-06 |  | stephan.kuche |  | []
TD-5218 | Milestone_Usertraining_completed | Task | User Training | To Do | 2024-10-29 | 2024-10-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Onboarding'}]
TD-5217 | Key User Introduction to Hypatos Change Requests | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5216 | Key User Admin Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5215 | Key User Reporting and Monitoring Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5214 | Insights Training and QandA | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5213 | Intro HY continual learning tech and QandA session | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 | recommendations to improve model performance | stephan.kuche |  | []
TD-5212 | Finish HY Academy Training | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5211 | Grant Access to HY Academy | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5210 | Provide UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5209 | Request UserList | Sub-task | User Onboarding | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | []
TD-5208 | User Onboarding | Task | User Training | To Do | 2024-07-01 | 2024-10-29 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Milestone_Usertraining_completed'}]
TD-5207 | User Training | Epic | Pilot | To Do | 2024-07-01 | 2024-10-30 |  | stephan.kuche |  | []
TD-5206 | Pilot | Project |  | To Do | 2024-07-01 | 2024-10-30 |  | stephan.kuche |  | []
TD-5205 | Lessons learned | Task | Delivery | To Do | 2024-08-01 | 2024-08-02 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}]
TD-5204 | MileStone_Hypercare Closing_Handover to Customer Care | Task | Delivery | To Do | 2024-07-31 | 2024-08-01 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Lessons learned'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Hypercare_Phase'}]
TD-5203 | Hypercare_Phase | Task | Delivery | To Do | 2024-06-28 | 2024-07-31 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Hypercare Closing_Handover to Customer Care'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Go Live'}]
TD-5202 | MileStone_Go Live | Task | Delivery | To Do | 2024-06-27 | 2024-06-28 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Hypercare_Phase'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Deployment'}]
TD-5201 | Deployment | Task | Delivery | To Do | 2024-06-25 | 2024-06-27 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Go Live'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}]
TD-5200 | Delivery | Epic | Pilot | To Do | 2024-06-25 | 2024-07-21 |  | stephan.kuche |  | []
TD-5199 | MileStone_UAT approved_Go Live decision | Task | Testing | To Do | 2024-06-24 | 2024-06-25 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Deployment'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'User Acceptance Testing'}]
TD-5198 | User Acceptance Testing | Task | Testing | To Do | 2024-06-03 | 2024-06-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_UAT approved_Go Live decision'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SIT approved'}]
TD-5197 | MileStone_SIT approved | Task | Testing | To Do | 2024-06-02 | 2024-06-03 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'User Acceptance Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'System Integration Test (E2E)'}]
TD-5196 | System Integration Test (E2E) | Task | Testing | To Do | 2024-05-26 | 2024-06-02 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SIT approved'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional_Testing'}]
TD-5195 | Functional_Testing | Task | Testing | To Do | 2024-05-23 | 2024-05-26 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'System Integration Test (E2E)'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Studio Configuration'}]
TD-5194 | Testing | Epic | Pilot | To Do | 2024-05-23 | 2024-06-25 |  | stephan.kuche |  | []
TD-5193 | Schema Configuration | Task | Application Implementation | To Do | 2024-05-09 | 2024-05-16 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5192 | Studio Configuration | Task | Application Implementation | To Do | 2024-05-09 | 2024-05-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional_Testing'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5191 | Reporting and Monitoring Configuration | Task | Application Implementation | To Do | 2024-05-09 | 2024-05-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5190 | Application Implementation | Epic | Pilot | To Do | 2024-05-09 | 2024-05-23 |  | stephan.kuche |  | []
TD-5189 | Integration Rules Implementation | Task | Integration Implementation | To Do | 2024-05-09 | 2024-05-10 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5188 | PO_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-05-09 | 2024-05-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5187 | Posting_Data_Inbound_Configuration | Task | Integration Implementation | To Do | 2024-05-09 | 2024-05-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5186 | Document Outbound Configuration | Task | Integration Implementation | To Do | 2024-05-09 | 2024-05-11 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5185 | Document Inbound Configuration | Task | Integration Implementation | To Do | 2024-05-09 | 2024-05-12 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5184 | Integration Implementation | Epic | Pilot | To Do | 2024-05-09 | 2024-05-12 |  | stephan.kuche |  | []
TD-5183 | Enrichment_Model_Configuration | Task | Machine Learning | To Do | 2024-05-09 | 2024-05-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5182 | Capturing Model Configuration | Task | Machine Learning | To Do | 2024-05-09 | 2024-05-30 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}]
TD-5181 | Machine Learning | Epic | Pilot | To Do | 2024-05-09 | 2024-05-30 |  | stephan.kuche |  | []
TD-5180 | MileStone_SoW and Solution Design Confirmation | Task | Design | To Do | 2024-05-08 | 2024-05-09 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Capturing Model Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Enrichment_Model_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Inbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Document Outbound Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Posting_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'PO_Data_Inbound_Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Integration Rules Implementation'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Reporting and Monitoring Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Studio Configuration'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Schema Configuration'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Functional Design'}]
TD-5179 | Functional Design | Task | Design | To Do | 2024-04-24 | 2024-05-08 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_SoW and Solution Design Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}]
TD-5178 | Design | Epic | Pilot | To Do | 2024-04-24 | 2024-05-09 |  | stephan.kuche |  | []
TD-5177 | MileStone_Training Data Confirmation | Task | Assessment | To Do | 2024-04-23 | 2024-04-24 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Functional Design'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5176 | Requirement Analysis | Task | Assessment | To Do | 2024-04-06 | 2024-04-23 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'MileStone_Training Data Confirmation'}, {'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5175 | Data Acquisition | Task | Assessment | To Do | 2024-04-06 | 2024-04-23 |  | stephan.kuche |  | [{'LinkType': 'is blocked by', 'LinkedIssueSummary': 'Project Set up'}]
TD-5174 | Assessment | Epic | Pilot | To Do | 2024-04-06 | 2024-04-24 |  | stephan.kuche |  | []
TD-5173 | MileStone_Kickoff Workshop | Task | Project Management | To Do | 2024-04-01 | 2024-04-02 |  | stephan.kuche |  | []
TD-5172 | Project Set up | Task | Project Management | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | [{'LinkType': 'blocks', 'LinkedIssueSummary': 'Data Acquisition'}, {'LinkType': 'blocks', 'LinkedIssueSummary': 'Requirement Analysis'}]
TD-5171 | Project Management | Epic | Pilot | To Do | 2024-04-01 | 2024-04-06 |  | stephan.kuche |  | []
TD-5170 | User Onboarding | Task | User Training | To Do | 2024-04-01 | 2024-07-30 |  | stephan.kuche |  | []
TD-5169 | User Training | Epic | Pilot | To Do | 2024-04-01 | 2024-07-30 |  | stephan.kuche |  | []
TD-5168 | Pilot | Project |  | To Do | 2024-04-01 | 2024-07-30 |  | stephan.kuche |  | []