## Gantt
| 2023-10-10 | 2023-10-15 | 2023-10-20 | 2023-11-11 | 2024-03-03 | 2023-11-30 | 2023-12-24 | 2024-01-01 | Duration (Days)
User Onboarding & Training | 2023-10-07 | 2023-10-17 | 2023-10-05 | [5 empty] | 10
Assessment & Design | 2023-10-05 | 2023-10-19 | 2023-10-19 | [5 empty] | 14
Providing Sampling Data | 2023-10-05 | 2023-10-26 | 2023-10-26 | [5 empty] | 21
ML Model Annotation | 2023-10-26 | 2023-11-09 | 2023-11-09 | [5 empty] | 14
ML Model Training | 2023-11-09 | 2023-11-16 | 2023-11-09 | 2023-11-16 |  |  |  |  | 7
Application Implementation | 2023-10-19 | 2023-11-09 | 2023-11-09 | 2023-11-19 |  |  |  |  | 21
Integration Implementation | 2023-10-19 | 2023-11-08 | [6 empty] | 20
Integration Validation (SIT) | 2023-11-08 | 2023-11-22 | 2023-11-22 | [5 empty] | 14
Solution Validation (UAT) | 2023-11-22 | 2023-12-06 | 2023-12-06 | [5 empty] | 14
Go Live & Hypercare | 2023-12-06 | 2023-12-26 | [6 empty] | 20
| Start | End | Milestone (activity level)
| Today: | 2024-03-03
(1st row = milestone dates) |  | Milestone
| Col 2 | Assessment Workshop
| Col 3 | Functional Workshop
| Col 4 | Technical Workshop
| Col 5 | Design Sign Off
| Col 6 | Today
| Col 7 | Functional Testing Completed
| Col 8 | Go Live Date Decision
| Col 9 | Go Live (not confirmed)
Dependencies | Assessment & Design |  | Col 4 (Tech Solution Confirmed)
Annotation
Studio
Duration Activity Level | Col 13